## All Site Info
Site | Grid Cell ID | NWS LI ID | Part of NMP? | Land Ownership Category | Landownership Detail | Site Type (New, Existing, Existing - Moved > 100 ft) | Latitude | Longitude | Elevation | County | State | Owner | Station Status | Station Status Note | Project Year (PY) | Installation Task Order & Fiscal Year | Installation Task Order Date Award | Contract Installation Deadline | O&M Period of Performance | Cultural Survey & Sec 106 Responsible Party | Section 106 Status | NEPA Status (Date REC Signed) | NRCS Soil Survey Status | Candidate Site Form_Site Report- Date Received | Station Report - Date Received | Annual Report - Date Received | Equipment Installation Complete | Data Transmitting
Bozeman | D-11 | BZNM8 | Y |  |  | Existing | 45.6621 | -111.0463 | 4927 | Gallatin | Montana | MT Climate Office | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-09 |  |  | USACE Contractor | Complete | Complete | 2021-09-10 | Y | Y | Y | 2020-10-30 | 2021-11-19
Absarokee W | G-12 | KEEM8 | Y | Private |  | Existing | 45.5573 | -109.6112 | 4608 | Stillwater | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-03 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-02 | 2021-11-19
Broadview E | I-10 | BDVM8 | Y | Private |  | Existing | 46.1282 | -108.7554 | 4095 | Yellowstone | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-14 | 2021-11-19
Crow Agency E | L-12 | CROM8 | Y | Tribal Lands | Crow indian reservation | Existing | 45.5861 | -107.4383 | 3119 | Big Horn | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-04 | 2021-11-19
Havre ARC | H-3 | HAEM8 | Y | University | Agriculture Research Center - Montana State University | Existing | 48.4891 | -109.7994 | 2721 | Hill | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-05-19 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-05-12 | 2021-11-19
Ingomar NE | M-9 | IGMM8 | Y |  |  | Existing | 46.6568 | -107.2238 | 3098 | Rosebud | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-04 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-12 | 2021-11-19
Melville SE | G-10 | MLVM8 | Y |  |  | Existing | 46.0015 | -109.8416 | 4710 | Sweet Grass | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Miles City | O-9 | MCYM8 | Y |  |  | Existing | 46.4054 | -105.9543 | 2718 | Custer | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-07 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-08-25 | 2021-11-19
Moccasin ARC | G-7 | MCIM8 | Y | University | Agriculture Research Center - Montana State University | Existing | 47.0585 | -109.9535 | 4257 | Judith Basin | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-05-13 | 2021-11-19
Roundup NE | J-9 | ROUM8 | Y |  |  | Existing | 46.5785 | -108.4243 | 3448 | Musselshell | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-06-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-09 | 2021-11-19
Sidney ARC | S-5 | SIYM8 | Y |  |  | Existing | 47.7823 | -104.2479 | 2260 | Richland | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-24 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Benton Lake W | D-5 | BLWM8 | Y | Private |  | Existing | 47.6907 | -111.4736 | 3706 | Cascade | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-08 |  |  |  | 2022-10-21 | 2022-11-01
Big Timber SE | G-11 | BTSM8 | Y | Private |  | Existing | 45.7435 | -109.8267 | 4423 | Sweet Grass | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-20 |  |  |  | 2022-08-23 | 2022-09-01
Coffee Creek N | G-6 | CFCM8 | Y | Private |  | Existing | 47.3935 | -110.1083 | 3739 | Fergus | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-07 |  |  |  | 2022-09-19 | 2022-09-22
Cooney Reservoir NW | H-12 | COOM8 | Y | Private |  | Existing | 45.4658 | -109.2597 | 4702 | Stillwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-21 |  |  |  | 2022-08-20 | 2022-09-01
Huntley ARC | J-11 | HNTM8 | Y | University | Agriculture Research Center - Montana State University | Existing | 45.9264 | -108.233 | 3055 | Yellowstone | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-06-03 |  |  |  | 2022-09-29 | 2022-11-01
MDA Oilmont | D-1 | OILM8 | Y | Private |  | Existing | 48.7816 | -111.6011 | 3597 | Toole | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-05-17 | 2022-08-27 |  |  | 2022-09-16 | 2022-09-22
MDA Toston | C-10 | TTNM8 | Y | Private |  | Existing | 46.1365 | -111.5432 | 4067 | Broadwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-19 | 2022-08-27 |  |  | 2022-09-21 | 2022-09-22
Midway Colony | C-4 | RADM8 | N | Private |  | New | 48.061 | -112.0077 | 3778 | Pondera | Montana | MT Climate Office | Complete | Replacement for Conrad ARC on TO2 | PY2 | TO2 MT (FY21) MOD | 2022-07-12 | 2022-10-30 | 2023-10-30 | USACE Contractor | Complete | Complete | 2022-05-18 | Complete |  |  | 2022-10-24 | 2022-11-01
Ashland E | O-12 |  | N | Federal | USFS | New | 45.5733 | -106.1432 | 3185 | Powder River | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Brady NE | D-4 |  | N | Private |  | New | 48.1032 | -111.6643 | 3376 | Pondera | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Busby S | M-12 |  | N | Private on Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.5186 | -106.9316 | 3582 | Big Horn | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Bynum W | B-4 |  | N | Private |  | New | 47.9572 | -112.4944 | 4439 | Teton | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Canyon Ferry N | C-8 |  | N | Federal | USFS | New | 46.6473 | -111.6222 | 4262 | Broadwater | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Chester SW | E-3 |  | N | Private |  | New | 48.4477 | -111.0376 | 3103 | Liberty | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Dupuyer N | B-3 |  | N | Private |  | New | 48.2956 | -112.5492 | 3890 | Pondera | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Forestgrove N | I-7 |  | N | Private |  | New | 47.1058 | -109.0888 | 4103 | Fergus | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Harlowton E | G-9 |  | N | Private |  | New | 46.413 | -109.7009 | 4086 | Wheatland | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Lame Deer E | N-12 |  | N | Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.6555 | -106.4879 | 4265 | Rosebud | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Aug 2022 | 2022-08-31 |  | 2022-10-01
Lavina N | I-9 |  | N | Private |  | New | 46.3989 | -108.9536 | 3684 | Golden Valley | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Lodge Grass W | L-13 |  | N | Private on Tribal Lands | Crow indian reservation | New | 45.3073 | -107.5154 | 3824 | Big Horn | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Loring SW | L-2 |  | N | Private |  | New | 48.7716 | -107.8779 | 2821 | Phillips | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Matador Ranch | K-5 |  | N | Non-Profit | The Nature Conservancy | New | 47.9264 | -108.3359 | 3027 | Phillips | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Molt S | I-11 |  | N | Private |  | New | 45.8414 | -108.9592 | 3899 | Stillwater | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Mosby NW | K-7 |  | N | Private |  | New | 47.0611 | -108.098 | 2989 | Petroleum | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Mosby S | K-8 |  | N | Private |  | New | 46.7823 | -107.9213 | 2805 | Petroleum | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Musselshell | K-9 |  | N | Private |  | New | 46.54 | -108.0218 | 3132 | Musselshell | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Otter E | O-13 |  | N | Federal | USFS | New | 45.2469 | -105.9845 | 3936 | Powder River | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Rapleje SW | H-11 |  | N | Private |  | New | 45.8858 | -109.4211 | 4710 | Stillwater | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Rothiemay W | H-9 |  | N | Private |  | New | 46.5349 | -109.348 | 4364 | Golden Valley | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Roy E | J-6 |  | N | Private |  | New | 47.3791 | -108.6778 | 3038 | Fergus | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Ryegate S | H-10 |  | N | Private |  | New | 46.1995 | -109.3111 | 4272 | Golden Valley | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Saco S | M-4 |  | N | Private |  | New | 48.2908 | -107.3912 | 2741 | Phillips | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Sand Springs NW | L-7 |  | N | Private |  | New | 47.1653 | -107.6384 | 3007 | Garfield | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Scobey NW | Q-2 |  | N | Private |  | New | 48.8602 | -105.4972 | 2467 | Daniels | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Sun River SE | C-6 |  | N | Private |  | New | 47.4118 | -111.7173 | 3596 | Cascade | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Turner N | K-2 |  | N | Private |  | New | 48.8743 | -108.3937 | 3073 | Blaine | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Twodot E | F-9 |  | N | Private |  | New | 46.4468 | -110.2055 | 4643 | Wheatland | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Valentine E | K-6 |  | N | Private |  | New | 47.358 | -108.2438 | 2904 | Petroleum | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
War Horse NW | J-7 |  | N | Private |  | New | 47.1472 | -108.5913 | 3151 | Petroleum | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Winnett SW | J-8 |  | N | Private |  | New | 46.9654 | -108.5024 | 3202 | Petroleum | Montana | MT Climate Office | In-Progress | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01
Fort Belknap S | J-3 |  | N | Tribal Lands | Fort Belknap Tribes | New | 48.4535 | -108.7704 | 2470 | Blaine | Montana | MT Climate Office | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. | PY4 | TO4 MT (FY23) Planned |  |  |  | Tribe
Hays N | J-4 |  | N | Tribal Lands | Fort Belknap Tribes | New | 48.1978 | -108.7055 | 2967 | Blaine | Montana | MT Climate Office | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. | PY4 | TO4 MT (FY23) Planned |  |  |  | Tribe
Amidon | U-9 | AIDN8 | N | Private |  | Existing | 46.4885 | -103.316 | 2883 | Slope | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-29 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-08 | 2021-11-19
Bowman | U-10 | BOMN8 | Y | Private |  | Existing | 46.1997 | -103.473 | 3032 | Bowman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-28 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-09 | 2021-11-19
Carson | Y-9 | CSRN8 | Y | Private |  | Existing | 46.443 | -101.3738 | 2107 | Grant | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-12 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-06-29 | 2021-11-19
Courtenay | AE-7 | CURN8 | N | Private |  | Existing | 47.2212 | -98.6799 | 1522 | Stutsman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-07-15 | 2021-11-19
Fortuna | T-2 | FTUN8 | N | Private |  | Existing | 48.9637 | -103.8058 | 2246 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-07 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-09 | 2021-11-19
Grenora | T-3 | GREN8 | N | Private |  | Existing | 48.735 | -103.8812 | 2108 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-08 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-08 | 2021-11-19
Hettinger | W-11 | HTGN8 | Y | University | NDSU | Existing | 46.0126 | -102.6453 | 2758 | Adams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-15 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-30 | 2021-11-19
Mott | W-10 | MATN8 | Y | Private |  | Existing | 46.3798 | -102.322 | 2473 | Hettinger | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-30 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-01 | 2021-11-19
Ray | U-3 | RAYN8 | Y | Private |  | Existing | 48.4009 | -103.169 | 2316 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-09 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-10 | 2021-11-19
Streeter | AC-8 | STRN8 | Y | University | NDSU | Existing | 46.718 | -99.4608 | 1992 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-19 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-07-20 | 2021-11-19
Williston | T-4 | WLLN8 | Y | University | NDSU | Existing | 48.1331 | -103.739 | 2132 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-22 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-15 | 2021-11-19
Hazen | X-7 | HAZN8 | Y | Private |  | Existing | 47.3018 | -101.6792 | 1849 | Mercer | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2021-08-23 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-10 | 2021-11-19
Oakes | AF-10 | OKNN8 | Y | University | NDSU | Existing | 46.0667 | -98.1031 | 1323 | Dickey | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2021-09-02 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-29 | 2021-11-19
Robinson | AB-7 | ROBN8 | Y | Private |  | Existing | 47.173 | -99.7982 | 1829 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2021-08-18 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-05 | 2021-11-19
Beach | T-8 | BCHN8 | Y | Private |  | Existing | 46.7894 | -103.9662 | 2932 | Golden Valley | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-07-06 | Complete | 2022-12-02 |  | 2022-06-09 | 2022-09-28
Dickinson | V-8 | DKSN8 | Y | University | NDSU | Existing | 46.8948 | -102.8131 | 2557 | Stark | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-08-03 | Complete | 2022-12-02 |  | 2022-06-10 | 2022-09-29
Edgeley | AE-9 | EDGN8 | Y | Private |  | Existing | 46.3192 | -98.7661 | 1649 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-09-12 | Complete | 2022-12-02 |  | 2022-09-02 | 2022-09-28
Garrison | X-5 | GANN8 | Y | Private |  | Existing | 47.7102 | -101.6795 | 2200 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-08-16 | Complete | 2022-12-02 |  | 2022-08-03 | 2022-09-28
Grassy Butte 2E | U-6 | GSBN8 | N | Private |  | Existing | 47.3865 | -103.2062 | 2688 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-07-21 | Complete | 2022-12-02 |  | 2022-07-12 | 2022-09-28
Jamestown | AD-8 | JSTN8 | Y | Private |  | Existing | 46.9064 | -98.9274 | 1639 | Stutsman | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-09-29 | Complete | 2022-12-02 |  | 2022-09-16 | 2022-09-28
Keene 5SW | V-5 | KEEN8 | N | Private |  | Existing | 47.8938 | -103.0482 | 2346 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-07-26 | Complete | 2022-12-02 |  | 2022-07-13 | 2022-09-28
Mandan | Z-8 | MMDN8 | Y | Federal | USDA | Existing | 46.7736 | -100.9139 | 1907 | Morton | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-08-18 | Complete | 2022-12-02 |  | 2022-08-15 | 2022-09-28
Marion | AF-9 | MARN8 | Y | Private |  | Existing | 46.5645 | -98.3276 | 1453 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-08-25 | Complete | 2022-12-02 |  | 2022-08-10 | 2022-09-28
Steele | AB-8 | SEEN8 | N | Private |  | Existing | 46.894 | -99.9927 | 1862 | Kidder | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-09-29 | Complete | 2022-12-02 |  | 2022-09-23 | 2022-09-28
Turtle Lake | Z-6 | TURN8 | Y | Private |  | Existing | 47.5679 | -100.9153 | 1927 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-08-16 | Complete | 2022-12-02 |  | 2022-08-02 | 2022-09-28
Wishek | AC-10 | WISN8 | Y | Private |  | Existing | 46.2599 | -99.6658 | 2219 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-08-26 | Complete | 2022-12-02 |  | 2022-08-15 | 2022-09-28
Zeeland | AC-11 | ZELN8 | N | Private |  | Existing | 46.0133 | -99.6877 | 2070 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/8/2021 | 2022-08-26 | Complete | 2022-12-02 |  | 2022-08-16 | 2022-09-28
Carrington | AD-6 | CRGN8 | Y | University | NDSU | Existing | 47.5086 | -99.1323 | 1561 | Foster | North Dakota | NDAWN | Complete | Install 2021 | na | Not on USACE Task Order | na | na | na |  | na | na | na | na | na | na | Y | 2021-11-19
Dooley | S-2 | DOOM8 | Y | Private |  | Existing | 48.8337 | -104.3846 |  | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-30 | Complete | 2022-12-02 |  | 2022-06-23 | 2022-10-28
Froid | S-4 | FROM8 | Y | Federal | USDA | Existing | 48.2579 | -104.4967 |  | Roosevelt | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-29 | Complete | 2022-12-02 |  | 2022-06-23 | 2022-10-28
Redstone | R-2 | RSTM8 | Y | Private |  | Existing | 48.8246 | -104.8417 |  | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-28 | Complete | 2022-12-02 |  | 2022-06-23 | 2022-10-28
Davis Dam 2NW | T-9 |  | N | Private |  | New | 46.5641 | -103.6971 | 2906 | Slope | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Fairfield | U-7 |  | N | Private |  | Existing | 47.1253 | -103.2432 | 2682 | Billings | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-10-15
Glen Ullin | X-8 |  | N | Private |  | New | 46.8045 | -102.0759 | 2450 | Morton | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-10-15
Linton | AB-10 |  | Y | Private |  | Existing | 46.3268 | -100.2809 | 1966 | Emmons | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-10-15
Marmarth 2N | T-10 |  | N | Private |  | New | 46.3228 | -103.9374 | 2840 | Slope | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
McKenzie 2E | AA-8 |  | N | Private |  | New | 46.8222 | -100.3617 | 1773 | Burleigh | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
New England 5W | V-9 |  | N | Private |  | New | 46.5264 | -102.968 | 2718 | Slope | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Pick City 8SW | Y-6 |  | N | Private |  | New | 47.4747 | -101.6123 | 2045 | Mercer | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Poker Jim | T-6 |  | N | Private |  | Existing | 47.5025 | -103.6559 | 2092 | McKenzie | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Pretty Rock 2E | X-10 |  | N | Private |  | New | 46.1597 | -101.7705 | 2514 | Grant | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-10-15
Sanger | Z-7 |  | N | Private |  | New | 47.1668 | -100.9891 | 1689 | Oliver | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-10-15
Sentinel Butte 10N | T-7 |  | N | Private |  | Existing | 47.0669 | -103.7933 | 2736 | Golden Valley | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Shell Lake | X-4 |  | N | Private |  | Existing | 48.1501 | -102.0727 | 2058 | Mountrail | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Wing | AA-7 |  | N | Private |  | New | 47.2719 | -100.3303 | 1973 | Burleigh | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Ypsilanti | AE-8 |  | N | Private |  | New | 46.7764 | -98.5236 | 1483 | Stutsman | North Dakota | NDAWN | In-Progress | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 |  | 2022-08-27
Boyd 1 | AF-20 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.8407 | -98.5042 | 1583 | Boyd | Nebraska | NE Mesonet | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. |  | Unk. Timeline |  |  |  | USACE Contractor
Boyd 2 | AE-20 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.9662 | -99.1393 | 2105 | Boyd | Nebraska | NE Mesonet | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. |  | Unk. Timeline |  |  |  | USACE Contractor
Cedar 2 | AI-20 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.7494 | -97.3975 | 1520 | Cedar | Nebraska | NE Mesonet | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. |  | Unk. Timeline |  |  |  | USACE Contractor
Cherry 1 | Y-21 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.6154 | -101.7244 | 3619 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. |  | Unk. Timeline |  |  |  | USACE Contractor
Knox 2 | AG-21 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.4909 | -98.2605 | 1556 | Knox | Nebraska | NE Mesonet | Candidate | Submitted as candidate site Oct 2021 - In-progress with Cultural/Env. |  | Unk. Timeline |  |  |  | USACE Contractor
Sheridan 1 | X-22 |  |  | State | State Educational Lands and Funds - Leased Public | New | 42.2794 | -102.1656 | 4130 | Sheridan | Nebraska | NE Mesonet | In-Progress | Submitted at Candidate 2021 - Sub for Long Pine - Install 2022 | PY2 | TO 1 NE Mod. | 2022-11-01 | 2022-12-31 | 2023-12-31 | USACE Contractor | Complete | Complete | On list for 2023 | 2021-10-15
Brookings | AJ-15 | BKMS2 | Y |  |  | Existing | 44.325 | -96.7685 | 1640 | Brookings | South Dakota | SD Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-08 |  |  | USACE Contractor | Complete | Complete | 2019-06-13 | 2022-08-27 | Y | Y | Y | 2021-11-19
Bowdle | AC-12 | BWLS2 | Y | City | Non-federal airport property | Existing | 45.4388 | -99.6733 | 1965 | Edmunds | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Caputa | V-17 | CPTS2 | Y |  |  | Existing | 44.0008 | -103.0008 | 2931 | Pennington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-07-30 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-18 | 2021-11-19
Edgemont | T-19 | EDTS2 | Y |  |  | Existing | 43.4737 | -103.9717 | 3710 | Fall River | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-07-29 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-20 | 2021-12-15
Highmore | AD-15 | HIHS2 | Y |  |  | Existing | 44.5256 | -99.4601 | 1879 | Hyde | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-06-19 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-22 | 2021-12-23
Leola | AE-11 | LLAS2 | Y |  |  | Existing | 45.7165 | -98.9311 | 1571 | McPherson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Oacoma | AD-17 | OCMS2 | Y |  |  | Existing | 43.7982 | -99.4156 | 1443 | Lyman | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-07-02 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-04 | 2021-11-19
Union Center | W-15 | UNIS2 | Y | City | Non-federal airport property | Existing | 44.5665 | -102.671 | 2938 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2022 | 2021-07-22 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-02 | 2021-12-15
White River | AA-18 | WRIS2 | Y | City | Non-federal airport property | Existing - Moved > 100ft | 43.5586 | -100.7423 | 2140 | Mellette | South Dakota | SD Mesonet | Complete | Installed in 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Staff | Complete | Complete 9/10/2021 | 2022-06-09 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-11-24 | 2021-12-15
Beresford | AJ-19 | BFMS2 | Y | University | SDSU | Existing - Moved > 100ft | 43.0404 | -96.9011 | 1278 | Clay | South Dakota | SD Mesonet | Complete | Install 2021; Sub for Martin on T01 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2021 | 2021-04-13 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-09 | 2021-12-23
Timber Lake | Z-12 | TIMS2 | Y | City |  | Existing | 45.4166 | -101.085 | 2196 | Dewey | South Dakota | SD Mesonet | Complete | Install 2021; Sub For Faulkton on TO1 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2021 | 2019-06-27 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-18 | 2021-12-15
Cottonwood | X-17 | CTWS2 | Y |  |  | Existing | 43.9599 | -101.8539 | 2365 | Jackson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-05 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Groton | AG-12 | GOTS2 | Y |  |  | Existing | 45.5735 | -98.0301 | 1309 | Brown | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
South Shore | AI-13 | SHSS2 | Y |  |  | Existing | 45.1055 | -97.1024 | 1850 | Codington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
Sturgis | U-16 | STMS2 | Y |  |  | Existing | 44.4245 | -103.3793 | 3237 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-25 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Antelope | U-12 | ATRS2 | Y | Private |  | Existing | 45.5193 | -103.2888 | 2903 | Harding | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/19/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Flandreau | AJ-16 | FLNS2 | Y | Private |  | Existing | 44.0867 | -96.5849 | 1624 | Moody | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/31/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Hamill | AC-18 | HMLS2 | Y | Private |  | Existing | 43.5938 | -99.7122 | 1863 | Tripp | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/24/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Nisland | U-15 | NISS2 | Y | Federal | BOR | Existing | 44.6783 | -103.5606 | 2906 | Butte | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/25/2021 | 6/12/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Rosebud | AA-19 | RBMS2 | Y | Tribal Lands | Rosebud Sioux Tribe | Existing | 43.2002 | -100.7208 | 2808 | Todd | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | Rosebud Tribe | Complete | Complete 8/5/2021 | 9/1/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Sioux Falls | AJ-18 | SFSS2 | Y | Private |  | Existing | 43.5048 | -96.7623 | 1407 | Minnehaha | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/14/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
White Lake | AE-17 | WTES2 | Y | Private |  | Existing | 43.7372 | -98.6936 | 1637 | Aurora | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 |  | Complete | Complete 3/7/2021 | 8/19/2022 (Orig. Sampling in 2019) |  |  |  | Y | 2022-08-20
Jewel Cave | T-18 | JWLS2 | Y | Federal | NPS - Jewel Cave National Monument | Existing | 43.7343 | -103.8278 | 5672 | Custer | South Dakota | SD Mesonet | In-Progress | Awarded in Sept 2021; Extended Installation POP to 2023 | PY2 | TO3 SD (FY21) Mod. | 2022-08-15 | 2023-09-30 | 2024-09-30 | NPS | Complete | Complete 8/30/2021 |  | 2022-08-27
Hayes 7SW | Z-16 | HAMS2 | N | Private | FPPA Statewide Importance Farmland | New | 44.3123 | -101.1292 | 2025 | Stanley | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-13 | 2022-08-27
Lecther 2ENE | AG-17 | LCMS2 | N | Private |  | New | 43.9029 | -98.1096 | 1306 | Sanborn | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-12 | 2022-08-27
Milesville 11W | X-15 | MVMS2 | N | Private | FPPA Prime Farmland | New | 44.4749 | -101.8991 | 2338 | Haakon | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-04 | 2022-08-27
Norris 10NNE | Z-18 | NOMS2 | N | Private |  | New | 43.5998 | -101.1013 | 2454 | Mellette | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-06 | 2022-08-27
Onida 13WSW | AB-15 | ONMS2 | N | Private on Tribal Lands | Crow Creek Indian Reservation; FPPA Prime Farmland | New | 44.6463 | -100.3202 | 1757 | Sully | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-13 | 2022-08-27
Provo 11S | T-20 | PVMS2 | N | Private |  | New | 43.0375 | -103.7986 | 3797 | Fall River | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-17 | 2022-08-27
Ralph 11NE | V-11 | RAMS2 | N | Private |  | New | 45.9061 | -102.9228 | 2742 | Perkins | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-20 | 2022-08-27
Carpenter 11WSW | AG-15 |  |  | Private |  | New | 44.6035 | -98.1298 | 1298 | Beadle | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Colome 4NNE | AC-19 |  |  | Private |  | New | 43.3141 | -99.693 | 2097 | Tripp | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Dallas 7S | AD-19 |  |  | Private |  | New | 43.1374 | -99.4933 | 2189 | Gregory | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Kennebec 6SSE | AC-17 |  |  | Private |  | New | 43.816 | -99.8254 | 1772 | Lyman | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Long Lake 4NW | AD-11 |  |  | Private |  | New | 45.8998 | -99.2611 | 1961 | McPherson | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Lower Brule 2WNW | AC-16 |  | N | Private |  | New | 44.0822 | -99.6111 | 1777 | Lyman | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Complete | 2022-08-31 |  | 2022-11-15
Lowry 2S | AB-13 |  |  | Private |  | New | 45.2816 | -99.9774 | 2104 | Walworth | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Ludlow 16W | T-11 |  |  | Private |  | New | 45.8268 | -103.7172 | 3134 | Harding | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Menno 7ESE | AH-19 |  |  | Private |  | New | 43.2109 | -97.4523 | 1477 | Hutchinson | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Midland 3ENE | Z-17 |  |  | Private |  | New | 44.0851 | -101.091 | 1851 | Haakon | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Mound City 4SSW | AB-12 | MCMS2 | Y | Private - Easement | FWS Easement for Sand Lake Wetland Management District; FPPA Prime Farmland | Existing | 45.6715 | -100.1148 | 1746 | Campbell | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 |  | 2022-11-15
Mount Vernon | AF-17 |  | N | Private |  | New | 43.7173 | -98.2793 | 3729 | Davison | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 |  | 2022-11-15
Oelrichs 11ESE | V-20 |  | N | Private |  | New | 43.1003 | -103.0547 | 3353 | Fall River | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 |  | 2022-11-15
Oelrichs 11SSW | U-20 |  |  | Private |  | New | 43.0409 | -103.3476 | 3592 | Fall River | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Prairie City 15SSW | V-13 |  |  | Private |  | New | 45.3388 | -102.9195 | 2835 | Perkins | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Raymond 5ENE | AG-14 |  |  | Private |  | New | 44.9374 | -97.8464 | 1736 | Clark | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Redig 3N | U-13 |  |  | Private |  | New | 45.3195 | -103.5495 | 3168 | Harding | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Spearfish 4NNW | T-15 |  |  | Private - Easement | NRCS EQIP Program | New | 44.5657 | -103.9164 | 3407 | Lawrence | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Spring Creek 12WNW | Z-19 |  | N | Private on Tribal Lands | Pine Ridge Reservation | New | 43.206 | -101.2295 | 5423 | Bennett | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 |  | Complete | 2022-08-31 |  | 2022-11-15
Vivian 12S | AB-18 |  |  | Private |  | New | 43.7508 | -100.2963 | 1919 | Lyman | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Volga | AI-15 | VGAS2 | Y | University | SDSU | Existing | 44.3042 | -96.9189 | 1642 | Brookings | South Dakota | SD Mesonet | In-Progress | Resubmittal - Replacement for Gann Valley; Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2021-08-30 | 2019-07-01
Woonsocket 4NNW | AF-16 |  |  | Private |  | New | 44.1113 | -98.3103 | 1315 | Sandorn | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Bath 3W | AF-12 |  |  | Commercial |  | New | 45.4722 | -98.3785 | 1297 | Brown | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Oct 2021; Pending Issues | PY3 | TO6 SD (FY23) Planned |  |  |  | USACE Contractor | Complete | Complete
Chelsea 6S | AE-13 |  |  | Private |  | New | 45.0847 | -98.7433 | 1351 | Faulk | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Oct 2021; Pending Landowner issues | PY3 | TO6 SD (FY23) Planned |  |  |  | USACE Contractor | Complete | Complete
Ipswich 5SSW | AD-12 |  |  | Private |  | New | 45.3759 | -99.0707 | 1553 | Edmunds | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Oct 2021; Pending Landowner issues | PY3 | TO6 SD (FY23) Planned |  |  |  | USACE Contractor | Complete | Complete
Newell 13NNW | U-14 |  | N | Private |  | New | 44.9002 | -103.4878 |  | Butte | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Nov 2021; Waiting on RE | PY3 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete
Onaka 4NNW | AC-13 |  |  | Private |  | New | 45.245 | -99.4815 | 1878 | Edmunds | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Oct 2021; Pending Landowner issues | PY3 | TO6 SD (FY23) Planned |  |  |  | USACE Contractor | Complete | Complete
Meadow | X-12 |  | N | Private on Tribal Lands | Standing Rock Reservation | New | 45.5735 | -101.9842 |  | Corson | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Nov 2021; Pending Issues |  | Unk. Timeline
Mobridge 8WSW | AA-12 |  | N | Private on Tribal Lands | Standing Rock Reservation | New | 45.4878 | -100.5773 |  | Corson | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Nov 2021; Pending Issues |  | Unk. Timeline
Wessington 3W | AE-15 |  |  | Private - Easement | NRCS Conservation Reserve Program | New | 44.4592 | -98.7614 |  | Hand | South Dakota | SD Mesonet | Candidate | Submitted as candidate site Oct 2021; Resubmitted |  | Unk. Timeline
Fort_Washakie | I-20 | FWMW4 | N | Tribal Lands | Wind River Tribe | New | 43.005 | -108.8803 | 5571 | Fremont | Wyoming | Wyoming Mesonet | Available | 106 and NEPA complete. Waiting on RE. | PY2 | TO1 WY (FY20) MOD |  |  |  | USACE Staff | Complete | 2022-01-20 | Summer 2023
Carlile 2S | R-16 | CAMW4 | N | Private |  | New | 44.4485 | -104.8021 | 4344 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | Summer 2023 | 2022-10-15
Crook 3 | S-15 |  | N | Private |  | New | 44.5871 | -104.2483 | 4021 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Crook 4 | R-15 |  | N | Private |  | New | 44.7389 | -104.6962 | 4442 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Crook 5 | S-16 |  | N | Private |  | New | 44.1959 | -104.2952 | 5415 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Crook 6 | S-14 |  | N | Private |  | New | 44.8605 | -104.5444 | 3613 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Crook 7 | Q-14 |  | N | Private |  | New | 44.953 | -105.0407 | 3895 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Devils Tower 16WNW | Q-15 | DTMW4 | N | Private |  | New | 44.713 | -105.014 | 4012 | Crook | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | Summer 2023 | 2022-10-15
Newcastle 13SSW | S-18 | NCMW4 | N | Private |  | New | 43.6662 | -104.2619 | 3804 | Weston | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | Summer 2023 | 2022-08-27
Osage 31SW | R-18 | RKMW4 | N | Private |  | New | 43.6795 | -104.8825 | 4305 | Weston | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | Summer 2023 | 2022-08-27
Upton 9S | R-17 | UPMW4 | N | Private |  | New | 43.9643 | -104.6376 | 4373 | Weston | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | Summer 2023 | 2022-10-15
Weston B | S-17 |  | N | Private |  | New | 43.9938 | -104.3791 | 4544 | Weston | Wyoming | Wyoming Mesonet | In-Progress | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | Summer 2023 | 2022-10-15
Powell | I-14 | PLMW4 | N | Univeristy | UWY |  | 44.7764 | -108.759 | 4372 | Park | Wyoming | Wyoming Mesonet | Complete | Install 2021 | PY1 | TO1 WY (FY20) | 2020-09-28 | 2021-09-30 | 2022-09-30 |  | Complete | Complete | 2022-08-03 | 2022-02-24 | 2022-02-24 | 2022-03-29 | 2021-12-17 | Y
Sheridan | M-14 | SHMW4 | N | Univeristy | UWY |  | 44.8407 | -106.839 | 3738 | Sheridan | Wyoming | Wyoming Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-10 |  |  | USACE Contractor | Complete | Complete | 2022-07-28 | Y | Y | Y | Y | Y
Cowley 4NNE | J-14 | CYMW4 | N | Federal | BOR | New | 44.9291 | -108.4324 | 4121 | Big Horn | Wyoming | Wyoming Mesonet | In-Progress | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-10-12
Pavillion 13W | I-19 | DDMW4 | N | Federal | BOR | New | 43.2314 | -108.9515 | 5682 | Fremont | Wyoming | Wyoming Mesonet | In-Progress | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2021-08-30 | 2022-10-19 | 2022-08-27
Shoshoni 6NNW | J-19 | BYMW4 | N | Federal | BOR | New | 43.3239 | -108.1331 | 4761 | Fremont | Wyoming | Wyoming Mesonet | In-Progress | Install 2022 | PY2 | TO2 WY (FY21) | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-09-21
Wapiti 6E | I-15 | BBMW4 | N | Federal | BOR | New | 44.4817 | -109.3083 | 5433 | Park | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 1/7/2022 | 2022-08-17 |  |  |  | 2022-09-15 | 2022-12-22
Conrad N | C-3 |  |  | Private | Private | New | 48.3045 | -111.9243 | 3704 | Pondera | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Springdale N | F-11 |  |  | Private | Private | New | 45.7732 | -110.2016 | 4490 | Sweet Grass | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Big Sandy NW | G-3 |  |  | Private | Private | New | 48.2416 | -110.3217 | 2858 | Choteau | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hogeland SW | J-2 |  |  | Private | Private | New | 48.8163 | -108.7802 | 3334 | Blaine | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Glasgow SW | N-4 |  |  | Private | Private | New | 48.1244 | -106.7489 | 2272 | Valley | Montana | MT Climate Office | Candidate | USACE performed Cultural Survey in Aug 2022 | PY4
Tampico N | N-3 |  |  | Private | Private | New | 48.3646 | -106.8509 | 2158 | Valley | Montana | MT Climate Office | Candidate | USACE performed Cultural Survey in Aug 2023 | PY4
Ophiem S | O-2 |  |  | Private | Private | New | 48.7878 | -106.3862 | 3117 | Valley | Montana | MT Climate Office | Candidate | USACE performed Cultural Survey in Aug 2024 | PY4
Larslan SW | O-3 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5267 | -106.243 | 2936 | Valley | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Nashua NE | O-4 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1961 | -106.3213 | 2380 | Valley | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Volt N | P-3 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5423 | -105.6621 | 2392 | Roosevelt | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Wolf Point NW | P-4 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1745 | -105.7379 | 2231 | Roosevelt | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Bredette NE | Q-3 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5506 | -105.2589 | 2582 | Roosevelt | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Poplar N | Q-4 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1781 | -105.2168 | 2137 | Roosevelt | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Medicine Lake W | R-3 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.52 | -104.731 | 2474 | Sheridan | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Fort Kipp NW | R-4 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.2234 | -104.7713 | 2110 | Roosevelt | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Billings S | J-12 |  |  | Private | Private | New | 45.6259 | -108.4906 | 4039 | Yellowstone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Buffalo Lake E | B-1 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.8536 | -112.6562 | 4121 | Glacier | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Carter N | E-4 |  |  | Private | Private | New | 48.0223 | -110.993 | 3492 | Choteau | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Christina W | H-6 |  |  | Private | Private | New | 47.4245 | -109.5207 | 3606 | Fergus | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Dog Gun Lake E | A-2 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.3778 | -113.0621 | 4836 | Glacier | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Fox Crossing SW | F-1 |  |  | Private | Private | New | 48.8994 | -110.7485 | 3136 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hill S | E-2 |  |  | Private | Private | New | 48.6887 | -111.1279 | 3606 | Liberty | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Inverness N | F-2 |  |  | Private | Private | New | 48.7189 | -110.7097 | 3208 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Inverness S | F-3 |  |  | Private | Private | New | 48.3754 | -110.7126 | 3065 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Lake Thibadeau W | H-2 |  |  | Private | Private | New | 48.746 | -109.6417 | 2627 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Mission Lake S | B-2 |  |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.5273 | -112.6334 | 4147 | Glacier | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Mosby SE | L-8 |  |  | Private | Private | New | 46.9362 | -107.6511 | 3176 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Mt Lebanon SE | E-1 |  |  | Private | Private | New | 48.8523 | -111.0375 | 4121 | Liberty | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Sunburst NW | C-1 |  |  | Private | Private | New | 48.915 | -112.0222 | 3743 | Toole | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Wetzel NE | A-1 |  |  | Private | Private | New | 48.7795 | -113.1185 | 4459 | Glacier | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Winifred NE | I-5 |  |  | Private | Private | New | 47.7319 | -109.2019 | 3220 | Fergus | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Big Sandy SE | G-4 |  |  | Private | Private | New | 48.034 | -110.0359 | 3099 | Choteau | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Bowmans Corner NW | B-6 |  |  | Private | Private | New | 47.308 | -112.1728 | 4267 | Lewis & Clark | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Judith Gap | G-8 |  |  | Private | Private | New | 46.7189 | -109.7684 | 4646 | Judith Basin | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Alexandria 6SW | AG-18 |  |  | Private | private | New | 43.655 | -97.8942 | 1291 | Hanson | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Artesian 13N | AG-16 |  |  | Private | private | New | 44.1895 | -97.9713 | 1318 | Sanborn | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Blunt 11S | AB-16 |  |  | University | SDSU | New | 44.3541 | -99.9997 | 1762 | Hughes | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Camp Crook 9SSW | T-13 |  |  | Private | private | New | 45.4235 | -104.0168 | 3287 | Harding | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Cherry Creek 10NE | Y-15 |  |  | Private on Tribal Lands | Cheyenne River Reservation | New | 44.7079 | -101.3658 | 2042 | Ziebach | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Erwin 5W | AH-15 |  |  | Private | private | New | 44.4951 | -97.5325 | 1773 | Kingsbury | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Fairburn 15ENE | V-18 |  |  | Private | private | New | 43.7387 | -102.9226 | 2939 | Custer | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Fort Pierre 6WSW | AA-16 |  |  | Private | private | New | 44.3213 | -100.4756 | 1801 | Stanley | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hurley 5SW | AI-19 |  |  | Private | private | New | 43.2351 | -97.1717 | 1290 | Turner | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Iona 5S | AD-18 |  |  | Private | private | New | 43.4642 | -99.439 | 1932 | Gregory | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Isabel 3WSW | Y-13 |  |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.3864 | -101.4925 | 2360 | Ziebach | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Kadoka 5WNW | Y-17 |  |  | Private | private | New | 43.874 | -101.5916 | 2355 | Jackson | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Lantry 5NNW | Y-14 |  |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.087 | -101.4843 | 2329 | Dewey | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Martin 4ENE | Y-19 |  |  | Private | private | New | 43.1991 | -101.6512 | 3197 | Bennett | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Mission Ridge 14SSE | AA-15 |  |  | Private | private | New | 44.4939 | -100.6937 | 2061 | Stanley | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Murdo 9NNW | AA-17 |  |  | Private | private | New | 44.0106 | -100.7678 | 2246 | Jones | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Opal 8WNW | V-14 |  |  | Private | private | New | 44.9196 | -102.7539 | 2645 | Meade | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Orland 5ENE | AI-17 |  |  | Private | private | New | 43.9146 | -97.0898 | 1752 | Lake | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Parade | Z-14 |  |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.0239 | -101.0771 | 2412 | Dewey | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Ridgeview 8ENE | AA-13 |  |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.1455 | -100.673 | 2001 | Dewey | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Rockham 6SSE | AE-14 |  |  | Private | private | New | 44.8223 | -98.7965 | 1365 | Hand | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Scenic 6ESE | W-18 |  |  | Private | private | New | 43.7574 | -102.4421 | 2679 | Pennington | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Seneca 15SSE | AD-14 |  |  | Private | private | New | 44.8572 | -99.4144 | 1921 | Hyde | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Smithwick 4SW | U-19 |  |  | Private | private | New | 43.2666 | -103.2909 | 3365 | Fall River | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Springfield 8WNW | AG-20 |  |  | Private | private | New | 42.8805 | -98.0471 | 1429 | Bon Homme | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Union Center 16NW | V-15 |  |  | Private | private | New | 44.7047 | -102.8964 | 2810 | Meade | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Wall Lake 7WSW | AI-18 |  |  | Private | private | New | 43.4885 | -97.0795 | 1469 | Turner | South Dakota | SD Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hofflund | U-4 | HOFN8 |  | University | NDSU | Existing | 48.1644 | -103.1082 | 1906 | Williams | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Pyramid Park | U-8 |  |  | University | NDSU | New | 46.7814 | -103.3584 | 2620 | Billings | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Cedar Lake 3W | V-10 |  |  | Private | Private | New | 46.2839 | -103.0284 | 2766 | Slope | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Manning 4SW | V-7 |  |  | University | NDSU | New | 47.1925 | -102.8325 | 2442 | Dunn | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Powers Lake 7SE | W-3 | POLN8 |  | Private | Private | Existing | 48.4841 | -102.5608 | 2298 | Mountrail | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Liberty 5E | W-5 | LBTN8 |  | Private | Private | Existing | 47.9143 | -102.2162 | 2041 | Mountrail | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Mandaree 9E | W-6 |  |  | Private | Private | New | 47.6896 | -102.4989 | 2130 | Dunn | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Lefor 10SE | W-9 |  |  | Private | Private | New | 46.5883 | -102.3851 | 2564 | Hettinger | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Zap 11N | X-6 |  |  | Private | Private | New | 47.4367 | -101.9714 | 2188 | Mercer | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Elgin 10NW | X-9 |  |  | Private | Private | New | 46.5011 | -101.9861 | 2387 | Grant | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Max 3N | Y-5 |  |  | Private | Private | New | 47.87 | -101.3143 | 2180 | Ward | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
New Salem 6SE | Y-8 |  |  | Private | Private | New | 46.7678 | -101.342 | 2186 | Morton | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Ross 9SE | W-4 | RSSN8 |  | Private | Private | New | 48.1962 | -102.4653 | 2341 | Mountrail | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Picardville 6SW | AA-6 |  |  | Private | Private | New | 47.4154 | -100.673 | 1896 | Sheridan | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Livona 5S | AA-9 |  |  | Private | Private | New | 46.4359 | -100.5677 | 1690 | Emmonds | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hurdsfield NW | AB-6 |  |  | Private | Private | New | 47.4511 | -99.9372 | 1903 | Wells | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Bremen 3W | AC-5 |  |  | Private | Private | New | 47.7458 | -99.3184 | 1563 | Wells | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Wirch 7NW | AD-10 |  |  | Private | Private | New | 46.1432 | -99.0659 | 1971 | McIntosh | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Buford 3SE | T-5 |  |  | Private | Private | New | 47.9707 | -103.9259 | 1868 | Wiliams | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Dull Center | Q-19 |  |  | Private | private | new | 43.2854 | -105.1376 | 4782 | Converse | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Jenne Trail | P-19 |  |  | Private | private | new | 43.378 | -105.5253 | 4845 | Converse | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Round Rock | O-19 |  |  | Private | private | new | 43.4138 | -105.8888 | 5420 | Converse | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Granite Peak | Q-20 |  |  | Private | private | new | 42.9384 | -105.2259 | 5040 | Converse | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Little Fork | M-15 |  |  | Private | private | new | 44.4898 | -106.8214 | 4836 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Watt | N-15 |  |  | Private | private | new | 44.4922 | -106.6011 | 4502 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Tipperary | N-16 |  |  | Private | private | new | 44.4079 | -106.3951 | 4098 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hollcroft | O-15 |  |  | Private | private | new | 44.5263 | -106.1102 | 3817 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Blue Butte | O-16 |  |  | Private | private | new | 44.2127 | -106.1034 | 4054 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Camino | N-17 |  |  | Private | private | new | 44.0091 | -106.4436 | 4806 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Harrison 2SW | T-21 |  |  | University | Board of Regents (UNL) | New | 42.664 | -103.898 | 4910 | Sioux | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Whitney 4SW | U-21 |  |  | University | Board of Regents (UNL) | New | 42.7423 | -103.3179 | 3492 | Dawes | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Marsland 6S | U-22 |  |  | State | Nebraska School Lands | New | 42.3557 | -103.3313 | 4525 | Box Butte | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hay Spring 12W | V-21 |  |  | State | Nebraska Board of Educational Lands and Funds | New | 42.6146 | -102.9095 | 4236 | Dawes | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hemingford 9NE | V-22 |  |  | State | Nebraska School Lands | New | 42.4087 | -102.9395 | 4088 | Box Butte | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Alliance 3SW | V-23 |  |  | State | Nebraska School Lands | New | 42.058 | -102.894 | 3959 | Box Butte | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Rushville 2SE | W-21 |  |  | State | Nebraska Board of Educational Lands and Funds | New | 42.7122 | -102.4373 | 3811 | Sheridan | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Hay Springs 22S | W-22 |  |  | University | Board of Regents (UNL) | New | 42.3697 | -102.6491 | 3924 | Sheridan | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Gordon 13SE | X-21 |  |  | University | Board of Regents (UNL) | New | 42.6483 | -102.0689 | 3625 | Sheridan | Nebraska | NE Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Falxa | O-17 |  |  | Private | private | New | 44.0276 | -106.1749 | 4144 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4
Worland | K-17 | WRMW4 | N | Federal | BOR | New | 44.0026 | -107.905 | 4203 | Washakie | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | [5 empty] | Complete | 2022-01-07 | 2022-08-24 |  |  |  | 2022-09-22 | 2022-12-22

## Categories
Attribute | Site | NWS LI Name | Part of NMP? | Land Ownership | Site Type | Orig Lat | Orig.Lon | Proposed Lat | Proposed Long | Elevation | County | State | Owner | Retrofit Category | Site Status | Task Order | Date Award | Contract Deadline | Operational Date | Sec 106 and NEPA Responsible party | Sec 106 Status | Sec 106 APE (Area of Potential Effect) | Nepa/REC | NRCS Soil Characterization | Site Report | Station Report | Annual Report | Installation Complete | Data Transmission
Description | Identifier given by states - some names end in a number and direction which is the distance in miles and cardinal direction to a major city | 5-digit name given by the National Weather Service for sites. For sites that are not yet in the network- these are proposed names by the Mesonet | Is the site part of the National Mesonet Program? | Type of land ownership where the station is e.g. private lands, state lands, public lands | Describes if site is a new or exisiting site or existing but moved more than 100 feet. | Orginal latitude at existing site | Original Longitude at existing site | Proposed Latitude for new site | Proposed Longitude for new site | Elevation in feet of station location based on Proposed Lat and Proposed Long. | County which station is in. | State that site is located | Name of Climate Center that Owns the Station | The percentage of a site being replaced base on cost. Category 1 - 80%; Category 2 - 50 to 80% percent; Category 3 - 20 to 50%; Category 4 - less than 20%. | The category of retrofit of the station. Future Retrofit - Exisiting site within the Network that may or may not be retrofitted. Retrofit complete- A retrofit that is already complete and operational. Retrofit In-Progress - Site is Awarded on a Task Order. Retrofit Planned - Site eligibility is being assessed fo future task order. | Name of Task Order (TO) that site is included on e.g. TO2 for ND and SD, T01 for NE, etc. | Date that the SATOC was awarded. Null means not yet awarded. | Date that site MUST be operational according to USACE Contract. Null means not yet awarded or unknown. | Date that the Mesonets have stated in their work plans that they will have the site operational by. | Repsonsible Party for Completing NEPA and Sec 106 Work. | Where are we at in the cultural clearance process | Type (Size) of Sec 106 Survey done based on area. Existing site is 1 -acre. Moved more that 100 feet from exisiting site or new site is 3- acres. | Date that REC (NEPA) was signed. Null [Not Begun], Complete - Date | Date that the Soil Assessment fieldwork is scheduled. | Tracks if the Site Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Date that installation is reported completed | Status of Data Transmission with MADIS
Options (may not be all inclusive for some categories) | E.g. Wapiti 6E | E.g. SHMW4 | Y (Yes) | Private | New | [6 empty] | Montana | MT Climate Office | 1: > 80% | Candidate | Intitial Purchase Order | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | USACE Contractor | MM/DD/YYYY- Anticipated data of field workd | 1-acre | Null | Null [No date scheduled] | Null [Not Submitted] | null [not submitted], | null [not submitted], | MM/DD/YYYY | Site not operational
| Worland |  | N (No) | City | Existing | [6 empty] | Nebraska | NE Mesonet | 2: 50% – 80% | Available | TO1 |  |  |  | USACE Staff | In-Progress SHPO/THPO - field work is done - now is it moving through the USACE and SHPO/THPO process | 3-acre | In-Progress | MM/DD/YYY [Date that fieldwork is scheduled] | N [Task Order Awarded but report not submitted] | N [station online but report not submitted], | N [station online for 1 year but report not submitted], |  | Site not transmitting
|  |  |  | State | Existing - Moved more than 100 Feet | [6 empty] | North Dakota | NDAWN | 3: 20% – 50% | In-Progress | TO2 |  |  |  | NPS | Complete - all work is complete |  | Complete - DD/MM/YYYY | I [Fieldwork Complete, Lab work not complete] | Y [Report Submitted and Received] | Y [report submitted] | Y [report submitted] |  | Site transmitting
|  |  |  | Federal (Many agencies) | [7 empty] | South Dakota | SD Mesonet | 4: < 20% | Complete | TO3 |  |  |  | Tribe |  |  | Flag | C [Fieldwork and Lab work Complete]
|  |  |  | Tribal Lands | [7 empty] | Wyoming | Wyoming Mesonet |  |  | TO4
TO5