## All Site Info
Site | Grid Cell ID | NWS LI ID | Part of NMP? | Land Ownership | Site Type (New Site (New), Existing Site (Existing), Existing but moved more than 100 feet from Orig Location (Exisiting- Moved) | Orig. Lat | Orig. Long | Proposed Lat | Proposed Long | Elevation | County | State | Owner | Retrofit Category | Station Status | Station Status Note | Mesonet Univ. Task Order & Fiscal Year | Date Award | Contract Deadline | Cultural or NEPA Task Order | Sec 106 Responsible party(USACE Contractor, USACE Staff, Local Landowner or Agency) | Section 106 (Date Fieldwork Scheduled, SHPO/THPO In-Progress or Complete) | NEPA (Date REC Signed) | NRCS Soil Char. Date Scheduled or Complete | Site Report | Station Report | Annual Report | Equipment Installation Complete | Data Available on Mesonet Website | Data Transmitting via USACE Oracle | Notes
Ashland E | O-12 |  | no | US Forest Service | new |  |  | 45.5733 | -106.1432 | 3185 | Powder River | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Busby S | M-12 |  | no | private | new |  |  | 45.5186 | -106.9316 | 3582 | Big Horn | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Canyon Ferry N | C-8 |  | no | US Forest Service | new |  |  | 46.6478 | -111.6372 | 4262 | Broadwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Forestgrove N | I-7 |  | no | private | new |  |  | 47.1058 | -109.0888 | 4103 | Fergus | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Harlowton E | G-9 |  | no | private | new |  |  | 46.413 | -109.7009 | 4086 | Wheatland | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Lodge Grass W | L-13 |  | no | private | new |  |  | 45.3073 | -107.5154 | 3824 | Big Horn | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Matador Ranch | K-5 |  | no | Nature Conservancy | new |  |  | 47.9264 | -108.3359 | 3027 | Phillips | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Molt S | I-11 |  | no | private | new |  |  | 45.8414 | -108.9592 | 3899 | Stillwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Mosby NW | K-7 |  | no | private | new |  |  | 47.0611 | -108.098 | 2989 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Musselshell | K-9 |  | no | private | new |  |  | 46.54 | -108.0218 | 3132 | Musselshell | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Otter E | O-13 |  | no | US Forest Service | new |  |  | 45.2469 | -105.9845 | 3936 | Powder River | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Rapleje SW | H-11 |  | no | private | new |  |  | 45.8858 | -109.4211 | 4710 | Stillwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Roy E | J-6 |  | no | private | new |  |  | 47.3791 | -108.6778 | 3038 | Fergus | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Ryegate S | H-10 |  | no | private | new |  |  | 46.1995 | -109.3111 | 4272 | Golden Valley | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Sand Springs NW | L-7 |  | no | private | new |  |  | 47.1653 | -107.6384 | 3007 | Garfield | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Scobey NW | Q-2 |  | no | private | new |  |  | 48.8602 | -105.4972 | 2467 | Daniels | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Twodot E | F-9 |  | no | private | new |  |  | 46.4468 | -110.2055 | 4643 | Wheatland | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Valentine E | K-6 |  | no | private | new |  |  | 47.358 | -108.2438 | 2904 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
War Horse NW | J-7 |  | no | private | new |  |  | 47.1472 | -108.5913 | 3151 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Winnett SW | J-8 |  | no | private | new |  |  | 46.9654 | -108.5024 | 3202 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021
Bozeman | D-11 | BMMM8 | y |  | Existing | 45.6621 | -111.0463 | 45.6621 | -111.0463 | 4927 |  | Montana | MT Climate Office | 1 | Complete | Pilot Station; Data transmission to Oracle Pending | Initial Purchase Order | 2020-04-09 | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2020 | Y
Capitol BLM |  |  | y | Bureau of Land Management |  | 45.325 | -104.1361 | 45.325 | -104.1361 | 3307.0766 | Capitol | Montana | MT Climate Office | 1 | Exisiting
Battle Creek BLM |  |  | y | Bureau of Land Management |  | 45.0684 | -103.7776 | 45.0684 | -103.7776 |  | Butte | South Dakota | MT Climate Office |  | Existing
Belfry E BLM |  |  | y | Bureau of Land Management |  | 45.1795 | -108.9027 | 45.1795 | -108.9027 | 3942 | Carbon | Montana | MT Climate Office | 1 | Existing
Benchland E MDA |  |  | y |  |  | 47.0949 | -109.9676 | 47.0949 | -109.9676 | 4245.7221 | Judith Basin | Montana | MT Climate Office | 1 | Existing
Broadus BLM |  |  | y | Bureau of Land Management |  | 45.4358 | -105.3584 | 45.4358 | -105.3584 | 3167.9694 | Powder River | Montana | MT Climate Office | 1 | Existing
Cherry Ridge BLM |  |  | y | Bureau of Land Management |  | 48.8722 | -109.0452 | 48.8722 | -109.0452 | 3030.8308 | Blaine | Montana | MT Climate Office | 1 | Existing
Chinook E MDA |  |  | y |  |  | 48.5754 | -109.1552 | 48.5754 | -109.1552 | 2390.4127 | Blaine | Montana | MT Climate Office | 1 | Existing
Choteau NE MDA |  |  | y |  |  | 47.893 | -112.0899 | 47.893 | -112.0899 | 3771.6422 | Teton | Montana | MT Climate Office | 1 | Existing
Churchill S |  |  | y |  |  | 45.7252 | -111.3664 | 45.7252 | -111.3664 | 4808.3844 | Gallatin | Montana | MT Climate Office | 1 | Existing
Dagmar NW MDA |  |  | y |  |  | 48.6621 | -104.2536 | 48.6621 | -104.2536 | 2119 | Sheridan | Montana | MT Climate Office | 1 | Existing
Dillon NE MDA |  |  | y |  |  | 45.2452 | -112.5884 | 45.2452 | -112.5884 | 5056.021 | Beaverhead | Montana | MT Climate Office | 1 | Existing
Edgar E MDA |  |  | y |  |  | 45.4637 | -108.8568 | 45.4637 | -108.8568 | 3509.5039 | Carbon | Montana | MT Climate Office | 1 | Existing
Fort Benton E |  |  | y |  |  | 47.7901 | -110.4816 | 47.7901 | -110.4816 | 3259.5046 | Choteau | Montana | MT Climate Office | 1 | Existing
Fort Keogh ARS SE |  |  | y |  |  | 46.3452 | -105.8336 | 46.3452 | -105.8336 | 2466.8561 | Custer | Montana | MT Climate Office | 1 | Existing
Fort Keogh ARS SW |  |  | y |  |  | 46.3043 | -105.9765 | 46.3043 | -105.9765 | 2799.8603 | Custer | Montana | MT Climate Office | 1 | Existing
Gildford N MDA |  |  | y |  |  | 48.7003 | -110.276 | 48.7003 | -110.276 | 2793.9548 | Hill | Montana | MT Climate Office | 1 | Existing
Glasgow W MDA |  |  | y |  |  | 48.2261 | -106.7163 | 48.2261 | -106.7163 | 2112.964 | Valley | Montana | MT Climate Office | 1 | Existing
Glendive BLM |  |  | y | Bureau of Land Management |  | 46.915 | -104.747 | 46.915 | -104.747 | 2352.3551 | Dawson | Montana | MT Climate Office | 1 | Existing
Hardin N MDA |  |  | y |  |  | 45.8685 | -107.6019 | 45.8685 | -107.6019 | 2844.627 | Big Horn | Montana | MT Climate Office | 1 | Existing
Harding Cutoff BLM |  |  | y | Bureau of Land Management |  | 45.1736 | -103.7281 | 45.1736 | -103.7281 |  | Butte | South Dakota | MT Climate Office |  | Existing
Hogeland SE MDA |  |  | y |  |  | 48.7712 | -108.5644 | 48.7712 | -108.5644 | 3108.9145 | Blaine | Montana | MT Climate Office | 1 | Existing
Ledger N MDA |  |  | y |  |  | 48.3378 | -111.8235 | 48.3378 | -111.8235 | 3428.645 | Pondera | Montana | MT Climate Office | 1 | Existing
Loma S |  |  | y |  |  | 47.8934 | -110.526 | 47.8934 | -110.526 | 2810.359 | Choteau | Montana | MT Climate Office | 1 | Existing
Malta MDA |  |  | y |  |  | 48.3507 | -108.0035 | 48.3507 | -108.0035 | 2270.0063 | Phillips | Montana | MT Climate Office | 1 | Existing
Manhattan S MDA |  |  | y |  |  | 45.7871 | -111.322 | 45.7871 | -111.322 | 4367.011 | Gallatin | Montana | MT Climate Office | 1 | Existing
Miles City S MDA |  |  | y |  |  | 46.2207 | -105.761 | 46.2207 | -105.761 | 2477.155 | Custer | Montana | MT Climate Office | 1 | Existing
Molt W |  |  | y |  |  | 45.8231 | -109.0905 | 45.8231 | -109.0905 | 4180.4336 | Stillwater | Montana | MT Climate Office | 1 | Existing
Plevna BLM |  |  | y | Bureau of Land Management |  | 46.4389 | -104.4253 | 46.4389 | -104.4253 | 3036.0801 | Fallon | Montana | MT Climate Office | 1 | Existing
Power S MDA |  |  | y |  |  | 47.6551 | -111.7118 | 47.6551 | -111.7118 | 3731.9441 | Teton | Montana | MT Climate Office | 1 | Existing
Pumpkin Ck BLM |  |  | y | Bureau of Land Management |  | 46.1968 | -105.6964 | 46.1968 | -105.6964 | 2731.291 | Custer | Montana | MT Climate Office | 1 | Existing
Rapleje N |  |  | y |  |  | 46.0446 | -109.2424 | 46.0446 | -109.2424 | 4188.9637 | Stillwater | Montana | MT Climate Office | 1 | Existing
Reed Point NE |  |  | y |  |  | 45.7976 | -109.4319 | 45.7976 | -109.4319 | 4249.331 | Stillwater | Montana | MT Climate Office | 1 | Existing
Reed Point S |  |  | y |  |  | 45.6125 | -109.556 | 45.6125 | -109.556 | 4704.7102 | Stillwater | Montana | MT Climate Office | 1 | Existing
Roundup NW BLM | J-9 |  | y | Bureau of Land Management |  | 46.5758 | -108.738 | 46.5758 | -108.738 | 3654.5165 | Musselshell | Montana | MT Climate Office | 1 | Existing | [15 empty] | Accessed through private property - Coordinate with local BLM Office
Roy BLM |  |  | y | Bureau of Land Management |  | 47.4943 | -108.9481 | 47.4943 | -108.9481 | 3086.9329 | Fergus | Montana | MT Climate Office | 1 | Existing
Scobey N MDA |  |  | y |  |  | 48.8819 | -105.4371 | 48.8819 | -105.4371 | 2408.254 | Daniels | Montana | MT Climate Office | 1 | Existing
Terry BLM |  |  | y | Bureau of Land Management |  | 46.8366 | -105.2602 | 46.8366 | -105.2602 | 2344.4811 | Prairie | Montana | MT Climate Office | 1 | Existing
Triple Crossing BLM |  |  | y | Bureau of Land Management |  | 47.9877 | -107.1063 | 47.9877 | -107.1063 | 3273.6122 | Valley | Montana | MT Climate Office | 1 | Existing | [15 empty] | No Cell Service available at this site
Twin Bridges S MDA |  |  | y |  |  | 45.4665 | -112.36 | 45.4665 | -112.36 | 4773.2796 | Madison | Montana | MT Climate Office | 1 | Existing
Vandalia N BLM |  |  | y | Bureau of Land Management |  | 48.5119 | -106.9058 | 48.5119 | -106.9058 | 2616.79 | Valley | Montana | MT Climate Office | 1 | Existing
Warren E BLM |  |  | y | Bureau of Land Management |  | 45.0422 | -108.4422 | 45.0422 | -108.4422 | 5220 | Carbon | Montana | MT Climate Office | 1 | Existing
Zortman |  |  | y | Bureau of Land Management |  | 47.8947 | -108.3233 | 47.892 | -108.331 | 3096 | Phillips | Montana | MT Climate Office | 1 | Existing
MDA Froid |  |  | y |  |  | 48.3459 | -104.48 | 48.3458 | -104.4776 | 2059 | Roosevelt | Montana | MT Climate Office | 1 | Existing | Removed from consideration bc in same cell as ND Froid retrofit | No longer being considered for a TO |  |  |  | USACE Contractor | Removed from list | Complete - 8/30/2021 | [7 empty] | Removed because in same site as NDAWN Froid
Benton Lake W | D-5 |  | y |  | Existing | 47.6907 | -111.4736 | 47.6907 | -111.4736 | 3706.0256 | Cascade | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Big Timber SE | G-11 |  | y |  | Existing | 45.7435 | -109.8267 | 45.7435 | -109.8267 | 4423.5431 | Sweet Grass | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Coffee Creek N | G-6 |  | y |  | Existing | 47.3883 | -110.1282 | 47.3935 | -110.1083 | 3738.8339 | Fergus | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Conrad ARC | C-3 |  | y |  | Existing | 48.3082 | -111.9259 | 48.3071 | -111.924 | 3728.3352 | Pondera | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Cooney Reservoir NW | H-12 |  | y |  | Existing | 45.4658 | -109.2597 | 45.4658 | -109.2597 | 4702.0856 | Stillwater | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021 | [7 empty] | Will move slightly closer to road access
Huntley ARC | J-11 |  | y |  | Existing | 45.9192 | -108.2344 | 45.9264 | -108.233 | 3054.7808 | Yellowstone | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
MDA Oilmont | D-1 |  | y | Private | Existing | 48.7816 | -111.6011 | 48.7816 | -111.6011 | 3596.7739 | Toole | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
MDA Toston | C-10 |  | y |  | Existing | 46.1178 | -111.5298 | 46.1365 | -111.5432 | 4066.5888 | Broadwater | Montana | MT Climate Office | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Absarokee W | G-12 |  | y |  | Existing | 45.5573 | -109.6112 | 45.5573 | -109.6112 | 4608 | Stillwater | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY 20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Broadview E | I-10 |  | y |  | Existing | 46.1282 | -108.7554 | 46.1282 | -108.7554 | 4094.8039 | Yellowstone | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Crow Agency E | L-12 |  | y | Crow indian reservation | Existing | 45.5861 | -107.4383 | 45.5861 | -107.4383 | 3119 | Big Horn | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | TO1 in MT, ND, SD, and WY |  | 2021-09-30 | TO2 | USACE Contractor | Complete | Complete | Complete
Havre ARC | H-3 |  | y |  | Existing | 48.4922 | -109.796 | 48.4891 | -109.7994 | 2721.4485 | Hill | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Ingomar NE | M-9 |  | y |  | Existing | 46.6568 | -107.2238 | 46.6568 | -107.2238 | 3097.7597 | Rosebud | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Melville SE | G-10 |  | y |  | Existing | 46.0015 | -109.8416 | 46.0015 | -109.8416 | 4709.9595 | Sweet Grass | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | TO1 in MT, ND, SD, and WY |  | 2021-09-30 | TO2 | USACE Contractor | Complete | Complete | Complete
Miles City | O-9 |  | y |  | Existing | 46.4054 | -105.9543 | 46.4054 | -105.9543 | 2717.8396 | Custer | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | TO1 in MT, ND, SD, and WY |  | 2021-09-30 | TO2 | USACE Contractor | Complete | Complete | Complete
Mocassin ARC | G-7 |  | y |  | Existing | 47.0585 | -109.9535 | 47.0585 | -109.9535 | 4256.5488 | Judith Basin | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Roundup NE | J-9 |  | y |  | Existing | 46.5785 | -108.4243 | 46.5785 | -108.4243 | 3448.1523 | Musselshell | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete |  |  |  | Installed 2021 | Y
Sidney ARC | S-5 |  | y |  | Existing | 47.7823 | -104.2479 | 47.7823 | -104.2479 | 2259.8357 | Richland | Montana | MT Climate Office | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | TO1 in MT, ND, SD, and WY |  | 2021-09-30 | TO2 | USACE Contractor | Complete | Complete | Complete
Alpha 9SE | T-9 |  | No | Private | New |  |  | 46.5641 | -103.6971 | 2906 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Marmarth 2N | T-10 |  | No | Private | New |  |  | 46.3228 | -103.9374 | 2840 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
McKenzie 2E | AA-8 |  | No | Private | New |  |  | 46.8222 | -100.3617 | 1773 | Burleigh | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Napoleon 1S | AC-9 |  | No | Private | New |  |  | 46.4863 | -99.7587 | 2007 | Logan | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
New England 5W | V-9 |  | No | Private | New |  |  | 46.5264 | -102.968 | 2718 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Pick City 8SW | Y-6 |  | No | Private | New |  |  | 47.4747 | -101.6123 | 2045 | Mercer | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Poker Jim | T-6 |  | No | Private | Existing |  |  | 47.5025 | -103.6559 | 2092 | McKenzie | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Sentinel Butte 10N | T-7 |  | No | Private | Existing |  |  | 47.0669 | -103.7933 | 2736 | Golden Valley | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Shell Lake | X-4 |  | No | Private | Existing |  |  | 48.1501 | -102.0727 | 2058 | Mountrail | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Wing | AA-7 |  | No | Private | New |  |  | 47.2719 | -100.3303 | 1973 | Burleigh | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Ypsilanti | AE-8 |  | No | Private | New |  |  | 46.7764 | -98.5236 | 1483 | Stutsman | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021
Arnegard |  |  | N | Private |  | 47.9395 | -103.4556 | 47.9395 | -103.4556 | 2254 | McKenzie | North Dakota | NDAWN | 2 | Existing
Brorson |  |  | Y | Montana State |  | 47.7823 | -104.2481 | 47.7823 | -104.2481 | 2257 | Richland | Montana | NDAWN | 1 | Existing
Charbonneau |  |  | N | Private |  | 47.9209 | -103.7905 | 47.9209 | -103.7905 | 2281 | McKenzie | North Dakota | NDAWN | 2 | Existing
Crane Creek |  |  | N | Private |  | 48.0648 | -102.3542 | 48.0648 | -102.3542 | 2203 | Mountrail | North Dakota | NDAWN | 2 | Existing
Croff |  |  | N | Private |  | 47.7495 | -102.8772 | 47.7495 | -102.8772 | 2240 | McKenzie | North Dakota | NDAWN | 2 | Existing
Dagmar |  |  | Y | Private |  | 48.5559 | -104.3465 | 48.5559 | -104.3465 |  | Sheridan | Montana | NDAWN | 1 | Existing
Dunn |  |  | Y | Private |  | 47.3416 | -102.6308 | 47.3416 | -102.631 | 2214 | Dunn | North Dakota | NDAWN | 1 | Existing | [15 empty] | Will not be retrofit
Epping |  |  | N | Private |  | 48.2561 | -103.318 | 48.2561 | -103.318 | 2218 | Williams | North Dakota | NDAWN | 2 | Existing
Fort Yates |  |  | Y | Standing Rock Reservation |  | 46.0849 | -100.6765 | 46.0849 | -100.6765 | 1662 | Sioux | North Dakota | NDAWN | 1 | Existing
Hawkeye |  |  | N | Private |  | 48.0241 | -102.9406 | 48.0241 | -102.9406 | 2323 | McKenzie | North Dakota | NDAWN | 2 | Existing
Hofflund |  |  | Y | Private |  | 48.1647 | -103.1086 | 48.1647 | -103.1086 | 1904 | Williams | North Dakota | NDAWN | 1 | Existing
Liberty |  |  | N | Private/Reservation |  | 47.9057 | -102.2196 | 47.9057 | -102.2196 | 2097 | Mountrail | North Dakota | NDAWN | 2 | Existing
Linton |  |  | Y | Private |  | 46.3275 | -100.2772 | 46.3268 | -100.281 | 2005 | Emmons | North Dakota | NDAWN | 1 | Existing
Medicine Hole |  |  | N | Private |  | 47.5599 | -102.9921 | 47.5599 | -102.9921 | 2555 | Dunn | North Dakota | NDAWN | 2 | Existing
Plaza |  |  | Y | Private/Reservation |  | 47.8623 | -101.9576 | 47.8623 | -101.9576 | 2117 | Mountrail | North Dakota | NDAWN | 1 | Existing
Rat Lake |  |  | N | Private |  | 48.1968 | -102.6986 | 48.1968 | -102.6986 | 2304 | Mountrail | North Dakota | NDAWN | 2 | Existing
Ross |  |  | Y | Private |  | 48.269 | -102.4811 | 48.269 | -102.4811 | 2382 | Mountrail | North Dakota | NDAWN | 1 | Existing
Sidney |  |  | Y | Montana State |  | 47.7298 | -104.1524 | 47.7298 | -104.1524 | 1928 | Richland | Montana | NDAWN | 1 | Existing
Watford City |  |  | Y | Private |  | 47.8104 | -103.2322 | 47.8104 | -103.2322 | 2141 | McKenzie | North Dakota | NDAWN | 1 | Existing
Werner |  |  | N | Private |  | 47.4445 | -102.5001 | 47.4445 | -102.5001 | 2276 | Dunn | North Dakota | NDAWN | 2 | Existing
Alamo |  |  | Y | Private | Existing | 48.5465 | -103.4718 | 48.5681 | -103.4718 | 2157 | Williams | North Dakota | NDAWN | 3 | Existing | [5 empty] | USACE Contractor | Removed from list | Complete - 8/30/2021 | [7 empty] | Dropped because in same cell as another station
Beach | T-8 |  | y | Private | Existing | 46.7894 | -103.9662 | 46.7894 | -103.9662 | 2932 | Golden Valley | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete
Dickinson | V-8 |  | y | NDSU | Existing | 46.8948 | -102.8131 | 46.8948 | -102.8131 | 2557 | Stark | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete
Dooley | S-2 |  | Y | Private | Existing | 48.8337 | -104.3846 | 48.8337 | -104.3846 |  | Sheridan | Montana | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Edgeley | AE-9 |  | y | Private | Existing | 46.3192 | -98.7661 | 46.3192 | -98.7661 | 1649 | LaMoure | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Froid | S-4 |  | Y | USDA | Existing | 48.2579 | -104.4967 | 48.2579 | -104.4967 |  | Roosevelt | Montana | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Garrison | X-5 |  | Y | Private | Existing | 47.7102 | -101.6795 | 47.7102 | -101.6795 | 2200 | McLean | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/2021
Grassy Butte 2E | U-6 |  | N | Private | Existing | 47.3865 | -103.2062 | 47.3865 | -103.2062 | 2688 | McKenzie | North Dakota | NDAWN |  | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202 | [7 empty] | Replacing Dunn site. All Dunn equipment being moved to this location
Jamestown | AD-8 |  | y | Private | Existing | 46.9064 | -98.9274 | 46.9064 | -98.9274 | 1639 | Stutsman | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Keene 5SW | V-5 |  | N | Private | Existing | 47.8938 | -103.0482 | 47.8938 | -103.0482 | 2346 | McKenzie | North Dakota | NDAWN |  | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Mandan | Z-8 |  | y | USDA | Existing | 46.7736 | -100.9139 | 46.7736 | -100.9139 | 1907 | Morton | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21
Marion | AF-9 |  | Y | Private | Existing | 46.5645 | -98.3276 | 46.5645 | -98.3276 | 1453 | LaMoure | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Redstone | R-2 |  | Y | Private | Existing | 48.8211 | -104.842 | 48.8246 | -104.8417 |  | Sheridan | Montana | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Steele | AB-8 |  | N | Private | Existing | 46.894 | -99.9927 | 46.894 | -99.9927 | 1862 | Kidder | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Turtle Lake | Z-6 |  | Y | Private | Existing | 47.5679 | -100.9153 | 47.5679 | -100.9153 | 1927 | McLean | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Wishek | AC-10 |  | Y | Private | Existing | 46.2599 | -99.6658 | 46.2599 | -99.6658 | 2219 | McIntosh | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21
Zeeland | AC-11 |  | N | Private | Existing | 46.0135 | -99.6877 | 46.0133 | -99.6877 | 2070 | McIntosh | North Dakota | NDAWN | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Amidon | U-9 |  | N | Private | Existing | 46.4884 | -103.3162 | 46.4885 | -103.316 | 2883 | Slope | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 9/29/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Bowman | U-10 |  | Y | Private | Existing | 46.1997 | -103.4731 | 46.1997 | -103.473 | 3032 | Bowman | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 8/28/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Carrington |  |  | Y | NDSU | Existing | 47.5086 | -99.1323 | 47.5086 | -99.1323 | 1561 | Foster | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | Not on Task Order by USACE | na | na | na | na | na | na | na | na | na | na | Installed except snow depth sensors | Y except snow depth data |  | Not funded by Network but network will accept data
Carson | Y-9 |  | Y | Private | Existing | 46.443 | -101.3738 | 46.443 | -101.3738 | 2107 | Grant | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 8/12/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Courtenay | AE-7 |  | N | Private | Existing | 47.2212 | -98.6799 | 47.2212 | -98.6799 | 1522 | Stutsman | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Field Season 2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Fortuna | T-2 |  | N | Private | Existing | 48.9637 | -103.8058 | 48.9637 | -103.8058 | 2246 | Divide | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Field Season 2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Grenora | T-3 |  | N | Private | Existing | 48.735 | -103.8812 | 48.735 | -103.8812 | 2108 | Divide | North Dakota | NDAWN | 3 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Field Season 2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Hazen | X-7 |  | y | Private | Existing | 47.3018 | -101.6792 | 47.3018 | -101.6792 | 1849 | Mercer | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO2 in ND and SD | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete - 2/8/2021 | Complete - 8/23/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data |  | next to current site, or within 200 ft
Hettinger | W-11 |  | Y | NDSU | Existing | 46.0126 | -102.6453 | 46.0126 | -102.6453 | 2758 | Adams | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 9/15/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Mott | W-10 |  | Y | Private | Existing | 46.3798 | -102.3219 | 46.3798 | -102.322 | 2473 | Hettinger | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 8/30/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Oakes | AF-10 |  | y | NDSU | Existing | 46.0667 | -98.1031 | 46.0667 | -98.1028 | 1323 | Dickey | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO2 in ND and SD | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete - 2/8/21 | Complete - 9/2/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data |  | Multiple changes to location
Ray | U-3 |  | Y | Private | Existing | 48.4009 | -103.1693 | 48.4009 | -103.169 | 2316 | Williams | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Field Season 2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Robinson | AB-7 |  | y | Private | Existing | 47.173 | -99.7982 | 47.173 | -99.7982 | 1829 | Kidder | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO2 in ND and SD | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete-2/8/21 | Complete - 8/18/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Streeter | AC-8 |  | Y | NDSU | Existing | 46.7185 | -99.4607 | 46.718 | -99.4608 | 1992 | Kidder | North Dakota | NDAWN | 2 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 8/19/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data |  | Waiting on Confirmation from NDAWN
Williston | T-4 |  | Y | NDSU | Existing | 48.1331 | -103.7385 | 48.1331 | -103.739 | 2132 | Williams | North Dakota | NDAWN | 1 | In-Progress | Equipment Installed except for snow sensor, Data Transmission pending | FY20 TO1 in ND and SD |  | 2021-09-30 |  |  | Complete | Complete | Complete - 9/22/2021 |  |  |  | Installed except snow depth sensors | Y except snow depth data
Long Pine 20S | AD-21 |  | Y | State Educational Lands and Funds - Leased Public | New |  |  | 42.2297 | -99.6581 |  | Brown | Nebraska | NE Mesonet | New | In-Progress | Awarded in Sept 2021 | FY21 TO1 NE | 2021-09-23 | 2022-09-30 |  | USACE Staff | Complete | Complete - 8/11/2021 | Summer 2022 | [6 empty] | New site
BERESFORD | AJ-19 | BFMS2 | y | University research farm; stop by the office 1,000' NNW of the site (605-563-2989, 29974 University Road) for escort | Existing but moved more than 100 feet | 43.0526 | -96.9041 | 43.0404 | -96.9011 | 1278 | Clay | South Dakota | SD Mesonet | 1 | Available |  | Sub for Martin on T01 (Planned) |  |  |  |  | Complete | Complete - 2/25/21 | Complete - 4/13/2021 | [6 empty] | 1
Timber Lake |  | TIMS2 | y | Non - federal airport property; City has not approved (as of 9/3/21) | Existing | 45.4167 | -101.0841 | 45.4166 | -101.085 | 2196 | Dewey | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (City Permissions - waiting on city council meeting first week of Oct.) | FY20 TO1 Planned replacement for Faulkton |  |  |  |  | Complete | Complete 2/25/2021 | Complete - 6/27/2019
BISON | W-12 | BSNS2 | y | On airport property; Special FAA Consultation | Existing | 45.5183 | -102.4694 | 45.5166 | -102.4673 | 2779 | Perkins | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 5/20/2021 | [6 empty] | 21
Eagle Butte | Z-14 | EGBS2 | y | On airport property; Special FAA Consultation | Existing | 44.9875 | -101.253 | 44.9875 | -101.253 | 2439 | Ziebach | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE Contractor | Complete 3/5/21 | Complete 2/25/21 | Complete - 6/27/2019
Gettysburg | AB-14 | GTBS2 | y | On airport property; Special FAA Consultation | Existing | 44.9865 | -99.9541 | 44.9888 | -99.9505 | 2059 | Potter | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Sampled in 2019 but moved | [6 empty] | 14
LEMMON |  | LMNS2 | y | On airport property; Special FAA Consultation | Existing | 45.9189 | -102.1082 | 45.9189 | -102.1082 | 2575 | Perkins | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 6/3/2019 | [6 empty] | 22
PARKSTON |  | PSTS2 | y | On airport property; Special FAA Consultation | Existing | 43.3841 | -97.9928 | 43.3819 | -97.9898 | 1414 | Hutchinson | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE | Complete 9/7/2021 | Pending - FAA Consultation | Sampled in 2019 but moved | [6 empty] | 16
REDFIELD |  | RDFS2 | y | On airport property; Special FAA Consultation | Existing | 44.8579 | -98.5289 | 44.8579 | -98.5289 | 1300 | Spink | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 6/11/2019 | [6 empty] | 17
WEBSTER |  | WEBS2 | y | On airport property; Special FAA Consultation | Existing | 45.2932 | -97.5154 | 45.2908 | -97.5188 | 1848 | Day | South Dakota | SD Mesonet | 1 | Candidate | Pending Availability (FAA Consultation) | FY21 TO3 (Planned) |  |  |  | USACE | Complete 9/7/2021 | Pending - FAA Consultation | Summer 2021- on hold | [6 empty] | 18
DAKOTA LAKES | AB-16 | PRFS2 | y | City has not approved as of 9/3/2021 | Existing | 44.2912 | -100.0063 | 44.2914 | -100.0084 | 1498 | Hughes | South Dakota | SD Mesonet | 1 | Candidate | Pending Available (Once land is sold to Univ in next couple years) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Sampled in 2019 but moved | [6 empty] | 8
Brookings | AJ-15 | BKMS2 | y |  |  | 44.325 | -96.7685 | 44.325 | -96.7685 | 1640 | Brookings | South Dakota | SD Mesonet | 1 | Complete | Pilot Station | FY19 Initial Purchase Order | 2020-04-08 |  |  |  | Complete | Complete | Complete - 6/13/2019 |  |  |  | 2020-08-06
Oak Lake |  | OAKS2 | y | University research facility; call director's cell and stop by the main admin building northwest of the site (301-412-9765) for escort; digging may need a US Fish and Wildlife Service permit due to butterfly habitat |  | 44.5073 | -96.5302 | 44.5074 | -96.53 | 1889 |  | South Dakota | SD Mesonet | 1 | Exisiting | Removed from further consideration | [5 empty] | Complete | Complete - 2/25/21 | Complete - 7/8/2019 | [6 empty] | No longer being considered due to location
MCINTOSH |  | MCTS2 | y | Standing Rock Tribal Land |  | 45.9154 | -101.3448 | 45.9154 | -101.3448 | 2263 | Corson | South Dakota | SD Mesonet | 1 | Existing | Pending conversations with Standing Rock | [7 empty] | Complete - 6/4/2019 | [6 empty] | 11
MCLAUGHLIN |  | MHTS2 | y | On airport property; Special FAA Consultation; Standing Rock Tribal Land |  | 45.7963 | -100.7805 | 45.7963 | -100.7805 | 2005 | Corson | South Dakota | SD Mesonet | 1 | Existing | Pending conversations with Standing Rock - Also FAA Site | [7 empty] | Complete - 6/4/2019 | [6 empty] | 15
Faulkton |  | FLKS2 | y | On airport property; Special FAA Consultation |  | 45.0292 | -99.1134 | 45.0295 | -99.1137 | 1569 | Faulk | South Dakota | SD Mesonet | 1 | Existing | Removed from further consideration | [7 empty] | Sampled in 2019 but moved
VOLGA |  | VGAS2 | y |  |  | 44.3042 | -96.9184 | 44.304 | -96.9189 | 1642 | Brookings | South Dakota | SD Mesonet | 1 | Existing | Removed from further consideration |  |  |  |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/202 | Complete - 7/1/2019 | [6 empty] | Removed from candidate list because too close to Brookings
Aurora |  | AURS2 | y |  |  | 44.3099 | -96.6735 | 44.3098 | -96.6712 | 1655 |  | South Dakota | SD Mesonet |  | Existing | [15 empty] | 24
BALTIC |  | BTCS2 | y |  |  | 43.7316 | -96.6814 | 43.732 | -96.6907 | 1550 | Minnehaha | South Dakota | SD Mesonet | 1 | Existing | [8 empty] | Sampled in 2019 but moved | [6 empty] | 23
BRITTON |  | BTNS2 | y |  |  | 45.6796 | -97.7504 | 45.6788 | -97.7491 | 1402 | Marshall | South Dakota | SD Mesonet | 1 | Existing | [15 empty] | 25
COLTON |  | CTNS2 | y |  |  | 43.7687 | -96.8897 | 43.768 | -96.8869 | 1588 | Minnehaha | South Dakota | SD Mesonet | 1 | Existing | [8 empty] | Sampled in 2019 but moved | [6 empty] | 12
Martin |  | MATS2 | y | On airport property; Special FAA Consultation | Existing | 43.1672 | -101.7162 | 43.1669 | -101.7163 | 3299 | Bennett | South Dakota | SD Mesonet | 1 | Existing |  | Taken off TO1 ND |  |  |  |  | Complete 2/18/21 | Complete | Complete - 6/25/2019
Mound City |  | MCMS2 | [5 empty] | 45.6716 | -100.115 | 1745 |  | South Dakota | SD Mesonet |  | Existing
ORAL |  | ORRS2 | y |  |  | 43.3784 | -103.281 | 43.3769 | -103.2793 | 3167 | Fall River | South Dakota | SD Mesonet | 1 | Existing | [15 empty] | 19
SF LANDFILL |  | SFWS2 | y |  |  | 43.5033 | -96.9218 | 43.5086 | -96.9296 | 1574 | Minnehaha | South Dakota | SD Mesonet | 1 | Existing | [15 empty] | 26
ANTELOPE | U-12 | ATRS2 | y |  | Existing | 45.5193 | -103.2888 | 45.5193 | -103.2888 | 2903 | Harding | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/202 | Complete - 6/26/2019 | [6 empty] | 6
Flandreau | AJ-16 | FLNS2 | y |  | Existing | 44.0867 | -96.5849 | 44.0867 | -96.5849 | 1624 | Moody | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021 | Complete - 5/30/2019 | [6 empty] | 20
HAMILL | AC-18 | HMLS2 | y |  | Existing | 43.5938 | -99.7122 | 43.5938 | -99.7122 | 1863 | Tripp | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Complete - 5/16/2019 | [6 empty] | 13
Jewel Cave | T-18 | JWLS2 | y | National Park Service land, survey to be done by NPS | Existing | 43.7343 | -103.8278 | 43.7343 | -103.8278 | 5672 | Custer | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | NPS | Complete 6/5/2021 | Complete - 8/30/2021 | [7 empty] | 2
NISLAND | U-15 | NISS2 | y | Bureau of Reclamation land | Existing | 44.6783 | -103.5606 | 44.6783 | -103.5606 | 2906 | Butte | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/25/2021 | Complete - 8/2/2019 | [6 empty] | 5
ROSEBUD | AA-19 | RBMS2 | y | Cultural Survey to be done by Rosebud Sioux Tribe | Existing | 43.2002 | -100.7208 | 43.2002 | -100.7208 | 2808 | Todd | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | Rosebud Tribe | Complete | Complete - 8/5/2021 | Complete - 6/20/2019 | [6 empty] | 10
SIOUX FALLS | AJ-18 | SFSS2 | y |  | Existing | 43.5048 | -96.7623 | 43.5048 | -96.7623 | 1407 | Minnehaha | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Complete -6/17/2019 | [6 empty] | 9
WHITE LAKE | AE-17 | WTES2 | y | no escort needed | Existing | 43.7321 | -98.6938 | 43.7372 | -98.6936 | 1637 | Aurora | South Dakota | SD Mesonet | 1 | In-Progress | Awarded in Sept 2021 | FY21 TO3 | 2021-09-29 | 2022-09-30 |  |  | Complete 3/5/21 | Complete 3/7/2021 | Complete - 6/21/2019 | [6 empty] | 4
White River | AA-18 | WRIS2 | y | Non - federal airport property | Existing but moved more than 100 feet | 43.5601 | -100.7435 | 43.5586 | -100.7423 | 2140 | Mellette | South Dakota | SD Mesonet | 1 | In-Progress | Put on hold bc of location change - now cleared for installation | FY20 TO1 in MT, ND, SD, and WY |  |  |  | USACE | Complete 9/7/2021 | Complete - 9/10/2021 | Summer 2021 - on hold | [6 empty] | This site was moved so Sec.106 and Env. was redone
Bowdle | AC-12 | BWLS2 | y | Non - federal airport property | Existing | 45.4406 | -99.6754 | 45.4388 | -99.6733 | 1965 | Edmunds | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 5/2021
Caputa | V-17 | CPTS2 | y |  | Existing | 44.0006 | -103.0007 | 44.0008 | -103.0008 | 2931 | Pennington | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 7/30/2021
Cottonwood | X-17 | CTWS2 | y |  | Existing | 43.9599 | -101.8539 | 43.9599 | -101.8539 | 2365 | Jackson | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO2 in ND and SD | 2021-03-20 | 2021-11-30 |  | USACE Contractor | Complete | Complete - 2/25/21 | Complete - 6/5/2019
Edgemont | T-19 | EDTS2 | y |  | Existing | 43.4737 | -103.9717 | 43.4737 | -103.9717 | 3710 | Fall River | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 7/29/2021
Groton | AG-12 | GOTS2 | y |  | Existing | 45.5735 | -98.0301 | 45.5735 | -98.0301 | 1309 | Brown | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO2 in ND and SD | 2021-03-20 | 2021-11-30 |  |  | Complete | Complete - 2/25/21 | Complete - 6/12/2019
Highmore | AD-15 | HIHS2 | y |  | Existing | 44.5256 | -99.4601 | 44.5256 | -99.4601 | 1879 | Hyde | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 6/19/2019
Leola | AE-11 | LLAS2 | y |  | Existing | 45.7163 | -98.931 | 45.7165 | -98.9311 | 1571 | McPherson | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 5/2019
Oacoma | AD-17 | OCMS2 | y |  | Existing | 43.7982 | -99.4156 | 43.7982 | -99.4156 | 1443 | Lyman | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete | Complete - 7/2/2019
South Shore | AI-13 | SHSS2 | y |  | Existing | 45.1055 | -97.1024 | 45.1055 | -97.1024 | 1850 | Codington | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO2 in ND and SD | 2021-03-20 | 2021-11-30 |  |  | Complete 3/5/21 | Complete -2/25/21 | Complete - 6/12/2019
Sturgis | U-16 | STMS2 | y |  | Existing | 44.4245 | -103.3793 | 44.4245 | -103.3793 | 3237 | Meade | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO2 in ND and SD | 2021-03-20 | 2021-11-30 |  |  | Complete | Complete -2/25/22 | Complete - 6/25/2019
Union Center | W-15 | UNIS2 | y | Non - federal airport property | Existing | 44.5643 | -102.6745 | 44.5665 | -102.671 | 2938 | Meade | South Dakota | SD Mesonet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  | 2021-09-30 |  |  | Complete | Complete -2/25/22 | Complete -7/22/2021
Cowley 4NNE | J-14 | CYMW4 | N | Bureau of Reclamation | New |  |  | 44.9298 | -108.4318 |  | Big Horn | Wyoming | WACNet | 1 | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - This site is just under 2 miles from the North Big Horn County Airport. No objections from the airport.
Pavillion 13W | I-19 | SRMW4 | N | Bureau of Reclamation | New |  |  | 43.2304 | -108.949 |  | Fremont | Wyoming | WACNet | 1 | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - Located near a house operated by Midvale Irrigation District. The site is within a grazing lease so should be protected from livestock accordingly. Otherwise this is a secure location. Midvale ID has no objections.
Shoshoni 6NNW | J-19 | BRMW4 | N | Bureau of Reclamation | New |  |  | 43.3239 | -108.1331 |  | Fremont | Wyoming | WACNet | 1 | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - This site is along a very busy and popular route, in the summertime, to Tough Creek campground within Boysen State Park. Good access and should be a secure location. No objections from State Parks.
Wapati |  | BBMW4 | N | Bureau of Reclamation | New |  |  | 44.4817 | -109.3085 |  | Park | Wyoming | WACNet | 1 | Candidate | Pending Availability (Real Estate Agreement) | Contract Mod for FY20 TO1 to replace Heart Mtn |  |  |  | USACE | Site Moved - needs to be redone | Site Moved - needs to be redone | Summer 2022 | [6 empty] | New site - This site is on the south side of Buffalo Bill Reservoir near boat ramp access. It is more than 150 meters off the water.
Sheridan | M-14 | SHMW4 / SHERIDAN 7ENE | No | University of WY |  | 44.8407 | -106.839 | 44.8407 | -106.839 | 3738 | Sheridan | Wyoming | WACNet | 1 | Complete | Pilot Station | FY19 Initial Purchase Order | 2020-04-10 |  |  |  | Complete | Complete | Summer 2022 | Complete | Complete | Complete - 08162021 | 2020-10-15
Fort_Washakie | I-20 | FWMW4 | N | Wind River Indian Reservation | New | 42.9982 | -108.8751 | 43.005 | -108.8803 | 5571 | Fremont | Wyoming | WACNet | 1 | In-Progress | Was awarded onTO1 (FY20) for WY- had to be moved due to land use change - new location secured - need to redo 106/NEPA | FY20 TO1 in MT, ND, SD, and WY |  |  |  | USACE | Needs to be Redone | Needs to be Redone | [7 empty] | Was listed on Task Order 1 for WY- Unable to be installed because of land use change
Worland | K-17 | WRMW4 | No | BOR | New | 44.0004 | -107.961 | 44.003 | -107.9061 | 4203 | Washakie | Wyoming | WACNet | 1 | In-Progress | Was awarded onTO1 (FY20) for WY- had to be moved due to land use change - new location secured - need to redo 106/NEPA | FY20 TO1 in MT, ND, SD, and WY |  |  |  | USACE | Needs to be Redone | Needs to be Redone | [7 empty] | Was listed on Task Order 1 for WY- Unable to be installed because of land use change
Powell | I-14 | PLMW4 / POWELL 2N | N | University of WY |  | 44.7764 | -108.759 | 44.7764 | -108.759 | 4372 | Park | Wyoming | WACNet | 1 | In-Progress |  | FY20 TO1 in MT, ND, SD, and WY |  |  |  |  | Complete | Complete | Summer 2022

## Categories
Attribute | Site | NWS LI Name | Part of NMP? | Land Ownership | Site Type | Orig Lat | Orig.Lon | Proposed Lat | Proposed Long | Elevation | County | State | Owner | Retrofit Category | Site Status | Task Order | Date Award | Contract Deadline | Operational Date | Sec 106 and NEPA Responsible party | Sec 106 Status | Sec 106 APE (Area of Potential Effect) | Nepa/REC | NRCS Soil Characterization | Site Report | Station Report | Annual Report | Installation Complete | Data Transmission
Description | Identifier given by states - some names end in a number and direction which is the distance in miles and cardinal direction to a major city | 5-digit name given by the National Weather Service for sites. For sites that are not yet in the network- these are proposed names by the Mesonet | Is the site part of the National Mesonet Program? | Type of land ownership where the station is e.g. private lands, state lands, public lands | Describes if site is a new or exisiting site or existing but moved more than 100 feet. | Orginal latitude at existing site | Original Longitude at existing site | Proposed Latitude for new site | Proposed Longitude for new site | Elevation in feet of station location based on Proposed Lat and Proposed Long. | County which station is in. | State that site is located | Name of Climate Center that Owns the Station | The percentage of a site being replaced base on cost. Category 1 - 80%; Category 2 - 50 to 80% percent; Category 3 - 20 to 50%; Category 4 - less than 20%. | The category of retrofit of the station. Future Retrofit - Exisiting site within the Network that may or may not be retrofitted. Retrofit complete- A retrofit that is already complete and operational. Retrofit In-Progress - Site is Awarded on a Task Order. Retrofit Planned - Site eligibility is being assessed fo future task order. | Name of Task Order (TO) that site is included on e.g. TO2 for ND and SD, T01 for NE, etc. | Date that the SATOC was awarded. Null means not yet awarded. | Date that site MUST be operational according to USACE Contract. Null means not yet awarded or unknown. | Date that the Mesonets have stated in their work plans that they will have the site operational by. | Repsonsible Party for Completing NEPA and Sec 106 Work. | Where are we at in the cultural clearance process | Type (Size) of Sec 106 Survey done based on area. Existing site is 1 -acre. Moved more that 100 feet from exisiting site or new site is 3- acres. | Date that REC (NEPA) was signed. Null [Not Begun], Complete - Date | Date that the Soil Assessment fieldwork is scheduled. | Tracks if the Site Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Date that installation is reported completed | Status of Data Transmission with MADIS
Options (may not be all inclusive for some categories) | E.g. Wapiti 6E | E.g. SHMW4 | Y (Yes) | Private | New | [6 empty] | Montana | MT Climate Office | 1 | Existing | Intitial Purchase Order | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | USACE Contractor | MM/DD/YYYY- Anticipated data of field workd | 1-acre | Null | Null [No date scheduled] | Null [Not Submitted] | null [not submitted], | null [not submitted], | MM/DD/YYYY | Site not operational
| Worland |  | N (No) | City | Existing | [6 empty] | Nebraska | NE Mesonet | 2 | Candidate | TO1 |  |  |  | USACE Staff | In-Progress SHPO/THPO - field work is done - now is it moving through the USACE and SHPO/THPO process | 3-acre | In-Progress | MM/DD/YYY [Date that fieldwork is scheduled] | N [Task Order Awarded but report not submitted] | N [station online but report not submitted], | N [station online for 1 year but report not submitted], |  | Site not transmitting
|  |  |  | State | Existing - Moved more than 100 Feet | [6 empty] | North Dakota | NDAWN | 3 | Available | TO2 |  |  |  | Agency Name | Complete - all work is complete |  | Complete - DD/MM/YYYY | I [Fieldwork Complete, Lab work not complete] | Y [Report Submitted and Received] | Y [report submitted] | Y [report submitted] |  | Site transmitting
|  |  |  | Federal (Many agencies) | [7 empty] | South Dakota | SD Mesonet | 4 | In-Progress | TO3 | [6 empty] | Flag | C [Fieldwork and Lab work Complete]
|  |  |  | Tribal Lands | [7 empty] | Wyoming | WACNet |  | Complete | TO4
TO5

## Notes
All SD, and BLM site locations have been verified with Nathan Edwards and Kevin Hyde respectively
all TO2 ND sites verified by Daryl Ritchinson
TO1 ND proposed cordinates are coordinates surveyed by Megan and Levi