## All Site Info
Site | Grid Cell ID | NWS LI ID | Land Ownership Category | Landownership Detail | Site Type (New, Existing, Existing - Moved > 100 ft) | Latitude | Longitude | Elevation | County | State | Owner | Station Status | Station Status Note | Project Year (PY) | Installation Task Order & Fiscal Year | Installation Task Order Date Award | Contract Installation Deadline | O&M Period of Performance | Cultural Survey & Sec 106 Responsible Party | Section 106 Status | NEPA Status (Date REC Signed) | NRCS Soil Survey Status | Candidate Site Form_Site Report- Date Received | Station Report - Date Received | Annual Report - Date Received | Equipment Installation Complete | Data Transmitting | NOTES
Bozeman | D-11 | BZNM8 | State | Montana State University | Existing | 45.6621 | -111.0463 | 4927 | Gallatin | Montana | MT Climate Office | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-09 | n/a | n/a | USACE Contractor | Complete | Complete | 2021-09-10 | Y | Y | Y | 2020-10-30 | 2021-11-19
Absarokee W | G-12 | KEEM8 | Private |  | Existing | 45.5573 | -109.6112 | 4608 | Stillwater | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-03 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-02 | 2021-11-19
Broadview E | I-10 | BDVM8 | Private |  | Existing | 46.1282 | -108.7554 | 4095 | Yellowstone | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-14 | 2021-11-19
Crow Agency E | L-12 | CROM8 | Tribal Lands | Crow indian reservation | Existing | 45.5861 | -107.4383 | 3119 | Big Horn | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-04 | 2021-11-19
Havre ARC | H-3 | HAEM8 | University | Agriculture Research Center - Montana State University | Existing | 48.4891 | -109.7994 | 2721 | Hill | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-05-19 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-05-12 | 2021-11-19
Ingomar NE | M-9 | IGMM8 | Private |  | Existing | 46.6568 | -107.2238 | 3098 | Rosebud | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-04 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-08-12 | 2021-11-19
Melville SE | G-10 | MLVM8 | Private |  | Existing | 46.0015 | -109.8416 | 4710 | Sweet Grass | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-17 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Miles City | O-9 | MCYM8 | Federal | USDA- Agricultural Research Service | Existing | 46.4054 | -105.9543 | 2718 | Custer | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-07-07 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-08-25 | 2021-11-19
Moccasin ARC | G-7 | MCIM8 | University | Agriculture Research Center - Montana State University | Existing | 47.0585 | -109.9535 | 4257 | Judith Basin | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-08-27 | 2022-01-04 | 2022-02-11 | 2021-05-13 | 2021-11-19
Roundup NE | J-9 | ROUM8 | Private |  | Existing | 46.5785 | -108.4243 | 3448 | Musselshell | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-06-08 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-06-09 | 2021-11-19
Sidney ARC | S-5 | SIYM8 | University | Agriculture Research Center - Montana State University | Existing | 47.7823 | -104.2479 | 2260 | Richland | Montana | MT Climate Office | Complete | Install 2021 | PY1 | TO1 MT (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Contractor | Complete | Complete | 2021-08-24 | 2021-12-01 | 2022-01-04 | 2022-02-11 | 2021-09-12 | 2021-11-19
Benton Lake W | D-5 | BLWM8 | Private |  | Existing | 47.6907 | -111.4736 | 3706 | Cascade | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-08 | na | 2022-12-12 | 2023-08-25 | 2022-10-21 | 2022-11-01
Big Timber SE | G-11 | BTSM8 | Private |  | Existing | 45.7435 | -109.8267 | 4423 | Sweet Grass | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-20 | na | 2022-12-12 | 2023-08-25 | 2022-08-23 | 2022-09-01
Coffee Creek N | G-6 | CFCM8 | Private |  | Existing | 47.3935 | -110.1083 | 3739 | Fergus | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-09-07 | na | 2022-12-12 | 2023-08-25 | 2022-09-19 | 2022-09-22
Cooney Reservoir NW | H-12 | COOM8 | Private |  | Existing | 45.4658 | -109.2597 | 4702 | Stillwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-21 | na | 2022-12-12 | 2023-08-25 | 2022-08-20 | 2022-09-01
Huntley ARC | J-11 | HNTM8 | University | Agriculture Research Center - Montana State University | Existing | 45.9264 | -108.233 | 3055 | Yellowstone | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-06-03 | na | 2022-12-12 | 2023-08-25 | 2022-09-29 | 2022-11-01
MDA Oilmont | D-1 | OILM8 | Private |  | Existing | 48.7816 | -111.6011 | 3597 | Toole | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-05-17 | na | 2022-12-12 | 2023-08-25 | 2022-09-16 | 2022-09-22
MDA Toston | C-10 | TTNM8 | Private |  | Existing | 46.1365 | -111.5432 | 4067 | Broadwater | Montana | MT Climate Office | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO2 MT (FY21) | 2021-09-13 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-19 | na | 2022-12-12 | 2023-08-25 | 2022-09-21 | 2022-09-22
Midway Colony | C-4 | RADM8 | Private |  | New | 48.061 | -112.0077 | 3778 | Pondera | Montana | MT Climate Office | Complete | Replacement for Conrad ARC on TO2 | PY2 | TO2 MT (FY21) MOD | 2022-07-12 | 2022-10-30 | 2023-10-30 | USACE Contractor | Complete | Complete | 2022-05-18 | na | 2022-12-12 | 2023-08-25 | 2022-10-24 | 2022-11-01
Ashland E | O-12 | ASAM8 | Federal | USFS | New | 45.5733 | -106.1432 | 3185 | Powder River | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-20 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Brady NE | D-4 | BRYM8 | Private |  | New | 48.1032 | -111.6643 | 3376 | Pondera | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-29 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Busby S | M-12 | BUSM8 | Private on Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.5186 | -106.9316 | 3582 | Big Horn | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-17 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Bynum W | B-4 | BYUM8 | Private |  | New | 47.9572 | -112.4944 | 4439 | Teton | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-28 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Chester SW | E-3 | CHSM8 | Private |  | New | 48.4477 | -111.0376 | 3103 | Liberty | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-30 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Dupuyer N | B-3 | DYRM8 | Private |  | New | 48.2956 | -112.5492 | 3890 | Pondera | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-27 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Forestgrove N | I-7 | FRGM8 | Private |  | New | 47.1058 | -109.0888 | 4103 | Fergus | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-09-28 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Harlowton E | G-9 | HWTM8 | Private |  | New | 46.413 | -109.7009 | 4086 | Wheatland | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Lame Deer E | N-12 | LMDM8 | Tribal Lands | Northern Cheyenne Indian Reservation | New | 45.656 | -106.4879 | 4265 | Rosebud | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Aug 2022 | 2022-08-31 | 2023-07-19 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Lavina N | I-9 | LVAM8 | Private |  | New | 46.3989 | -108.9536 | 3684 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-09 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Lodge Grass W | L-13 | LGGM8 | Private on Tribal Lands | Crow indian reservation | New | 45.3073 | -107.5154 | 3824 | Big Horn | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-18 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Loring SW | L-2 | LORM8 | Private |  | New | 48.7716 | -107.8779 | 2821 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-01 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Matador Ranch | K-5 | MTRM8 | Non-Profit | The Nature Conservancy | New | 47.9264 | -108.3359 | 3027 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-04 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Molt S | I-11 | MOTM8 | Private |  | New | 45.8414 | -108.9592 | 3899 | Stillwater | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Mosby NW | K-7 | MOBM8 | Private |  | New | 47.0611 | -108.098 | 2989 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-21 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Mosby S | K-8 | MOYM8 | Private |  | New | 46.7823 | -107.9213 | 2805 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-10-16 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Musselshell | K-9 | MSSM8 | Private |  | New | 46.54 | -108.0218 | 3132 | Musselshell | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-10-20 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Otter E | O-13 | OTRM8 | Federal | USFS | New | 45.2469 | -105.9845 | 3936 | Powder River | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-07-21 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Rapleje SW | H-11 | RAPM8 | Private |  | New | 45.8858 | -109.4211 | 4710 | Stillwater | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Rothiemay W | H-9 | RMYM8 | Private |  | New | 46.5351 | -109.3477 | 4364 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-08 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Roy E | J-6 | RYOM8 | Private |  | New | 47.3791 | -108.6778 | 3038 | Fergus | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Ryegate S | H-10 | RGTM8 | Private |  | New | 46.1995 | -109.3111 | 4272 | Golden Valley | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-05-10 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Saco S | M-4 | SASM8 | Private |  | New | 48.2908 | -107.3912 | 2741 | Phillips | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-03 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Sand Springs NW | L-7 | SDSM8 | Private |  | New | 47.1653 | -107.6384 | 3007 | Garfield | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-25 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Scobey NW | Q-2 | SCYM8 | Private |  | New | 48.8602 | -105.4972 | 2467 | Daniels | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-06-15 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Sun River SE | C-6 | SURM8 | Private |  | New | 47.4118 | -111.7173 | 3596 | Cascade | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-09-27 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Turner N | K-2 | TRNM8 | Private |  | New | 48.8743 | -108.3937 | 3073 | Blaine | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-02 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Twodot E | F-9 | TWOM8 | Private |  | New | 46.4468 | -110.2055 | 4643 | Wheatland | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Valentine E | K-6 | VLTM8 | Private |  | New | 47.358 | -108.2438 | 2904 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
War Horse NW | J-7 | WRHM8 | Private |  | New | 47.1472 | -108.5913 | 3151 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-23 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Winnett SW | J-8 | WIEM8 | Private |  | New | 46.9654 | -108.5024 | 3202 | Petroleum | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-24 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30
Bowmans Corner NW | B-6 | BNWM8 | Private | Private | New | 47.308 | -112.1728 | 4267 | Lewis & Clark | Montana | MT Climate Office | Complete | Install 2023 | PY3 | TO3 MT (FY22) MOD | 2023-09-13 | 2023-11-30 | 2024-11-30 | USACE Contractor | Aug 2022 | 2022-08-31 | 2023-08-24 | 2022-10-01 | 2023-12-22 | 2024-01-26 | 2023 | 2023-09-30 | FPPA >160
Springdale | F-11 |  | Private | Private | New | 45.7465 | -110.1568 | 4294 | Sweet Grass | Montana | MT Climate Office | Candidate | Submitted as new location for Springdale | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST | [5 empty] | Submitted as new location for Springdale N
The Pines | N-05 |  | Federal | USACE | New | 47.8549 | -106.6674 | 2410 | Valley | Montana | MT Climate Office | Candidate | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST
Carrington | AD-6 | CRGN8 | University | NDSU | Existing | 47.5086 | -99.1323 | 1561 | Foster | North Dakota | NDAWN | Complete | Install 2021 | na | Not on USACE Task Order | na | na | na |  | na | na | na | na | na | na | Y | 2021-11-19
Robinson | AB-7 | ROBN8 | Private |  | Existing | 47.173 | -99.7982 | 1829 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-08-18 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-05 | 2021-11-19
Streeter | AC-8 | STRN8 | University | NDSU | Existing | 46.718 | -99.4608 | 1992 | Kidder | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-19 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-07-20 | 2021-11-19
Courtenay | AE-7 | CURN8 | Private |  | Existing | 47.2212 | -98.6799 | 1522 | Stutsman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-01 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-07-15 | 2021-11-19
Oakes | AF-10 | OKNN8 | University | NDSU | Existing | 46.0667 | -98.1031 | 1323 | Dickey | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-09-02 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-29 | 2021-11-19
Fortuna | T-2 | FTUN8 | Private |  | Existing | 48.9637 | -103.8058 | 2246 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-07 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-09 | 2021-11-19
Grenora | T-3 | GREN8 | Private |  | Existing | 48.735 | -103.8812 | 2108 | Divide | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-08 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-08 | 2021-11-19
Williston | T-4 | WLLN8 | University | NDSU | Existing | 48.1331 | -103.739 | 2132 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-22 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-15 | 2021-11-19
Bowman | U-10 | BOMN8 | Private |  | Existing | 46.1997 | -103.473 | 3032 | Bowman | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-28 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-09 | 2021-11-19
Ray | U-3 | RAYN8 | Private |  | Existing | 48.4009 | -103.169 | 2316 | Williams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-09 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-10 | 2021-11-19
Amidon | U-9 | AIDN8 | Private |  | Existing | 46.4885 | -103.316 | 2883 | Slope | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-29 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-09-08 | 2021-11-19
Mott | W-10 | MATN8 | Private |  | Existing | 46.3798 | -102.322 | 2473 | Hettinger | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-30 | 2022-08-27 | 2022-01-31 | 2022-03-04 | 2021-07-01 | 2021-11-19
Hettinger | W-11 | HTGN8 | University | NDSU | Existing | 46.0126 | -102.6453 | 2758 | Adams | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-09-15 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-06-30 | 2021-11-19
Hazen | X-7 | HAZN8 | Private |  | Existing | 47.3018 | -101.6792 | 1849 | Mercer | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO2 ND (FY20) | 2021-03-24 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | 2021-02-08 | 2021-08-23 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2021-08-10 | 2021-11-19
Carson | Y-9 | CSRN8 | Private |  | Existing | 46.443 | -101.3738 | 2107 | Grant | North Dakota | NDAWN | Complete | Install 2021 | PY1 | TO1 ND (FY20) | 2020-09-28 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete | 2021-08-12 | 2022-01-31 | 2022-01-31 | 2022-03-04 | 2022-06-29 | 2021-11-19
Steele | AB-8 | SEEN8 | Private |  | Existing | 46.894 | -99.9927 | 1862 | Kidder | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-09-29 | Complete | 2022-12-02 | 2023-01-10 | 2022-09-23 | 2022-09-28
Wishek | AC-10 | WISN8 | Private |  | Existing | 46.2599 | -99.6658 | 2219 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-26 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-15 | 2022-09-28
Zeeland | AC-11 | ZELN8 | Private |  | Existing | 46.0133 | -99.6877 | 2070 | McIntosh | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-26 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-16 | 2022-09-28
Jamestown | AD-8 | JSTN8 | Private |  | Existing | 46.9064 | -98.9274 | 1639 | Stutsman | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2/8/2021 | 2022-09-29 | Complete | 2022-12-02 | 2023-01-10 | 2022-09-16 | 2022-09-28
Edgeley | AE-9 | EDGN8 | Private |  | Existing | 46.3192 | -98.7661 | 1649 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-09-12 | Complete | 2022-12-02 | 2023-01-10 | 2022-09-02 | 2022-09-28
Marion | AF-9 | MARN8 | Private |  | Existing | 46.5645 | -98.3276 | 1453 | LaMoure | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-25 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-10 | 2022-09-28
Redstone | R-2 | RSTM8 | Private |  | Existing | 48.8246 | -104.8417 |  | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE | Complete | Complete 8/30/2021 | 2022-06-28 | Complete | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Dooley | S-2 | DOOM8 | Private |  | Existing | 48.8337 | -104.3846 |  | Sheridan | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-30 | Complete | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Froid | S-4 | FROM8 | Federal | USDA | Existing | 48.2579 | -104.4967 |  | Roosevelt | Montana | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 2022-06-29 | Complete | 2022-12-02 | 2023-01-10 | 2022-06-23 | 2022-10-28
Beach | T-8 | BCHN8 | Private |  | Existing | 46.7894 | -103.9662 | 2932 | Golden Valley | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-07-06 | Complete | 2022-12-02 | 2023-01-10 | 2022-06-09 | 2022-09-28
Grassy Butte 2E | U-6 | GSBN8 | Private |  | Existing | 47.3865 | -103.2062 | 2688 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-21 | Complete | 2022-12-02 | 2023-01-10 | 2022-07-12 | 2022-09-28
Keene 5SW | V-5 | KEEN8 | Private |  | Existing | 47.8938 | -103.0482 | 2346 | McKenzie | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-07-26 | Complete | 2022-12-02 | 2023-01-10 | 2022-07-13 | 2022-09-28
Dickinson | V-8 | DKSN8 | University | NDSU | Existing | 46.8948 | -102.8131 | 2557 | Stark | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete | 2022-08-03 | Complete | 2022-12-02 | 2023-01-10 | 2022-06-10 | 2022-09-29
Garrison | X-5 | GANN8 | Private |  | Existing | 47.7102 | -101.6795 | 2200 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-16 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-03 | 2022-09-28
Turtle Lake | Z-6 | TURN8 | Private |  | Existing | 47.5679 | -100.9153 | 1927 | McLean | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-08-30 | 2022-08-16 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-02 | 2022-09-28
Mandan | Z-8 | MMDN8 | Federal | USDA | Existing | 46.7736 | -100.9139 | 1907 | Morton | North Dakota | NDAWN | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 ND (FY21) | 2021-09-21 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | 2021-02-08 | 2022-08-18 | Complete | 2022-12-02 | 2023-01-10 | 2022-08-15 | 2022-09-28
Wing | AA-7 | WNGN8 | Private |  | New | 47.2719 | -100.3303 | 1973 | Burleigh | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-05-19 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
McKenzie 2E | AA-8 | MCKN8 | Private |  | New | 46.8222 | -100.3617 | 1773 | Burleigh | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-22 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Linton | AB-10 | LINN8 | Private |  | Existing | 46.3268 | -100.2809 | 1966 | Emmons | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-09 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Ypsilanti | AE-8 | YPLN8 | Private |  | New | 46.7764 | -98.5236 | 1483 | Stutsman | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-29 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Marmarth 2N | T-10 | MRNN8 | Private |  | New | 46.3228 | -103.9374 | 2840 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-28 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Poker Jim | T-6 | PKJN8 | Private |  | Existing | 47.5025 | -103.6559 | 2092 | McKenzie | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-18 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Sentinel Butte 10N | T-7 | SLBN8 | Private |  | Existing | 47.0669 | -103.7933 | 2736 | Golden Valley | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-11 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Davis Dam 2NW | T-9 | DVDN8 | Private |  | New | 46.5641 | -103.6971 | 2906 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-06-23 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Fairfield | U-7 | FLDN8 | Private |  | Existing | 47.1253 | -103.2432 | 2682 | Billings | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-09-22 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
New England 5W | V-9 | NEDN8 | Private |  | New | 46.5264 | -102.968 | 2718 | Slope | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-03 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Pretty Rock 2E | X-10 | PTON8 | Private |  | New | 46.1597 | -101.7705 | 2514 | Grant | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-10-17 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Shell Lake | X-4 | SHLN8 | Private |  | Existing | 48.1501 | -102.0727 | 2058 | Mountrail | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-22 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Glen Ullin (Hebron) | X-8 | HBNN8 | Private |  | New | 46.8045 | -102.0759 | 2450 | Morton | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-10 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Pick City 8SW | Y-6 | PCDN8 | Private |  | New | 47.4747 | -101.6123 | 2045 | Mercer | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-15 | 2022-08-27 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Sanger | Z-7 | SNRN8 | Private |  | New | 47.1668 | -100.9891 | 1689 | Oliver | North Dakota | NDAWN | Complete | Install 2023 | PY3 | TO4 ND (FY22) | 2022-10-21 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete Aug 2022 | 2022-08-31 | 2023-08-25 | 2022-10-15 | 2024-01-10 | 2024-01-10 | 2023 | 2023-09-30
Boyd 1 (Lynch 2W) | AF-20 | LYHN1 | State | State Educational Lands and Funds - Leased Public | New | 42.8411 | -98.5037 | 1583 | Boyd | Nebraska | NE Mesonet | Complete | Submitted as candidate site Oct 2021 - On Task Order Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-09-07 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023 | 2023-10-30
Boyd 2 (Naper 2W) | AE-20 | NARN1 | State | State Educational Lands and Funds - Leased Public | New | 42.9663 | -99.1388 | 2105 | Boyd | Nebraska | NE Mesonet | Complete | Submitted as candidate site Oct 2021 - On Task Order Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-10-10 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023 | 2023-10-30
Cedar 2 (Fordyce 4NW) | AI-20 | FRDN1 | State | State Educational Lands and Funds - Leased Public | New | 42.7493 | -97.3981 | 1520 | Cedar | Nebraska | NE Mesonet | Complete | Submitted as candidate site Oct 2021 - On Task Order Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-09-11 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023 | 2023-10-30
Cherry 1 (Merriman 21S) | Y-21 | MEIN1 | State | State Educational Lands and Funds - Leased Public | New | 42.6154 | -101.7244 | 3619 | Cherry | Nebraska | NE Mesonet | Complete | Submitted as candidate site Oct 2021 - On Task Order Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | NEED TO FILL IN | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023 | 2023-10-30
Knox 2 (Orchard 10N) | AG-21 | OHDN1 | State | State Educational Lands and Funds - Leased Public | New | 42.4907 | -98.2611 | 1556 | Knox | Nebraska | NE Mesonet | Complete | Submitted as candidate site Oct 2021 - On Task Order Install 2023 | PY3 | TO 2 NE (FY22) | 2023-02-27 | 2023-10-30 | 2024-10-30 | USACE Contractor | Complete | Complete | 2023-10-11 | 2021-10-15 | 2023-12-19 | 2024-01-18 | 2023 | 2023-10-30
Sheridan 1 (Ellsworth 16NE) | X-22 | ESWN1 | State | State Educational Lands and Funds - Leased Public | New | 42.2803 | -102.1628 | 4130 | Sheridan | Nebraska | NE Mesonet | Complete | Submitted at Candidate 2021 - Sub for Long Pine - Install 2022 | PY2 | TO 1 NE (FY21) Mod. | 2022-11-01 | 2022-12-31 | 2023-12-31 | USACE Contractor | Complete | Complete | NEED TO FILL IN | 2021-10-15 | 2023-12-19 | 2024-01-18 | NEED TO FILL IN | 2023-10-30 | Replacement for Longpine on TO1. Modification. Supposed to be by Dec 2022 but delayed through the summer. O&M date will still end in Dec. 2023
Brookings | AJ-15 | BKMS2 |  |  | Existing | 44.325 | -96.7685 | 1640 | Brookings | South Dakota | SD Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-08 |  |  | USACE Contractor | Complete | Complete | 2019-06-13 | 2022-08-27 | Y | Y | Y | 2021-11-19
Bowdle | AC-12 | BWLS2 | City | Non-federal airport property | Existing | 45.4388 | -99.6733 | 1965 | Edmunds | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Caputa | V-17 | CPTS2 |  |  | Existing | 44.0008 | -103.0008 | 2931 | Pennington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-07-30 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-18 | 2021-11-19
Edgemont | T-19 | EDTS2 |  |  | Existing | 43.4737 | -103.9717 | 3710 | Fall River | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2021-07-29 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-20 | 2021-12-15
Highmore | AD-15 | HIHS2 |  |  | Existing | 44.5256 | -99.4601 | 1879 | Hyde | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-06-19 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-22 | 2021-12-23
Leola | AE-11 | LLAS2 |  |  | Existing | 45.7165 | -98.9311 | 1571 | McPherson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-05-01 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-10 | 2021-12-15
Oacoma | AD-17 | OCMS2 |  |  | Existing | 43.7982 | -99.4156 | 1443 | Lyman | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete | 2019-07-02 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-04 | 2021-11-19
Union Center | W-15 | UNIS2 | City | Non-federal airport property | Existing | 44.5665 | -102.671 | 2938 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2022 | 2021-07-22 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-12-02 | 2021-12-15
White River | AA-18 | WRIS2 | City | Non-federal airport property | Existing - Moved > 100ft | 43.5586 | -100.7423 | 2140 | Mellette | South Dakota | SD Mesonet | Complete | Installed in 2021 | PY1 | TO1 SD (FY20) | 2020-09-29 | 2022-01-15 | 2023-01-15 | USACE Staff | Complete | Complete 9/10/2021 | 2022-06-09 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-11-24 | 2021-12-15
Beresford | AJ-19 | BFMS2 | University | SDSU | Existing - Moved > 100ft | 43.0404 | -96.9011 | 1278 | Clay | South Dakota | SD Mesonet | Complete | Install 2021; Sub for Martin on T01 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2021 | 2021-04-13 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-09 | 2021-12-23
Timber Lake | Z-12 | TIMS2 | City |  | Existing | 45.4166 | -101.085 | 2196 | Dewey | South Dakota | SD Mesonet | Complete | Install 2021; Sub For Faulkton on TO1 | PY1 | TO1 SD (FY20) Mod | 2021-12-03 | 2022-01-15 | 2023-01-15 |  | Complete | Complete 2/25/2021 | 2019-06-27 | 2022-08-27 | 2022-01-26 | 2022-01-18 | 2021-12-18 | 2021-12-15
Cottonwood | X-17 | CTWS2 |  |  | Existing | 43.9599 | -101.8539 | 2365 | Jackson | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-05 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Groton | AG-12 | GOTS2 |  |  | Existing | 45.5735 | -98.0301 | 1309 | Brown | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
South Shore | AI-13 | SHSS2 |  |  | Existing | 45.1055 | -97.1024 | 1850 | Codington | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-12 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-23
Sturgis | U-16 | STMS2 |  |  | Existing | 44.4245 | -103.3793 | 3237 | Meade | South Dakota | SD Mesonet | Complete | Install 2021 | PY1 | TO2 SD (FY20) | 2021-03-20 | 2021-11-30 | 2022-11-30 | USACE Contractor | Complete | Complete 2/25/2021 | 2019-06-25 | 2022-01-26 | 2022-01-26 | 2022-01-18 | 2021-11-27 | 2021-12-15
Antelope | U-12 | ATRS2 | Private |  | Existing | 45.5193 | -103.2888 | 2903 | Harding | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/19/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Flandreau | AJ-16 | FLNS2 | Private |  | Existing | 44.0867 | -96.5849 | 1624 | Moody | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 8/31/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Hamill | AC-18 | HMLS2 | Private |  | Existing | 43.5938 | -99.7122 | 1863 | Tripp | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/24/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Nisland | U-15 | NISS2 | Federal | BOR | Existing | 44.6783 | -103.5606 | 2906 | Butte | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 2/25/2021 | 6/12/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Rosebud | AA-19 | RBMS2 | Tribal Lands | Rosebud Sioux Tribe | Existing | 43.2002 | -100.7208 | 2808 | Todd | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | Rosebud Tribe | Complete | Complete 8/5/2021 | 9/1/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Sioux Falls | AJ-18 | SFSS2 | Private |  | Existing | 43.5048 | -96.7623 | 1407 | Minnehaha | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 | USACE Contractor | Complete | Complete 8/30/2021 | 6/14/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
White Lake | AE-17 | WTES2 | Private |  | Existing | 43.7372 | -98.6936 | 1637 | Aurora | South Dakota | SD Mesonet | Complete | Awarded in Sept 2021; Install 2022 | PY2 | TO3 SD (FY21) | 2021-09-29 | 2022-09-30 | 2023-09-30 |  | Complete | Complete 3/7/2021 | 8/19/2022 (Orig. Sampling in 2019) |  | 2024-02-28 | 2024-02-28 | Y | 2022-08-20
Loma | F-04 |  | Private | Private | New | 47.9537 | -110.4917 | 2768 | Choteau | Montana | MT Climate Office | Candidate | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST
Jewel Cave | T-18 | JWLS2 | Federal | NPS - Jewel Cave National Monument | Existing | 43.7343 | -103.8278 | 5672 | Custer | South Dakota | SD Mesonet | In-Progress | Awarded in Sept 2021; Extended Installation POP to 2024 | PY4 | TO3 SD (FY21) Mod. | 2022-08-15 | 2024-09-30 | 2025-09-30 | NPS | Complete | Complete 8/30/2021 | Push to 2024 | 2022-08-27 |  |  |  |  | NPS decided they needed a a more complete tribal review & Special Use Permit (SUP). Has delayed the install on this. CIRE Proj coord. Has been in direction communication with Mike Wiles from NPS to keep moving forward.
Hayes 7SW | Z-16 | HAMS2 | Private | FPPA Statewide Importance Farmland | New | 44.3123 | -101.1292 | 2025 | Stanley | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-13 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Lecther 2ENE | AG-17 | LCMS2 | Private |  | New | 43.9029 | -98.1096 | 1306 | Sanborn | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-12 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Milesville 11W | X-15 | MVMS2 | Private | FPPA Prime Farmland | New | 44.4749 | -101.8991 | 2338 | Haakon | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-04 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Norris 10NNE | Z-18 | NOMS2 | Private |  | New | 43.5998 | -101.1013 | 2454 | Mellette | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-06 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Onida 13WSW | AB-15 | ONMS2 | Private on Tribal Lands | Crow Creek Indian Reservation; FPPA Prime Farmland | New | 44.6463 | -100.3202 | 1757 | Sully | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-13 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Provo 11S | T-20 | PVMS2 | Private |  | New | 43.0375 | -103.7986 | 3797 | Fall River | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-17 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Ralph 11NE | V-11 | RAMS2 | Private |  | New | 45.9061 | -102.9228 | 2742 | Perkins | South Dakota | SD Mesonet | Complete | Awarded June 2022; Install 2022 | PY2 | TO4 SD (FY22) [FY21 Funds] | 2022-06-24 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | Complete | 2022-10-20 | 2022-08-27 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Colome 4NNE | AC-19 | WNMS2 | Private |  | New | 43.3141 | -99.693 | 2097 | Tripp | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-05-25 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2022-09-30
Dallas 7S | AD-19 | GGMS2 | Private |  | New | 43.1374 | -99.4933 | 2189 | Gregory | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-05-26 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Kennebec 6SSE | AC-17 | KBMS2 | Private |  | New | 43.816 | -99.8254 | 1772 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-17 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Lower Brule 2WNW | AC-16 | LBMS2 | Private |  | New | 44.0822 | -99.6111 | 1777 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | Tribe | Complete | 2022-08-31 | 2023-08-29 | 2022-11-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Lowry 2S | AB-13 | LRMS2 | Private |  | New | 45.2816 | -99.9774 | 2104 | Walworth | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-24 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Ludlow 16W | T-11 | LNMS2 | Private |  | New | 45.8268 | -103.7172 | 3134 | Harding | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-30 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Menno 7ESE | AH-19 | MNMS2 | Private |  | New | 43.2109 | -97.4523 | 1477 | Hutchinson | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-06-05 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Midland 3ENE | Z-17 | MLMS2 | Private |  | New | 44.0851 | -101.091 | 1851 | Haakon | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-09-21 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Mound City 4SSW | AB-12 | MCMS2 | Private - Easement | FWS Easement for Sand Lake Wetland Management District; FPPA Prime Farmland | Existing | 45.6715 | -100.1148 | 1746 | Campbell | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 | 2023-07-26 | 2022-11-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Mount Vernon | AF-17 | VNMS2 | Private |  | New | 43.7173 | -98.2793 | 3729 | Davison | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 | 2023-06-29 | 2022-11-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Oelrichs 11ESE | V-20 | FLMS2 | Private |  | New | 43.1003 | -103.0547 | 3353 | Fall River | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2022-08-31 | 2023-07-11 | 2022-11-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Oelrichs 11SSW | U-20 | OEMS2 | Private |  | New | 43.0409 | -103.3476 | 3592 | Fall River | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-10 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Prairie City 15SSW | V-13 | PCMS2 | Private |  | New | 45.3388 | -102.9195 | 2835 | Perkins | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-31 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Raymond 5ENE | AG-14 | CLMS2 | Private |  | New | 44.9374 | -97.8464 | 1736 | Clark | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-13 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Redig 3N | U-13 | RDMS2 | Private |  | New | 45.3195 | -103.5495 | 3168 | Harding | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-08-31 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Spearfish 4NNW | T-15 | SPMS2 | Private - Easement | NRCS EQIP Program | New | 44.5657 | -103.9164 | 3407 | Lawrence | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-09-19 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Spring Creek 12WNW | Z-19 | THMS2 | Private on Tribal Lands | Pine Ridge Reservation | New | 43.206 | -101.2295 | 5423 | Bennett | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 |  | Complete | 2022-08-31 | 2023-07-27 | 2022-11-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Vivian 12S | AB-18 | VVMS2 | Private |  | New | 43.7508 | -100.2963 | 1919 | Lyman | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-14 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Volga | AI-15 | VGAS2 | University | SDSU | Existing | 44.3042 | -96.9189 | 1642 | Brookings | South Dakota | SD Mesonet | Complete | Resubmittal - Replacement for Gann Valley; Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2021-08-30 | 2019-07-01 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Woonsocket 4NNW | AF-16 | WSMS2 | Private |  | New | 44.1113 | -98.3103 | 1315 | Sandorn | South Dakota | SD Mesonet | Complete | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 | 2023-07-25 | 2022-10-15 | 2024-02-28 | 2024-02-28 | Y | 2023-09-30
Carpenter 11WSW | AG-15 |  | Private |  | New | 44.6035 | -98.1298 | 1298 | Beadle | South Dakota | SD Mesonet | Removed | Install 2023 | PY3 | TO5 SD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15
Carpenter 7SW | AG-15 |  | Private | Private | New | 44.5732 | -98.0121 | 418 | Beadle | South Dakota |  | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO5 SD (FY22) MOD. Sub for Carpenter Planned
Long Lake 4NW | AD-11 |  | Private |  | New | 45.9066 | -99.2554 | 613 | McPherson | South Dakota | SD Mesonet | In-Progress | Install 2023 | PY3 | TO5 SD MOD (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Complete | 2022-08-31 |  | 2022-10-15 |  |  |  |  | Nathan Edwards sent updated location on 4/18/24
Highwood Bench | E-05 |  | Private | Private | New | 47.6848 | -110.8996 | 3329 | Choteau | Montana | MT Climate Office | Candidate | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST
Savoy SW | J-03 |  | Tribal Lands | Fort Belknap Tribes - Reservation | New | 48.417 | -108.5907 | 2459 | Blaine | Montana | MT Climate Office | Candidate | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST | [5 empty] | Replacement for Ft. Belknap and Hayes sites from 2023 on Ft. Belknap Tribes
Dry Lake | J-04 |  | Tribal Lands | Fort Belknap Tribes - Reservation | New | 48.0419 | -108.6416 | 3418 | Blaine | Montana | MT Climate Office | Candidate | Submitted as Candidate Fall 2023 - Proposed for 2nd TO Fy23 - Install 2024 | PY4 | 2nd FY23 TO5 (Planned) | [6 empty] | MAKE SURE ON 2025 LIST | [5 empty] | Replacement for Ft. Belknap and Hayes sites from 2023 on Ft. Belknap Tribes
Little Fork | M-15 |  | Private | Private | New | 44.4898 | -106.5722 | 4836 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Tipperary | N-16 |  | Private | Private | New | 44.4079 | -106.3951 | 4098 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Blue Butte | O-16 |  | Private | Private | New | 44.2127 | -106.1034 | 4054 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2022-10-31
Sheridan | M-14 | SHMW4 | Univeristy | UWY | New | 44.8407 | -106.839 | 3738 | Sheridan | Wyoming | Wyoming Mesonet | Complete | Pilot Station; Installed in 2020 | Pilot Year | Initial Purchase Order (FY19) | 2020-04-10 |  |  | USACE Contractor | Complete | Complete | 2022-07-28 | Y | Y | Y | Y | Y
Falxa | O-17 |  | Private | Private | New | 44.0276 | -106.1749 | 4144 | Johnson | Wyoming | Wyoming Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | REMOVED | [7 empty] | 2023-01-12 |  |  |  |  | Landowner did not agree to location - removing and waiting on new location from Ginger 5/1/2023
Alliance 3SW | V-23 |  | State | Nebraska School Lands | New | 42.058 | -102.894 | 3959 | Box Butte | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Gordon 13SE | X-21 |  | University | Board of Regents (UNL) | New | 42.6483 | -102.0689 | 3625 | Sheridan | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Harrison 2SW | T-21 |  | University | Board of Regents (UNL) | New | 42.664 | -103.898 | 4910 | Sioux | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Powell | I-14 | PLMW4 | Univeristy | UWY | New | 44.7764 | -108.759 | 4372 | Park | Wyoming | Wyoming Mesonet | Complete | Install 2021 | PY1 | TO1 WY (FY20) | 2020-09-28 | 2021-09-30 | 2022-09-30 | USACE Staff | Complete | Complete | 2022-08-03 | 2022-02-24 | 2022-02-24 | 2022-03-29 | 2021-12-17 | Y
Wapiti 6E (Buffalo Bill Reservoir) | I-15 | BBMW4 | Federal | BOR | New | 44.4817 | -109.3083 | 5433 | Park | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 1/7/2022 | 2022-08-17 | na | 2023-10-30 | 2023-10-30 | 2022-09-15 | 2022-12-22
Worland 3E | K-17 | WRMW4 | Federal | BOR | New | 44.0026 | -107.905 | 4203 | Washakie | Wyoming | Wyoming Mesonet | Complete | MOD on TO1 award; Install 2022 | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 2022-01-07 | 2022-08-24 | na | 2023-10-30 | 2023-10-30 | 2022-09-22 | 2022-12-22
Fort_Washakie | I-20 | FWMW4 | Tribal Lands | Wind River Tribe | New | 43.005 | -108.8803 | 5571 | Fremont | Wyoming | Wyoming Mesonet | In-Progress | 106 and NEPA complete. Waiting on RE. | PY2 | TO1 WY (FY20) MOD | 2022-08-15 | 2022-12-30 | 2023-12-30 | USACE Staff | Complete | 2022-01-20 | Push to 2024 | na
Shoshoni 6NNW (Boysen Reservoir) | J-19 | BYMW4 | Federal | BOR | New | 43.3239 | -108.1331 | 4761 | Fremont | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) | 2022-09-21 | 2022-09-30 | 2023-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-09-21 | na | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Cowley 4NNE | J-14 | CYMW4 | Federal | BOR | New | 44.9291 | -108.4324 | 4121 | Big Horn | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 8/30/2021 | 2022-10-12 | na | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Pavillion 13W (Diversion Dam) | I-19 | DDMW4 | Federal | BOR | New | 43.2314 | -108.9515 | 5682 | Fremont | Wyoming | Wyoming Mesonet | Complete | Install 2022 | PY2 | TO2 WY (FY21) MOD | 2022-09-21 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete | 2021-08-30 | 2022-10-19 | 2022-08-27 | 2023-10-30 | 2023-10-30 | 2022-09-29 | 2022-09-30
Carlile 2S | R-16 | CRMW4 | Private | Private | New | 44.4485 | -104.8021 | 4344 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | 2023-06-29 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Crook 3 (Aladdin 5SW) | S-15 | ALMW4 | Private | Private | New | 44.5871 | -104.2483 | 4021 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-07-27 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Crook 4 (Hulett 6NW) | R-15 | HUMW4 | Private | Private | New | 44.7389 | -104.6962 | 4442 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-08-09 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Crook 5 (Four Corners 11NW) | S-16 | FCMW4 | Private | Private | New | 44.1959 | -104.2952 | 5415 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-06-28 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Crook 6 (Alva 12NNW) | R-14 | AVNW4 | Private | Private | New | 44.8605 | -104.5444 | 3613 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-08-08 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Devils Tower 16WNW | Q-15 | DTMW4 | Private | Private | New | 44.713 | -105.014 | 4012 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | 2023-09-19 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Hay Spring 12W | V-21 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.6146 | -102.9095 | 4236 | Dawes | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Hay Springs 22S | W-22 |  | University | Board of Regents (UNL) | New | 42.3697 | -102.6491 | 3924 | Sheridan | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Hemingford 9NE | V-22 |  | State | Nebraska School Lands | New | 42.4087 | -102.9395 | 4088 | Box Butte | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Marsland 6S | U-22 |  | State | Nebraska School Lands | New | 42.3557 | -103.3313 | 4525 | Box Butte | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.; Swift fox measures requied by NE Game and Parks.
Rushville 2SE | W-21 |  | State | Nebraska Board of Educational Lands and Funds | New | 42.7122 | -102.4373 | 3811 | Sheridan | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Whitney 4SW | U-21 |  | University | Board of Regents (UNL) | New | 42.7423 | -103.3179 | 3492 | Dawes | Nebraska | NE Mesonet | In-Progress | Install 2024 | PY4 | TO 3 NE (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - Whooping Crane surveys Required by USFWS.
Wessington 3W | AE-15 |  | Private - Easement | NRCS Conservation Reserve Program | New | 44.4592 | -98.7614 |  | Hand | South Dakota | SD Mesonet | In-Progress | Submitted as candidate site Oct 2021; Resubmitted with new location |  | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | [8 empty] | FPPA Site - Score >160; AD-1006 form submitted
Big Sandy NW | G-03 |  | Private | Private | New | 48.2416 | -110.3217 | 2858 | Choteau | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | Scheduled fo 2024 | [5 empty] | FPPA <160
Big Sandy SE | G-4 |  | Private | Private | New | 48.034 | -110.0359 | 3099 | Choteau | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Billings S | J-12 |  | Private | Private | New | 45.6259 | -108.4906 | 4039 | Yellowstone | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Bredette NE | Q-03 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5506 | -105.2589 | 2582 | Roosevelt | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Buffalo Lake E | B-01 |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.8536 | -112.6562 | 4121 | Glacier | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Carter N | E-4 |  | Private | Private | New | 48.0223 | -110.993 | 3492 | Choteau | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Christina W | H-6 |  | Private | Private | New | 47.4245 | -109.5207 | 3606 | Fergus | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Conrad N | C-03 |  | Private | Private | New | 48.3045 | -111.9243 | 3704 | Pondera | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Dog Gun Lake E | A-02 |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.3778 | -113.0621 | 4836 | Glacier | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Fort Kipp NW | R-04 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.2234 | -104.7713 | 2110 | Roosevelt | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Fox Crossing SW | F-01 |  | Private | Private | New | 48.8994 | -110.7485 | 3136 | Hill | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Glasgow SW | N-04 |  | Private | Private | New | 48.1244 | -106.7489 | 2272 | Valley | Montana | MT Climate Office | In-Progress | USACE performed Cultural Survey in Aug 2022 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Hogeland SW | J-02 |  | Private | Private | New | 48.8163 | -108.7802 | 3334 | Blaine | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Inverness N | F-02 |  | Private | Private | New | 48.7189 | -110.7097 | 3208 | Hill | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Inverness S | F-03 |  | Private | Private | New | 48.3754 | -110.7126 | 3065 | Hill | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Judith Gap | G-8 |  | Private | Private | New | 46.7189 | -109.7684 | 4646 | Judith Basin | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Lake Thibadeau W | H-02 |  | Private | Private | New | 48.746 | -109.6417 | 2627 | Hill | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Larslan SW | O-03 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5267 | -106.243 | 2936 | Valley | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Medicine Lake W | R-03 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.52 | -104.731 | 2474 | Sheridan | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Mission Lake S | B-02 |  | Tribal Lands | Sovereign Tribal jurisdiction by Blackfeet Tribe | New | 48.5273 | -112.6334 | 4147 | Glacier | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Mosby SE | L-08 |  | Private | Private | New | 46.9362 | -107.6511 | 3176 | Garfield | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Canyon Ferry N | C-8 | CFDM8 | Federal | USFS | New | 46.6473 | -111.6222 | 4262 | Broadwater | Montana | MT Climate Office | In-Progress | Install 2023 | PY4 | TO3 MT (FY22) | 2022-09-30 | 2023-09-30 | 2024-09-30 | USACE Contractor | Aug 2022 | 2022-08-31 |  | 2022-10-01 |  |  |  |  | To steep to install
Mt Lebanon SE | E-01 |  | Private | Private | New | 48.8523 | -111.0375 | 4121 | Liberty | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Nashua NE | O-04 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1961 | -106.3213 | 2380 | Valley | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Ophiem S | O-02 |  | Private | Private | New | 48.7878 | -106.3862 | 3117 | Valley | Montana | MT Climate Office | In-Progress | USACE performed Cultural Survey in Aug 2024 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA >160
Poplar N | Q-04 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1785 | -105.2164 | 2137 | Roosevelt | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Tampico N | N-03 |  | Private | Private | New | 48.3646 | -106.8509 | 2158 | Valley | Montana | MT Climate Office | In-Progress | USACE performed Cultural Survey in Aug 2023 | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Volt N | P-03 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.5423 | -105.6621 | 2392 | Roosevelt | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Wetzel NE | A-01 |  | Private | Private | New | 48.7795 | -113.1185 | 4459 | Glacier | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Winifred NE | I-5 |  | Private | Private | New | 47.7319 | -109.2019 | 3220 | Fergus | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Wolf Point NW | P-04 |  | Tribal Lands | Sovereign Tribal jurisdiction by Fort Peck Tribes | New | 48.1745 | -105.7379 | 2231 | Roosevelt | Montana | MT Climate Office | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) | 2023-09-18 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Sunburst NW | C-01 |  | Private | Private | New | 48.915 | -112.0222 | 3743 | Toole | Montana | MT Climate Office | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) Planned | [12 empty] | FPPA >160
Hill S | E-02 |  | Private | Private | New | 48.6887 | -111.1279 | 3606 | Liberty | Montana | MT Climate Office | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO4 MT (FY23) REMOVED | [12 empty] | FPPA >160 - Land owner pulled out of location
Jenne Trail (miller) | P-19 |  | Private | Private | New | 43.378 | -105.5253 | 4845 | Converse | Wyoming | Wyoming Mesonet | Available | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2022-10-31 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. ; AKA Miller - Needs to move -working with landowner on new location
Granite Peak | Q-20 |  | Private | Private | New | 42.9384 | -105.2259 | 5040 | Converse | Wyoming | Wyoming Mesonet | Available | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2023-01-12 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. ; Needs new language in landuse so needs to go through University to approve changes.
Dull Center | Q-19 |  | Private | Private | New | 43.2854 | -105.1376 | 4782 | Converse | Wyoming | Wyoming Mesonet | In-Progress | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete |  | 2023-01-12 |  |  |  |  | ENV. - Sage Grouse - Thunder Basin Core Habitat Area - no constuction activties between March 15 - June 3-. Seed distrubed areas with native seed. Implement nesting, perching deterrents ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey. .
Round Rock | O-19 |  | Private | Private | New | 43.4138 | -105.8886 | 5420 | Converse | Wyoming | Wyoming Mesonet | In-Progress | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete |  | 2023-01-12 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Hollcroft | O-15 |  | Private | Private | New | 44.5263 | -106.1102 | 3817 | Johnson | Wyoming | Wyoming Mesonet | In-Progress | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete |  | 2022-10-31 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Camino | N-17 |  | Private | Private | New | 44.0091 | -106.4436 | 4806 | Johnson | Wyoming | Wyoming Mesonet | In-Progress | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete |  | 2023-01-12 |  |  |  |  | ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Crago | S-14 |  | Private | Private | New | 44.9586 | -104.2547 | Need to fill in | Need to fill in | Wyoming | Wyoming Mesonet | In-Progress | Install 2024 | PY4 | TO4 WY (FY23) | 2024-02-23 | 2024-09-30 | 2025-09-30 | USACE Staff | Complete | Complete | [6 empty] | Note this location has BLM land within 0.25 miles to the east and west, but currently avoids it. Also, site is located in sage grouse general habitat, 3+ miles from an active LEK. ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Watt | N-15 |  | Private | Private | New | 44.4846 | -106.8214 | 4502 | Johnson | Wyoming | Wyoming Mesonet | Removed | Install 2024 | PY4 | TO4 WY (FY23) |  |  |  |  | Complete | Complete |  | 2022-10-31 |  |  |  |  | ENV - Burrowing Owl, burrowing owl - do survey in June and if you see anything delay construction until Sept 16th OR don't do survey and delay construction. ENV. Ferruginous Hawk, Golden Eagle - Delay all activity until Aug 1 OR a single visit survey conducted no earlier than mid-May for nests locations that are within lin-of-sight of the project area. Use a spotting scope and use accessible roads within 1 mile of project area to survey.
Bremen 3W | AC-5 |  | Private | Private | New | 47.7458 | -99.3184 | 1563 | Wells | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Buford 3SE | T-5 |  | Private | Private | New | 47.9707 | -103.9259 | 1868 | Wiliams | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Cedar Lake 3W | V-10 |  | Private | Private | New | 46.2839 | -103.0284 | 2766 | Slope | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Elgin 10NW | X-9 |  | Private | Private | New | 46.5011 | -101.9861 | 2387 | Grant | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Hofflund | U-4 | HOFN8 | University | NDSU | Existing | 48.1644 | -103.1082 | 1906 | Williams | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Hurdsfield NW | AB-6 |  | Private | Private | New | 47.4511 | -99.9372 | 1903 | Wells | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | ENV. - USFWS Wetland easement - site installation and access avoids these wetlands. No SUP needed.
Lefor 10SE | W-9 |  | Private | Private | New | 46.5883 | -102.3851 | 2564 | Hettinger | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Camp Crook 9SSW | T-13 |  | Private | private | New | 45.4235 | -104.0168 | 3287 | Harding | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Erwin 5W | AH-15 |  | Private | private | New | 44.4951 | -97.5325 | 1773 | Kingsbury | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Fairburn 15ENE | V-18 |  | Private | private | New | 43.7387 | -102.9226 | 2939 | Custer | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Hurley 5SW | AI-19 |  | Private | private | New | 43.2351 | -97.1717 | 1290 | Turner | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Iona 5S | AD-18 |  | Private | private | New | 43.4642 | -99.439 | 1932 | Gregory | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Kadoka 5WNW | Y-17 |  | Private | private | New | 43.874 | -101.5916 | 2355 | Jackson | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Liberty 5E | W-5 | LBTN8 | Private | Private | Existing | 47.9143 | -102.2162 | 2041 | Mountrail | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Livona 5S | AA-9 |  | Private | Private | New | 46.4359 | -100.5677 | 1690 | Emmonds | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Werner Mandaree 9E | W-6 |  | County | Dunn County | New | 47.4015 | -102.5039 | 2220 | Dunn | North Dakota | NDAWN | Candidate | Re-Submitted as Candidate in April 2024 in replacement for Mandaree; In-Progress with Env. & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress |  | 2022-09-29 |  |  |  |  | April 19 2024 update - NDAWN sent replacement on different property. Now called Werner. CUL. - Likely going to be removed bc on historic site of some kind. Working with landowner to see other options. July 24 ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.
Manning 4SW | V-7 |  | University | NDSU | New | 47.1925 | -102.8325 | 2442 | Dunn | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Max 3N | Y-5 |  | Private | Private | New | 47.87 | -101.3143 | 2180 | Ward | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
New Salem 6SE | Y-8 |  | Private | Private | New | 46.7678 | -101.342 | 2186 | Morton | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Picardville 6SW | AA-6 |  | Private | Private | New | 47.4154 | -100.673 | 1896 | Sheridan | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS; ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.; ENV. - USFWS Wetland easement - site installation and access avoids wetlands. No SUP needed.
Powers Lake 7SE | W-3 | POLN8 | Private | Private | Existing | 48.4841 | -102.5608 | 2298 | Mountrail | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS; ENV. - Dakota Skipper - If habitat is determined to be present by surveys conducted in the summer of 2023, occupancy surveys shall be conducted by a USFWS permitted surveyor following the 2022 Dakota Skipper Survey Protocol.
Pyramid Park | U-8 |  | University | NDSU | New | 46.7814 | -103.3584 | 2620 | Billings | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Ross 9SE | W-4 | RSSN8 | Private | Private | New | 48.1962 | -102.4653 | 2341 | Mountrail | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Wirch 7NW | AD-10 |  | Private | Private | New | 46.1432 | -99.0659 | 1971 | McIntosh | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29
Zap 11N | X-6 |  | Private | Private | New | 47.4367 | -101.9714 | 2188 | Mercer | North Dakota | NDAWN | In-Progress | Install 2024 | PY4 | TO5 ND (FY23) | 2023-09-12 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete |  | 2022-09-29 |  |  |  |  | FPPA Form submitted to NRCS
Martin 4ENE | Y-19 |  | Private | private | New | 43.1991 | -101.6512 | 3197 | Bennett | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Opal 8WNW | V-14 |  | Private | private | New | 44.9196 | -102.7539 | 2645 | Meade | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Orland 5ENE | AI-17 |  | Private | private | New | 43.9146 | -97.0898 | 1752 | Lake | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Rockham 6SSE | AE-14 |  | Private | private | New | 44.8223 | -98.7965 | 1365 | Hand | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Scenic 6ESE | W-18 |  | Private | private | New | 43.7574 | -102.4421 | 2679 | Pennington | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Seneca 15SSE | AD-14 |  | Private | private | New | 44.8572 | -99.4144 | 1921 | Hyde | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Union Center 16NW | V-15 |  | Private | private | New | 44.7047 | -102.8964 | 2810 | Meade | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Newcastle 13SSW | S-18 | NCMW4 | Private | Private | New | 43.6662 | -104.2619 | 3804 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | 2023-07-26 | 2022-08-27 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Upton 9S | R-17 | UPMW4 | Private | Private | New | 43.9643 | -104.6376 | 4373 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | 2023-09-20 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Weston B (Osage 2ENE) | S-17 | OSMW4 | Private | Private | New | 43.9938 | -104.3791 | 4544 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-06-27 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | 2023-09-30
Crook 7 (Biddle 18SE) | Q-14 | BDMW4 | Private | Private | New | 44.953 | -105.0407 | 3895 | Crook | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | USACE Staff | Complete Aug 2022 | 2022-09-16 | 2023-08-10 | 2022-10-15 | 2024-02-03 | Outstanding | 2023-09-29 | Incomplete
Osage 31SW | R-18 | RKMW4 | Private | Private | New | 43.6795 | -104.8825 | 4305 | Weston | Wyoming | Wyoming Mesonet | Complete | Install 2023 | PY3 | TO3 WY (FY22) | 2022-11-30 | 2023-09-30 | 2024-09-30 | FY22 Solv Contract | Complete Aug 2022 | 2022-08-31 | 2023-07-25 | 2022-08-27 | 2024-02-03 | Outstanding | 2023-09-29 | 2024-04-17
Wall Lake 7WSW | AI-18 |  | Private | private | New | 43.4885 | -97.0795 | 1469 | Turner | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) | 2023-11-08 | 2024-09-30 | 2025-09-30 | USACE | Complete | Complete
Artesian 13N | AG-16 |  | Private | private | New | 44.1895 | -97.9713 | 1318 | Sanborn | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Blunt 11S | AB-16 |  | University | SDSU | New | 44.3541 | -99.9997 | 1762 | Hughes | South Dakota | SD Mesonet | In-Progress | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) |  |  |  | USACE Staff | Complete | Complete
Fort Pierre 6WSW | AA-16 |  | Private | private | New | 44.3213 | -100.4756 | 1801 | Stanley | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete
Mission Ridge 14SSE | AA-15 |  | Private | private | New | 44.4939 | -100.6937 | 2061 | Stanley | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete
Murdo 9NNW | AA-17 |  | Private | private | New | 44.0106 | -100.7678 | 2246 | Jones | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Springfield 8WNW | AG-20 |  | Private | private | New | 42.8805 | -98.0471 | 1429 | Bon Homme | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted: removed landowners backed out; Phone convo with Nathan Edwards on 27 Nov 2023
Alexandria 6SW | AG-18 |  | Private | private | New | 43.655 | -97.8942 | 1291 | Hanson | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned | [12 empty] | Landowner backed out - Removed
Smithwick 4SW | U-19 |  | Private | private | New | 43.2666 | -103.2909 | 3365 | Fall River | South Dakota | SD Mesonet | Removed | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO6 SD (FY23) Planned | [12 empty] | Landowner backed out - Removed
Cherry Creek 10NE | Y-15 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 44.7079 | -101.3658 | 2042 | Ziebach | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Isabel 3WSW | Y-13 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.3864 | -101.4925 | 2360 | Ziebach | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete
Lantry 5NNW | Y-14 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.087 | -101.4843 | 2329 | Dewey | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Parade | Z-14 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.0239 | -101.0771 | 2412 | Dewey | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete | [6 empty] | FPPA Site - Score >160; AD-1006 form submitted
Ridgeview 8ENE | AA-13 |  | Private on Tribal Lands | Cheyenne River Reservation | New | 45.1455 | -100.673 | 2001 | Dewey | South Dakota | SD Mesonet | Available | Submitted as Candidate in Fall 2022; In-Progress with Env. & Cultural | PY4 | TO7 SD (FY23) Planned |  |  |  | USACE Staff | Complete | Complete
Herreid 2NNW | AB-11 |  | Private | Private | New | 45.8664 | -100.0909 | 522 | Campell | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Gettysburg 14W | AB-14 |  | Private | Private | New | 45.0057 | -100.2423 | 570 | Potter | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Mina 4ESE | AE-12 |  | Private | Private | New | 45.4054 | -98.6834 | 425 | Brown | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Platte 15WNW | AE-18 |  | Private | Private | New | 43.4992 | -99.0929 | 529 | Charles Mix | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Brentford 2E | AF-13 |  | Private | Private | New | 45.1544 | -98.2781 | 397 | Spink | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Frankfurt 5W | AF-14 |  | Private | Private | New | 44.8859 | -98.4066 | 394 | Spink | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Hays N | J-4 |  | Tribal Lands | Fort Belknap Tribes | New | 48.1978 | -108.7055 | 2967 | Blaine | Montana | MT Climate Office | Removed | Submitted as candidate site Oct 2021 - Fort Belkap THPO Cleared | PY4 | Unk. Timeline |  |  |  | Tribe | Complete | [7 empty] | Getting resited
Avon 3E | AG-20 |  | Private | Private | New | 43.0096 | -98.0002 | 468 | Bon Homme | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
DY Junction | J-05 |  | NGO | American Prairie Foundation | New | 47.7401 | -108.7227 | 3090 | Phillips | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Sun Prairie | L-05 |  | NGO | American Prairie Foundation | New | 47.7689 | -107.6761 | 2702 | Phillips | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Brusett E | M-06 |  | Private | Private | New | 47.4376 | -107.1188 | 2944 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Cohagen S | N-08 |  | Private | Private | New | 46.9123 | -106.6809 | 2982 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Edwards E | M-07 |  | Private | Private | New | 47.178 | -107.1767 | 2872 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Van Norman S | O-07 |  | Private | Private | New | 47.2142 | -106.2268 | 2527 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Cohagen N | N-07 |  | Private | Private | New | 47.1207 | -106.6444 | 2903 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Rock Springs N | O-08 |  | Private | Private | New | 46.8853 | -106.2137 | 2769 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Content | L-04 |  | Private | Private | New | 48.0177 | -107.5792 | 2320 | Philllips | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Wagner SW (formerly Dodson) | K-04 |  | Private | Private | New | 48.2629 | -108.1489 | 2560 | Phillips | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Blazier Butte | M-08 |  | Private | Private | New | 47.0098 | -107.0051 | 3259 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Kester School S | N-06 |  | Private | Private | New | 47.5584 | -106.6641 | 2599 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Weldon SW | O-06 |  | Private | Private | New | 47.5536 | -106.1103 | 2436 | McCone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Brockway | P-07 |  | Private | Private | New | 47.3102 | -105.7745 | 2562 | McCone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Vida W | P-05 |  | Private | Private | New | 47.8009 | -105.7896 | 2536 | McCone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Circle N | P-06 |  | Private | Private | New | 47.5882 | -105.6622 | 2641 | McCone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Vida NE | Q-05 |  | Private | Private | New | 47.9228 | -105.3495 | 2299 | McCone | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Crane W | S-06 |  | Private | Private | New | 47.5696 | -104.3186 | 2113 | Richland | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Barth Spring | M-05 |  | Private | Private | New | 47.8242 | -107.2374 | 2913 | Valley | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Brusett NW | L-06 |  | Private | Private | New | 47.522 | -107.5156 | 3306 | Garfield | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Kremlin NW | G-02 |  | Private | Private | New | 48.7389 | -110.2174 | 2755 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Cleveland N | I-03 |  | Private | Private | New | 48.3868 | -109.1378 | 3065 | Blaine | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Simpson | G-01 |  | Private | Private | New | 48.9283 | -110.1941 | 2781 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Warrick S | H-04 |  | Private | Private | New | 47.9893 | -109.6392 | 3532 | Hill | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Bootlegger S CG SW | D-03 |  | Private | Private | New | 48.3147 | -111.3428 | 3228 | Toole | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Ethridge N | C-02 |  | Private | Private | New | 48.6111 | -112.1457 | 3498 | Toole | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Augusta N | B-05 |  | Private | Private | New | 47.5853 | -112.36 | 4321 | Teton | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Fairfield | C-05 |  | Private | Private | New | 47.6846 | -111.9394 | 3906 | Teton | Montana | MT Climate Office | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 MT (FY24) Planned
Fort Yates 2W | AA-10 | FYTN8 | Tribal Lands | Standing Rock Sioux Tribe (Sitting Bull College) | Existing - Moved > 100ft (670 ft) | 46.0846 | -100.6792 | 1786 | Sioux | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Kintyre 3S | AB-9 |  | Private | Private | New | 46.5013 | -99.9689 | 1958 | Emmons | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Heaton 1S | AC-6 |  | City | Heaton Township | New | 47.4619 | -99.544 | 1725 | Wells | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Tappen 3E | AC-7 | TAPN8 | Private | Private | Existing - Moved < 50 ft | 46.8855 | -99.5751 | 1833 | Kidder | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Neudorf 10SW (Erble Site) | AC-9 |  | Private | Private | New | 46.5001 | -99.3664 | 1956 | Logan | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Woodworth 2NE | AD-7 |  | Private | Private | New | 47.154 | -99.2687 | 1957 | Stutsman | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Jud 1S | AD-9 |  | Private | Private | New | 46.5151 | -98.8918 | 1728 | LaMoure | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Ellendale 4NE | AE-10 |  | Private | Private | New | 46.0529 | -98.4953 | 1459 | Dickey | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Dagmar 7WSW | S-3 | DAGM8 | Private | Private | Existing - Moved >100 Ft (235 ft) | 48.5555 | -104.3476 | 2109 | Sheridan | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Watford City 3SW | U-5 | WFCN8 | County | McKenzie County | Existing - Moved >100 Ft (30,375 ft. ) | 47.7793 | -103.3468 | 2180 | McKenzie | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Dry Fork 1SE | V-4 |  | County | Williams County | Existing - Moved < 50 ft | 48.2408 | -102.894 | 2140 | Williams | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Taylor 6NW | W-8 |  | Private | Private | New | 46.9556 | -102.5178 | 2208 | Stark | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
St. Gertrude 12S | Y-10 |  | Private | Private | New | 46.1183 | -101.3329 | 1948 | Grant | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Center 5S | Y-7 |  | Private | Private | Existing - Moved < 50 ft | 47.0519 | -101.2794 | 2026 | Oliver | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Benedict 4SE | Z-5 |  | Private | Private | New | 47.7888 | -101.0134 | 2069 | McLean | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
St. Anthony 8SW | Z-9 |  | Private | Private | New | 46.5128 | -101.0065 | 2089 | Morton | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Battleview 11N | V-3 |  | Private | Private | Existing | 48.7315 | -102.7011 | 2449 | Burke | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Marshall 5N | W-7 |  | ND State | ND Department Trust Lands | New | 47.2056 | -102.3452 | 2225 | Dunn | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Selfridge 8N | Z-10 |  | ND State | ND Department Trust Lands | New | 46.1611 | -100.9479 | 2060 | Sioux | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress
Schiffer | N 18 |  | Private | Private | New | 43.6063 | -106.5404 | 4806 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Dead Horse Ranch | N 19 |  | Private | Private | New | 43.3666 | -106.5106 | 5205 | Natrona | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Arndt | O 16 |  | Private | Private | New | 44.2828 | -106.1526 | 3937 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Mackey | P 15 |  | Private | Private | New | 44.5701 | -105.6756 | 4124 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Hines/ Davis | P 16 |  | Private | Private | New | 44.2787 | -105.6175 | 4920 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Leavitt | P 18 |  | Private | Private | New | 43.6499 | -105.6229 | 5200 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
McNally | Q 16 |  | Private | Private | New | 44.2828 | -105.2101 | 4288 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Edwards | Q 17 |  | Private | Private | New | 43.8993 | -105.2639 | 4780 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Keeline | Q 18 |  | Private | Private | New | 43.6596 | -105.1074 | 4504 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Kremers | R 20 |  | Private | Private | New | 43.0416 | -104.5764 | 4536 | Niobrara | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Shorma-Meade Creek | M 15 |  | Private | Private | New | 44.704 | -106.8614 | 4158 | Sheridan | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
SR Cattle | N 14 |  | Private | Private | New | 44.9076 | -106.6008 | 3823 | Sheridan | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Camino 2 (Changed from Camino) | N 16 |  | Private | Private | New | 44.2353 | -106.6878 |  | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Rogers | O 14 |  | Private | Private | New | 44.9391 | -105.9224 | 3535 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Christensen | O 17 |  | Private | Private | New | 43.9194 | -105.9827 | 4825 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Morse | O 18 |  | Private | Private | New | 43.6053 | -106.1908 | 5016 | Johnson | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Manor | P 14 |  | Private | Private | New | 44.9575 | -105.6085 | 3976 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Innes | P 17 |  | Private | Private | New | 43.9356 | -105.8274 | 4973 | Campbell | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
BLM | L 17 |  | Federal | Bureau of Land Management | New | 43.9816 | -107.4564 | 4810 | Washakie | Wyoming | Wyoming Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO5 WY (FY24)
Springview 2W | AC-20 | SVWN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.8282 | -99.7958 | 2461 | Keya Paha | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Sparks 3E | AB-20 | SKSN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.9592 | -100.2093 | 2857 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Kilgore 5E | AA-20 | KLGN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.9196 | -100.8578 | 2844 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Merriman 7E | Y-20 | MEAN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.9178 | -101.5621 | 3304 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Crookston 17S | AA-21 | COON1 | State | Nebraska Board of Educational Lands and Funds | New | 42.6948 | -100.8384 | 2894 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Wood Lake 3SE | AB-21 | WDLN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.6139 | -100.1996 | 2669 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Ainsworth 5N | AC-21 | AINN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.6144 | -99.8466 | 2502 | Brown | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Bassett 8N | AD-21 | BATN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.7006 | -99.4979 | 2133 | Rock | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Cody 4SW | Z-20 | CODN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.8773 | -101.272 | 3129 | Cherry | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Harrison 15S | T-22 | HIMN1 | State | Nebraska Board of Educational Lands and Funds | New | 42.4819 | -103.7894 | 4713 | Sioux | Nebraska | NE Mesonet | Candidate | Submitted as Candidate Fall 2023; In-Progress with Env & Cultural | PY5 | TO 4 NE (FY24) Planned
Carthage 3E | AH-16 |  | Private | Private | New | 44.1673 | -97.6605 | 453 | Miner | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Kranzburg 6WSW | AI-14 |  | Private | Private | New | 44.8491 | -97.0304 | 538 | Codington | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO8 SD (FY23) Planned
Buffalo 8W | T-12 |  | Private | Private | New | 45.571 | -103.7185 | 933 | Harding | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Belle Fourche 18N | T-14 |  | Private | Private | New | 44.9673 | -103.7712 | 964 | Butte | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
New Underwood 10N | V-16 |  | Private | Private | New | 44.235 | -102.8288 | 867 | Meade | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Bison | W-12 |  | Private | Private | Existing | 45.5182 | -102.4866 | 829 | Perkins | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Bison 20SSE | W-13 |  | Private | Private | New | 45.2552 | -102.3204 | 736 | Perkins | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Elm Springs | W-16 |  | Private | Private | New | 44.3142 | -102.486 | 814 | Meade | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Philip 10 NNE | Y-16 |  | Private | Private | New | 44.1817 | -101.5261 | 711 | Haakon | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Hayes 14NNW | Z-15 |  | Private | Private | New | 44.5596 | -101.1418 | 625 | Stanley | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Carter 6SSW | AB-19 |  | Private | Private | New | 43.3075 | -100.2552 | 715 | Todd | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Harrold 8NW | AC-15 |  | Private | Private | New | 44.6109 | -99.8298 | 506 | Sully | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Britton 7E | AG-11 |  | Private | Private | New | 45.7778 | -97.6052 | 481 | Marshall | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Lake City 8E | AH-11 |  | Private | Private | New | 45.7359 | -97.2537 | 607 | Marshall | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Manderson 16N | W-19 |  | Tribal Lands | Oglala-Sioux Tribe | New | 43.4759 | -102.5022 | 840 | Oglala Lakota | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Pine Ridge 3NE | W-20 |  | Tribal Lands | Oglala-Sioux Tribe | New | 43.046 | -102.4652 | 1039 | Oglala Lakota | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Kyle | X-19 |  | Tribal Lands | Oglala-Sioux Tribe | New | 43.4172 | -102.1711 | 889 | Oglala Lakota | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Batesland | X-20 |  | Tribal Lands | Oglala-Sioux Tribe | New | 43.1311 | -102.0994 | 1045 | Bennett | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Wanblee 5E | Y-18 |  | Tribal Lands | Oglala-Sioux Tribe | New | 43.5885 | -101.5609 | 827 | Jackson | South Dakota | SD Mesonet | Candidate | Candidate Feb 2024; In-Progress with Env. & Cultural |  | TO9 SD (FY24)
Bath 3W | AF-12 |  | Commercial |  | New | 45.4722 | -98.3785 | 1297 | Brown | South Dakota | SD Mesonet | Available | Submitted as candidate site Oct 2021; Pending Issues | PY4 | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Chelsea 6S | AE-13 |  | Private |  | New | 45.0847 | -98.7433 | 1351 | Faulk | South Dakota | SD Mesonet | Available | Submitted as candidate site Oct 2021; Pending Landowner issues | PY4 | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Ipswich 5SSW | AD-12 |  | Private |  | New | 45.3759 | -99.0707 | 1553 | Edmunds | South Dakota | SD Mesonet | Available | Submitted as candidate site Oct 2021; Pending Landowner issues | PY4 | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Newell 13NNW | U-14 |  | Private |  | New | 44.9002 | -103.4878 |  | Butte | South Dakota | SD Mesonet | Available | Submitted as candidate site Nov 2021; Waiting on RE | PY4 | Unk. Timeline |  |  |  | USACE Staff | Complete | Complete
Onaka 4NNW | AC-13 |  | Private |  | New | 45.245 | -99.4815 | 1878 | Edmunds | South Dakota | SD Mesonet | Available | Submitted as candidate site Oct 2021; Pending Landowner issues | PY4 | Unk. Timeline |  |  |  | USACE Contractor | Complete | Complete
Fort Belknap S | J-3 |  | Tribal Lands | Fort Belknap Tribes | New | 48.4535 | -108.7704 | 2470 | Blaine | Montana | MT Climate Office | Removed | Submitted as candidate site Oct 2021 - Fort Belkap THPO Cleared | PY4 | Unk. Timeline - Re -siting |  |  |  | Tribe | Complete | [7 empty] | Getting resited
Meadow | X-12 |  | Private on Tribal Lands | Standing Rock Reservation | New | 45.5735 | -101.9842 |  | Corson | South Dakota | SD Mesonet | Available | Submitted as candidate site Nov 2021; Pending Issues |  | Unk. Timeline |  |  |  | USACE Staff | Complete | Complete
Mobridge 8WSW | AA-12 |  | Private on Tribal Lands | Standing Rock Reservation | New | 45.4878 | -100.5773 |  | Corson | South Dakota | SD Mesonet | Available | Submitted as candidate site Nov 2021; Pending Issues |  | Unk. Timeline |  |  |  | USACE Staff | Complete | Complete
Little Missouri State Park | V-6 |  | Private | Private | New | 47.5572 | -102.7566 | 2436 | Dunn | North Dakota | NDAWN | Candidate | Submitted as Candidate in Fall 2023; In-Progress with Env & Cultural | PY5 | TO6 ND (FY24) Planned |  |  |  | USACE | In-Progress | In-Progress | [6 empty] | Received a 3rd location on April 15 2024 - In review with USACE team

## Categories
Attribute | Site | Grid Cell ID | NWS LI Name | Part of NMP? | Land Ownership Category | Landownership Detail | Site Type | Latitude | Longitude | Elevation | County | State | Owner | Site Status | Station Status Note | Project Year (PY) | Installation Task Order & Fiscal Year | Installation Task Order Date of Award | Contract Installation Deadline | O&M Period Of Performance | Operational Date | Cultural Survey and Sec 106 Responsible party | Sec 106 Status | NEPA Status (Date REC Signed) | NRCS Soil Survey Status | Candidate Site Form - Date Received | Station Report | Annual Report | Equipment Installation Complete | Data Transmission
Description | Identifier given by states - some names end in a number and direction which is the distance in miles and cardinal direction to a major city | Identifier for the UMRB Network Grid Cell that the station is assigned | 5-digit name given by the National Weather Service for sites. For sites that are not yet in the network- these are proposed names by the Mesonet | Is the site part of the National Mesonet Program? | Broad Category for landownership | Detail on landownership such as agency, tribe or other entity. | Describes if site is a new or exisiting site or existing but moved more than 100 feet. | Latitude for site | Longitude for site | Elevation in feet of station location | County which station is in. | State that site is located | Name of Climate Center that Owns the Station | The category of retrofit of the station. Future Retrofit - Exisiting site within the Network that may or may not be retrofitted. Retrofit complete- A retrofit that is already complete and operational. Retrofit In-Progress - Site is Awarded on a Task Order. Retrofit Planned - Site eligibility is being assessed fo future task order. | A general note to signify where a station is at in the UMRB Network Cycle and if there are any special notes or changes. | The UMRB Network Project Year that the station is associated with | Name of Task Order (TO) that site is included on e.g. TO2 for ND and SD, T01 for NE, etc. and the associated Fiscal Year | Date that the TO was awarded. Null means not yet awarded. | Date that equipment must be installed by and site MUST be operational according to USACE Contract. Null means not yet awarded or unknown. | Date that USACE will provide O&M until. This is typically one year after the installation deadline. | Date that the Mesonets have stated in their work plans that they will have the site operational by. | Repsonsible Party for Completing NEPA and Sec 106 Work. | The status of the cultural clearance process | Date that REC (NEPA) was signed. Null [Not Begun], Complete - Date | Date that the Soil Assessment fieldwork was completed. | Date that the Candidate Site Form (sub for Site Report) was submitted and recevied. | Date that the State Report was submitted and recevied. | Date that the Annual Report was submitted and recevied. | Date that equipment installation is reported completed | Date that data was reported transmitting to USACE or MADIS.
Options (may not be all inclusive for some categories) | Wapiti 6E | I-20 | E.g. SHMW4 | Y (Yes) | Private | University of Wyoming | New |  |  |  |  | Montana | MT Climate Office | Candidate | Notes. | PY1 | Intitial Purchase Order | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | USACE Contractor | "Null"- Work not yet begun | "Null" - Work not yet begun | Null [Not yet complete] | Null [Not Submitted or was a site that existed prior to candidate site form ] | null [not submitted], | null [not submitted] | Null [Not yet complete] | Null [Data not yet transmitting]
| Worland | S-15 |  | N (No) | City | USDA | Existing |  |  |  |  | Nebraska | NE Mesonet | Available |  | PY2 | TO1 MT (FY20) |  |  |  |  | USACE Staff | "In-Progress" - Cultural work is underway (Station is on a cultural Task Order) and survey needs to be done. | "In-Progress" - USACE is working on NEPA and REC | MM/DD/YYY [Date that fieldwork was completed] | MM/DD/YYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY
| ETC. | Etc. |  |  | State | BLM | Existing - Moved more than 100 Feet |  |  |  |  | North Dakota | NDAWN | In-Progress |  | PY3 | TO3 MT (FY22) |  |  |  |  | NPS | "In-Progress SHPO/THPO" - field work is done - now is it moving through the USACE and SHPO/THPO process | "Complete - DD/MM/YYYY" - Date REC is signed.
[5 empty] | Federal | etc. | [5 empty] | South Dakota | SD Mesonet | Complete |  | PY4 | TO2 ND (FY20) |  |  |  |  | Tribe | "Complete - MM/DD/YYY" - Site is culturally cleared. Date it was complete. | Flag
[5 empty] | Tribal Lands | [6 empty] | Wyoming | Wyoming Mesonet | Removed |  | PY5 | etc. |  |  |  |  | etc.
[12 empty] | Minnesota |  |  |  | PY6
[12 empty] | Iowa |  |  |  | PY7

## Sheet1
| # of Sites COMPLETE prior to this year | # of sites COMPLETE this summer | Totals | # coming up for Award FY23 - Year 4
MT | 19 | 32 | 51 | 30
ND | 31 | 15 | 46 | 18
NE | 0 | 6 | 6 | 9
SD | 29 | 21 | 50 | 23
WY | 7 | 11 | 18 | 8
TOTALS | 86* | 85 | 171 | 88
*Web Map says 84 because Cowly and Pavillion (WY) are not marked as Complete (my fault)