## All Site Info
Site | Grid Cell ID | NWS LI ID | Part of NMP? | Land Ownership | Site Type (New, Existing, Existing - Moved > 100 ft) | Latitude | Longitude | Elevation | County | State | Owner | Retrofit Category | Station Status | Station Status Note | Task Order & Fiscal Year | Date Award | Contract Installation Deadline | Cultural or NEPA Task Order | Sec 106 Responsible party | Section 106 (Date Fieldwork Scheduled, SHPO/THPO In-Progress or Complete) | NEPA (Date REC Signed) | NRCS Soil Char. Date Scheduled or Complete | Site Report | Station Report | Annual Report | Equipment Installation Complete | Data Available on Mesonet Website | Data Transmitting via USACE Oracle | Notes
Ashland E | O-12 |  | N | US Forest Service | New | 45.5733 | -106.1432 | 3185 | Powder River | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Brady NE | D-4 |  | N | Private | New | 48.1032 | -111.6643 | 3376 | Pondera | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Busby S | M-12 |  | N | Private; Tribal Lands - Northern Cheyenne Indian Reservation | New | 45.5186 | -106.9316 | 3582 | Big Horn | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Bynum W | B-4 |  | N | Private | New | 47.9572 | -112.4944 | 4439 | Teton | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Canyon Ferry N | C-8 |  | N | US Forest Service | New | 46.6478 | -111.6372 | 4262 | Broadwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Chester SW | E-3 |  | N | Private | New | 48.4477 | -111.0376 | 3103 | Liberty | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Conrad S | C-4 |  | N | Private | New | 48.06 | -112.0115 | 3778 | Pondera | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Dupuyer N | B-3 |  | N | Private | New | 48.2956 | -112.5492 | 3890 | Pondera | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Forestgrove N | I-7 |  | N | Private | New | 47.1058 | -109.0888 | 4103 | Fergus | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Fort Belknap S | J-3 |  | N | Tribal Lands - Fort Belknap Tribes | New | 48.4535 | -108.7704 | 2470 | Blaine | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Harlowton E | G-9 |  | N | Private | New | 46.413 | -109.7009 | 4086 | Wheatland | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Hays N | J-4 |  | N | Tribal Lands - Fort Belknap Tribes | New | 48.1978 | -108.7055 | 2967 | Blaine | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Lame Deer E | N-12 |  | N | Tribal Lands - N Cheyenne Tribe | New | 45.6555 | -106.4879 | 4265 | Rosebud | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Lavina N | I-9 |  | N | Private | New | 46.3989 | -108.9536 | 3684 | Golden Valley | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Lodge Grass W | L-13 |  | N | Private; Tribal Lands - Crow Reservation | New | 45.3073 | -107.5154 | 3824 | Big Horn | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Loring SW | L-2 |  | N | Private | New | 48.7716 | -107.8779 | 2821 | Phillips | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Matador Ranch | K-5 |  | N | Nature Conservancy | New | 47.9264 | -108.3359 | 3027 | Phillips | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Molt S | I-11 |  | N | Private | New | 45.8414 | -108.9592 | 3899 | Stillwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Mosby NW | K-7 |  | N | Private | New | 47.0611 | -108.098 | 2989 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Mosby S | K-8 |  | N | Private | New | 46.7823 | -107.9213 | 2805 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Musselshell | K-9 |  | N | Private | New | 46.54 | -108.0218 | 3132 | Musselshell | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Otter E | O-13 |  | N | US Forest Service | New | 45.2469 | -105.9845 | 3936 | Powder River | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Rapleje SW | H-11 |  | N | Private | New | 45.8858 | -109.4211 | 4710 | Stillwater | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Rothiemay W | H-9 |  | N | Private | New | 46.5349 | -109.348 | 4364 | Golden Valley | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Roy E | J-6 |  | N | Private | New | 47.3791 | -108.6778 | 3038 | Fergus | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Ryegate S | H-10 |  | N | Private | New | 46.1995 | -109.3111 | 4272 | Golden Valley | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Saco S | M-4 |  | N | Private | New | 48.2908 | -107.3912 | 2741 | Phillips | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Sand Springs NW | L-7 |  | N | Private | New | 47.1653 | -107.6384 | 3007 | Garfield | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Scobey NW | Q-2 |  | N | Private | New | 48.8602 | -105.4972 | 2467 | Daniels | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Springdale E | F-11 |  | N | Private | New | 45.7318 | -110.173 | 4700 | Sweet Grass | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Sun River SE | C-6 |  | N | Private | New | 47.4118 | -111.7173 | 3596 | Cascade | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Turner N | K-2 |  | N | Private | New | 48.8743 | -108.3937 | 3073 | Blaine | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Twodot E | F-9 |  | N | Private | New | 46.4468 | -110.2055 | 4643 | Wheatland | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Valentine E | K-6 |  | N | Private | New | 47.358 | -108.2438 | 2904 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
War Horse NW | J-7 |  | N | Private | New | 47.1472 | -108.5913 | 3151 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Winnett SW | J-8 |  | N | Private | New | 46.9654 | -108.5024 | 3202 | Petroleum | Montana | MT Climate Office |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Absarokee W | G-12 |  | Y |  | Existing | 45.5573 | -109.6112 | 4608 | Stillwater | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Broadview E | I-10 |  | Y |  | Existing | 46.1282 | -108.7554 | 4094.8039 | Yellowstone | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Havre ARC | H-3 |  | Y |  | Existing | 48.4891 | -109.7994 | 2721.4485 | Hill | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Ingomar NE | M-9 |  | Y |  | Existing | 46.6568 | -107.2238 | 3097.7597 | Rosebud | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Mocassin ARC | G-7 |  | Y |  | Existing | 47.0585 | -109.9535 | 4256.5488 | Judith Basin | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Roundup NE | J-9 |  | Y |  | Existing | 46.5785 | -108.4243 | 3448.1523 | Musselshell | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | T01 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Bozeman | D-11 | BMMM8 | Y |  | Existing | 45.6621 | -111.0463 | 4927 |  | Montana | MT Climate Office | 1: > 80% | Complete | Pilot Station; Data transmission to Oracle Pending | FY19 Initial Purchase Order | 2020-04-09 | 2021-09-30 | T01 | USACE Contractor | Complete | Complete | Complete | Y | Y | Y | Y | Y | Y 11/19/2021
Crow Agency E | L-12 |  | Y | Crow indian reservation | Existing | 45.5861 | -107.4383 | 3119 | Big Horn | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | TO2 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Melville SE | G-10 |  | Y |  | Existing | 46.0015 | -109.8416 | 4709.9595 | Sweet Grass | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | TO2 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Miles City | O-9 |  | Y |  | Existing | 46.4054 | -105.9543 | 2717.8396 | Custer | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | TO2 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Sidney ARC | S-5 |  | Y |  | Existing | 47.7823 | -104.2479 | 2259.8357 | Richland | Montana | MT Climate Office | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 MT |  | 2021-01-15 | TO2 | USACE Contractor | Complete | Complete | Complete | Y 12/1/21 |  |  | Y | Y | Y 11/19/2021
Benton Lake W | D-5 |  | Y |  | Existing | 47.6907 | -111.4736 | 3706.0256 | Cascade | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Big Timber SE | G-11 |  | Y |  | Existing | 45.7435 | -109.8267 | 4423.5431 | Sweet Grass | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Coffee Creek N | G-6 |  | Y |  | Existing | 47.3935 | -110.1083 | 3738.8339 | Fergus | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Conrad ARC | C-3 |  | Y |  | Existing | 48.3071 | -111.924 | 3728.3352 | Pondera | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Cooney Reservoir NW | H-12 |  | Y |  | Existing | 45.4658 | -109.2597 | 4702.0856 | Stillwater | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021 | [7 empty] | Will move slightly closer to road access
Huntley ARC | J-11 |  | Y |  | Existing | 45.9264 | -108.233 | 3054.7808 | Yellowstone | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
MDA Oilmont | D-1 |  | Y | Private | Existing | 48.7816 | -111.6011 | 3596.7739 | Toole | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
MDA Toston | C-10 |  | Y |  | Existing | 46.1365 | -111.5432 | 4066.5888 | Broadwater | Montana | MT Climate Office | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO2 MT | 2021-09-13 | 2022-09-30 | T02 | USACE Contractor | Complete | Complete - 8/30/2021
Dooley | S-2 |  | Y | Private | Existing | 48.8337 | -104.3846 |  | Sheridan | Montana | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Froid | S-4 |  | Y | US Department of Agriculture | Existing | 48.2579 | -104.4967 |  | Roosevelt | Montana | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Redstone | R-2 |  | Y | Private | Existing | 48.8246 | -104.8417 |  | Sheridan | Montana | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021
Boyd 1 | AF-20 |  |  | State Educational Lands and Funds - Leased Public | New | 42.8407 | -98.5042 | 1583 | Boyd | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Boyd 2 | AE-20 |  |  | State Educational Lands and Funds - Leased Public | New | 42.9662 | -99.1393 | 2105 | Boyd | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Cedar 2 | AI-20 |  |  | State Educational Lands and Funds - Leased Public | New | 42.7494 | -97.3975 | 1520 | Cedar | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Cherry 1 | Y-21 |  |  | State Educational Lands and Funds - Leased Public | New | 42.6154 | -101.7244 | 3619 | Cherry | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Knox 2 | AG-21 |  |  | State Educational Lands and Funds - Leased Public | New | 42.4909 | -98.2605 | 1556 | Knox | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Knox S2 | AH-20 |  |  | Tribal Lands - Santee Indian Reservation | New | 42.7506 | -97.8787 | 1580 | Knox | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Sheridan 1 | X-22 |  |  | State Educational Lands and Funds - Leased Public | New | 42.2794 | -102.1656 | 4130 | Sheridan | Nebraska | NE Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Long Pine 20S | AD-21 |  | Y | State Educational Lands and Funds - Leased Public | New | 42.2297 | -99.6581 |  | Brown | Nebraska | NE Mesonet |  | In-Progress | Awarded in Sept 2021 | FY21 TO1 NE | 2021-09-23 | 2022-09-30 |  | USACE Staff | Complete | Complete - 8/11/2021 | Summer 2022 | [6 empty] | New site
Davis Dam 2NW | T-9 |  | N | Private | New | 46.5641 | -103.6971 | 2906 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned | [13 empty] | Originally called Alpha 9SSE - NDAWN informed Cat of change on 12/6/21
Fairfield | U-7 |  | N | Private | Existing | 47.1253 | -103.2432 | 2682 | Billings | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Glen Ullin | X-8 |  | N | Private | New | 46.8045 | -102.0759 | 2450 | Morton | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Linton | AB-10 |  | Y | Private | Existing | 46.3268 | -100.2809 | 1966 | Emmons | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Marmarth 2N | T-10 |  | N | Private | New | 46.3228 | -103.9374 | 2840 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
McKenzie 2E | AA-8 |  | N | Private | New | 46.8222 | -100.3617 | 1773 | Burleigh | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Napoleon 1S | AC-9 |  | N | Private | New | 46.4863 | -99.7587 | 2007 | Logan | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
New England 5W | V-9 |  | N | Private | New | 46.5264 | -102.968 | 2718 | Slope | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Pick City 8SW | Y-6 |  | N | Private | New | 47.4747 | -101.6123 | 2045 | Mercer | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Poker Jim | T-6 |  | N | Private | Existing | 47.5025 | -103.6559 | 2092 | McKenzie | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Pretty Rock 2E | X-10 |  | N | Private | New | 46.1597 | -101.7705 | 2514 | Grant | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned | [13 empty] | Originally called Leith 15SW
Sanger | Z-7 |  | N | Private | New | 47.1668 | -100.9891 | 1689 | Oliver | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Sentinel Butte 10N | T-7 |  | N | Private | Existing | 47.0669 | -103.7933 | 2736 | Golden Valley | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Shell Lake | X-4 |  | N | Private | Existing | 48.1501 | -102.0727 | 2058 | Mountrail | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Wing | AA-7 |  | N | Private | New | 47.2719 | -100.3303 | 1973 | Burleigh | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Ypsilanti | AE-8 |  | N | Private | New | 46.7764 | -98.5236 | 1483 | Stutsman | North Dakota | NDAWN |  | Candidate | Submitted as candidate site Aug 2021 | FY22 TO Planned
Amidon | U-9 |  | N | Private | Existing | 46.4885 | -103.316 | 2883 | Slope | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 9/29/2021 |  |  |  | Y | Y | Y 11/19/2021
Bowman | U-10 |  | Y | Private | Existing | 46.1997 | -103.473 | 3032 | Bowman | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 8/28/2021 |  |  |  | Y | Y | Y 11/19/2021
Carson | Y-9 |  | Y | Private | Existing | 46.443 | -101.3738 | 2107 | Grant | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 8/12/2021 |  |  |  | Y | Y | Y 11/19/2021
Courtenay | AE-7 |  | N | Private | Existing | 47.2212 | -98.6799 | 1522 | Stutsman | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 2021 |  |  |  | Y | Y | Y 11/19/2021
Fortuna | T-2 |  | N | Private | Existing | 48.9637 | -103.8058 | 2246 | Divide | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 2021 |  |  |  | Y | Y | Y 11/19/2021
Grenora | T-3 |  | N | Private | Existing | 48.735 | -103.8812 | 2108 | Divide | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 2021 |  |  |  | Y | Y | Y 11/19/2021
Hettinger | W-11 |  | Y | University - NDSU | Existing | 46.0126 | -102.6453 | 2758 | Adams | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 9/15/2021 |  |  |  | Y | Y | Y 11/19/2021
Mott | W-10 |  | Y | Private | Existing | 46.3798 | -102.322 | 2473 | Hettinger | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 8/30/2021 |  |  |  | Y | Y | Y 11/19/2021
Ray | U-3 |  | Y | Private | Existing | 48.4009 | -103.169 | 2316 | Williams | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 2021 |  |  |  | Y except snow sensor | Y except snow | Y
Streeter | AC-8 |  | Y | University - NDSU | Existing | 46.718 | -99.4608 | 1992 | Kidder | North Dakota | NDAWN | 2: 50% – 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 8/19/2021 |  |  |  | Y | Y | Y 11/19/2021
Williston | T-4 |  | Y | University - NDSU | Existing | 48.1331 | -103.739 | 2132 | Williams | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO1 ND |  | 2021-11-30 |  |  | Complete | Complete | Complete - 9/22/2021 |  |  |  | Y | Y | Y 11/19/2021
Hazen | X-7 |  | Y | Private | Existing | 47.3018 | -101.6792 | 1849 | Mercer | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO2 ND | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete - 2/8/2021 | Complete - 8/23/2021 |  |  |  | Y except snow sensor | Y except snow | Y | next to current site, or within 200 ft
Oakes | AF-10 |  | Y | University - NDSU | Existing | 46.0667 | -98.1028 | 1323 | Dickey | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO2 ND | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete - 2/8/21 | Complete - 9/2/2021 |  |  |  | Y | Y | Y 11/19/2021 | Multiple changes to location
Robinson | AB-7 |  | Y | Private | Existing | 47.173 | -99.7982 | 1829 | Kidder | North Dakota | NDAWN | 1: > 80% | Complete | Installed in 2021 | FY20 TO2 ND | 2021-03-24 | 2021-11-30 |  |  | Complete | Complete-2/8/21 | Complete - 8/18/2021 |  |  |  | Y | Y | Y 11/19/2021
Carrington |  |  | Y | University - NDSU | Existing | 47.5086 | -99.1323 | 1561 | Foster | North Dakota | NDAWN | 3: 20% – 50% | Complete | Installed in 2021 | Not on Task Order by USACE | na | na | na |  | na | na | na | na | na | na | Y | Y | Y 11/19/2021 | Not funded by Network but network will accept data
Beach | T-8 |  | Y | Private | Existing | 46.7894 | -103.9662 | 2932 | Golden Valley | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete
Dickinson | V-8 |  | Y | University - NDSU | Existing | 46.8948 | -102.8131 | 2557 | Stark | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete
Edgeley | AE-9 |  | Y | Private | Existing | 46.3192 | -98.7661 | 1649 | LaMoure | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Garrison | X-5 |  | Y | Private | Existing | 47.7102 | -101.6795 | 2200 | McLean | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/2021
Grassy Butte 2E | U-6 |  | N | Private | Existing | 47.3865 | -103.2062 | 2688 | McKenzie | North Dakota | NDAWN |  | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202 | [7 empty] | Replacing Dunn site. All Dunn equipment being moved to this location
Jamestown | AD-8 |  | Y | Private | Existing | 46.9064 | -98.9274 | 1639 | Stutsman | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Keene 5SW | V-5 |  | N | Private | Existing | 47.8938 | -103.0482 | 2346 | McKenzie | North Dakota | NDAWN |  | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Mandan | Z-8 |  | Y | US Department of Agriculture | Existing | 46.7736 | -100.9139 | 1907 | Morton | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21
Marion | AF-9 |  | Y | Private | Existing | 46.5645 | -98.3276 | 1453 | LaMoure | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Steele | AB-8 |  | N | Private | Existing | 46.894 | -99.9927 | 1862 | Kidder | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Turtle Lake | Z-6 |  | Y | Private | Existing | 47.5679 | -100.9153 | 1927 | McLean | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete 08/17/2021 | Complete - 8/30/202
Wishek | AC-10 |  | Y | Private | Existing | 46.2599 | -99.6658 | 2219 | McIntosh | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21
Zeeland | AC-11 |  | N | Private | Existing | 46.0133 | -99.6877 | 2070 | McIntosh | North Dakota | NDAWN | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 ND | 2021-09-21 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/8/21 | [7 empty] | next to current site, or within 200 ft
Bison | W-12 | BSNS2 | Y | Federal Aviation Administration | Existing | 45.5166 | -102.4673 | 2779 | Perkins | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 5/20/2021 | [6 empty] | 21
Eagle Butte | Z-14 | EGBS2 | Y | Federal Aviation Administration | Existing | 44.9875 | -101.253 | 2439 | Ziebach | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE Contractor | Complete 3/5/21 | Complete 2/25/21 | Complete - 6/27/2019
Gettysburg | AB-14 | GTBS2 | Y | Federal Aviation Administration | Existing | 44.9888 | -99.9505 | 2059 | Potter | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Sampled in 2019 but moved | [6 empty] | 14
Lemmon |  | LMNS2 | Y | Federal Aviation Administration | Existing | 45.9189 | -102.1082 | 2575 | Perkins | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 6/3/2019 | [6 empty] | 22
Parkston |  | PSTS2 | Y | Federal Aviation Administration | Existing | 43.3819 | -97.9898 | 1414 | Hutchinson | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE | Complete 9/7/2021 | Pending - FAA Consultation | Sampled in 2019 but moved | [6 empty] | 16
Redfield |  | RDFS2 | Y | Federal Aviation Administration | Existing | 44.8579 | -98.5289 | 1300 | Spink | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Pending - FAA Consultation | Complete - 6/11/2019 | [6 empty] | 17
Webster |  | WEBS2 | Y | Federal Aviation Administration | Existing | 45.2908 | -97.5188 | 1848 | Day | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Availability (FAA Consultation) | Unk. Timeline |  |  |  | USACE | Complete 9/7/2021 | Pending - FAA Consultation | Summer 2021- on hold | [6 empty] | 18
Dakota Lakes | AB-16 | PRFS2 | Y | City | Existing | 44.2914 | -100.0084 | 1498 | Hughes | South Dakota | SD Mesonet | 1: > 80% | Candidate | Pending Available (Once land is sold to Univ in next couple years) | Unk. Timeline |  |  |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Sampled in 2019 but moved | [6 empty] | 8
Bath 3W | AF-12 |  |  | Commercial | New | 45.4722 | -98.3785 |  | Brown | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Carpenter 11WSW | AG-15 |  |  | Private | New | 44.6035 | -98.1298 |  | Beadle | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Chelsea 6S | AE-13 |  |  | Private | New | 45.0847 | -98.7433 |  | Faulk | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Colome 4NNE | AC-19 |  |  | Private | New | 43.3141 | -99.693 |  | Tripp | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Dallas 7S | AD-19 |  |  | Private | New | 43.1374 | -99.4933 |  | Gregory | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Gann Valley 14N | AE-16 |  |  | Private | New | 44.2362 | -99.0228 |  | Hand | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Ipswich 5SSW | AD-12 |  |  | Private | New | 45.3759 | -99.0677 |  | Edmunds | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Kennebec 6SSE | AC-17 |  |  | Private | New | 43.816 | -99.8254 |  | Lyman | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Long Lake 4NW | AD-11 |  |  | Private | New | 45.8998 | -99.2611 |  | McPherson | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Lowry 2S | AB-13 |  |  | Private | New | 45.2816 | -99.9774 |  | Walworth | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Ludlow 16W | T-11 |  |  | Private | New | 45.8268 | -103.7172 |  | Harding | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Menno 7ESE | AH-19 |  |  | Private | New | 43.2109 | -97.4523 |  | Hutchinson | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Midland 3ENE | Z-17 |  |  | Private | New | 44.0851 | -101.091 |  | Haakon | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Oelrichs 11SSW | U-20 |  |  | Private | New | 43.0409 | -103.3476 |  | Fall River | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Onaka 4NNW | AC-13 |  |  | Private | New | 45.2457 | -99.4808 |  | Edmunds | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Prairie City 15SSW | V-13 |  |  | Private | New | 45.3388 | -102.9195 |  | Perkins | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Raymond 5ENE | AG-14 |  |  | Private | New | 44.9374 | -97.8464 |  | Clark | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Redig 3N | U-13 |  |  | Private | New | 45.3195 | -103.5495 |  | Harding | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Spearfish 4NNW | T-15 |  |  | Private - NRCS EQIP Program | New | 44.5657 | -103.9164 |  | Lawrence | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Vivian 12S | AB-18 |  |  | Private | New | 43.7508 | -100.2963 |  | Lyman | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Wessington 3W | AE-15 |  |  | Private | New | 44.4592 | -98.7614 |  | Hand | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Woonsocket 4NNW | AF-16 |  |  | Private - NRCS Conservation Reserve Program | New | 44.1113 | -98.3103 |  | Sandorn | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Brookings | AJ-15 | BKMS2 | Y |  | Existing | 44.325 | -96.7685 | 1640 | Brookings | South Dakota | SD Mesonet | 1: > 80% | Complete | Pilot Station | FY19 Initial Purchase Order | 2020-04-08 |  |  |  | Complete | Complete | Complete - 6/13/2019 | Y | Y | Y | Y | Y | Y 11/19/2021
Caputa | V-17 | CPTS2 | Y |  | Existing | 44.0008 | -103.0008 | 2931 | Pennington | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 7/30/2021 |  |  |  | Y | Y | Y 11/19/2021
Edgemont | T-19 | EDTS2 | Y |  | Existing | 43.4737 | -103.9717 | 3710 | Fall River | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 7/29/2021 |  |  |  | Y | Y | Y 12/15/2021
Oacoma | AD-17 | OCMS2 | Y |  | Existing | 43.7982 | -99.4156 | 1443 | Lyman | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 7/2/2019 |  |  |  | Y | Y | Y 11/19/2021
Bowdle | AC-12 | BWLS2 | Y | Non - federal airport property | Existing | 45.4388 | -99.6733 | 1965 | Edmunds | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 5/2021 |  |  |  | Y | Y | Y 12/15/2021
Highmore | AD-15 | HIHS2 | Y |  | Existing | 44.5256 | -99.4601 | 1879 | Hyde | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 6/19/2019 |  |  |  | Y | Y | Y 12/23/2021
Leola | AE-11 | LLAS2 | Y |  | Existing | 45.7165 | -98.9311 | 1571 | McPherson | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete | Complete - 5/2019 |  |  |  | Y | Y | Y 12/15/2021
Union Center | W-15 | UNIS2 | Y | Non - federal airport property | Existing | 44.5665 | -102.671 | 2938 | Meade | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete -2/25/22 | Complete -7/22/2021 |  |  |  | Y | Y | Y 12/15/2021
White River | AA-18 | WRIS2 | Y | Non - federal airport property | Existing - Moved > 100ft | 43.5586 | -100.7423 | 2140 | Mellette | South Dakota | SD Mesonet | 1: > 80% | Complete | Put on hold bc of location change - now cleared for installation | FY20 TO1 SD |  | 2022-01-15 |  | USACE | Complete 9/7/2021 | Complete - 9/10/2021 | Summer 2021 - on hold |  |  |  | Y | Y | Y 12/15/2021 | This site was moved so Sec.106 and Env. was redone
Beresford | AJ-19 | BFMS2 | Y | University - SDSU | Existing - Moved > 100ft | 43.0404 | -96.9011 | 1278 | Clay | South Dakota | SD Mesonet | 1: > 80% | Complete | Sub for Martin on T01 | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete - 2/25/21 | Complete - 4/13/2021 |  |  |  | Y | Y | Y 12/23/2021 | 1
Timber Lake | Z-12 | TIMS2 | Y | City | Existing | 45.4166 | -101.085 | 2196 | Dewey | South Dakota | SD Mesonet | 1: > 80% | Complete | Sub For Faulkton on TO1 | FY20 TO1 SD |  | 2022-01-15 |  |  | Complete | Complete 2/25/2021 | Complete - 6/27/2019 |  |  |  | Y | Y | Y 12/15/2021
Cottonwood | X-17 | CTWS2 | Y |  | Existing | 43.9599 | -101.8539 | 2365 | Jackson | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO2 SD | 2021-03-20 | 2022-01-15 |  | USACE Contractor | Complete | Complete - 2/25/21 | Complete - 6/5/2019 |  |  |  | Y | Y | Y 12/15/2021
Groton | AG-12 | GOTS2 | Y |  | Existing | 45.5735 | -98.0301 | 1309 | Brown | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO2 SD | 2021-03-20 | 2021-11-30 |  |  | Complete | Complete - 2/25/21 | Complete - 6/12/2019 |  |  |  | Y | Y | Y 12/23/2021
South Shore | AI-13 | SHSS2 | Y |  | Existing | 45.1055 | -97.1024 | 1850 | Codington | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO2 SD | 2021-03-20 | 2021-11-30 |  |  | Complete 3/5/21 | Complete -2/25/21 | Complete - 6/12/2019 |  |  |  | Y | Y | Y 12/23/2021
Sturgis | U-16 | STMS2 | Y |  | Existing | 44.4245 | -103.3793 | 3237 | Meade | South Dakota | SD Mesonet | 1: > 80% | Complete |  | FY20 TO2 SD | 2021-03-20 | 2021-11-30 |  |  | Complete | Complete -2/25/22 | Complete - 6/25/2019 |  |  |  | Y | Y | Y 12/15/2021
Antelope | U-12 | ATRS2 | Y |  | Existing | 45.5193 | -103.2888 | 2903 | Harding | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/202 | Complete - 6/26/2019 | [6 empty] | 6
Flandreau | AJ-16 | FLNS2 | Y |  | Existing | 44.0867 | -96.5849 | 1624 | Moody | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 8/30/2021 | Complete - 5/30/2019 | [6 empty] | 20
Hamill | AC-18 | HMLS2 | Y |  | Existing | 43.5938 | -99.7122 | 1863 | Tripp | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Complete - 5/16/2019 | [6 empty] | 13
Jewel Cave | T-18 | JWLS2 | Y | National Park Service - Jewel Cave National Monument | Existing | 43.7343 | -103.8278 | 5672 | Custer | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | NPS | Complete 6/5/2021 | Complete - 8/30/2021 | [7 empty] | 2
Nisland | U-15 | NISS2 | Y | Bureau of Reclamation | Existing | 44.6783 | -103.5606 | 2906 | Butte | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete | Complete - 2/25/2021 | Complete - 8/2/2019 | [6 empty] | 5
Rosebud | AA-19 | RBMS2 | Y | Tribal Lands - Rosebud Sioux Tribe | Existing | 43.2002 | -100.7208 | 2808 | Todd | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | Rosebud Tribe | Complete | Complete - 8/5/2021 | Complete - 6/20/2019 | [6 empty] | 10
Sioux Falls | AJ-18 | SFSS2 | Y |  | Existing | 43.5048 | -96.7623 | 1407 | Minnehaha | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  | USACE Contractor | Complete 8/20/2021 | Complete - 8/30/2021 | Complete -6/17/2019 | [6 empty] | 9
White Lake | AE-17 | WTES2 | Y |  | Existing | 43.7372 | -98.6936 | 1637 | Aurora | South Dakota | SD Mesonet | 1: > 80% | In-Progress | Awarded in Sept 2021 | FY21 TO3 SD | 2021-09-29 | 2022-09-30 |  |  | Complete 3/5/21 | Complete 3/7/2021 | Complete - 6/21/2019 | [6 empty] | 4
Onida 13WSW | AB-15 |  | N | Private; Tribal Lands - Crow Creek Reservation | New | 44.6463 | -100.3202 |  | Sully | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Hayes 7SW | Z-16 |  | N | Private | New | 44.3123 | -101.1292 |  | Stanley | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Lower Brule 2WNW | AC-16 |  | N | Private | New | 44.0822 | -99.6111 |  | Lyman | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | Tribal Archaeologist
Ralph 11NE | V-11 |  | N | Private | New | 45.9061 | -102.9228 |  | Perkins | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Mobridge 8WSW | AA-12 |  | N | Private; Tribal Lands - Standing Rock Reservation | New | 45.4878 | -100.5773 |  | Corson | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned
Lecther 2ENE | AG-17 |  | N | Private | New | 43.9029 | -98.1096 |  | Sanborn | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Oelrichs 11ESE | V-20 |  | N | Private; Within USFS National Grasslands | New | 43.1003 | -103.0547 |  | Fall River | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Contractor
Newell 13NNW | U-14 |  | N | Private | New | 44.9002 | -103.4878 |  | Butte | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Provo 11S | T-20 |  | N | Private; Within USFS National Grasslands | New | 43.0375 | -103.7986 |  | Fall River | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Spring Creek 12WNW | Z-19 |  | N | Private; Tribal Lands- Pine Ridge Reservation | New | 43.206 | -101.2295 |  | Bennett | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned
Norris 10NNE | Z-18 |  | N | Private | New | 43.5998 | -101.1013 |  | Mellette | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Meadow 12ENE | X-12 |  | N | Private; Tribal Lands - Standing Rock Reservation; USFS National Grasslands | New | 45.5735 | -101.9842 |  | Corson | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned
Milesville 11W | X-15 |  | N | Private | New | 44.4749 | -101.8991 |  | Haakon | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Staff
Mount Vernon | AF-17 |  | N | Private | New | 43.7173 | -98.2793 |  | Davison | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned |  |  |  | USACE Contractor
Mound City 4SSW | AB-12 | MCMS2 | Y | Private; FWS Easement for Sand Lake Wetland Management District | New | 45.6715 | -100.1148 |  | Campbell | South Dakota | SD Mesonet |  | Candidate | Submitted as candidate site Nov 2021 | FY22 TO Planned
Wapati | I-15 | BBMW4 | N | Bureau of Reclamation | New | 44.4817 | -109.3085 |  | Park | Wyoming | Wyoming Mesonet | 1: > 80% | Candidate | Pending Availability (Real Estate Agreement) | Contract Mod for FY20 TO1 to replace Heart Mtn |  |  |  | USACE Staff | SHPO In-Progress | Site Moved - needs to be redone | Summer 2022 | [6 empty] | New site - This site is on the south side of Buffalo Bill Reservoir near boat ramp access. It is more than 150 meters off the water.
Cowley 4NNE | J-14 | CYMW4 | N | Bureau of Reclamation | New | 44.9298 | -108.4318 |  | Big Horn | Wyoming | Wyoming Mesonet | 1: > 80% | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE Staff | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - This site is just under 2 miles from the North Big Horn County Airport. No objections from the airport.
Pavillion 13W | I-19 | SRMW4 | N | Bureau of Reclamation | New | 43.2304 | -108.949 |  | Fremont | Wyoming | Wyoming Mesonet | 1: > 80% | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE Staff | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - Located near a house operated by Midvale Irrigation District. The site is within a grazing lease so should be protected from livestock accordingly. Otherwise this is a secure location. Midvale ID has no objections.
Shoshoni 6NNW | J-19 | BRMW4 | N | Bureau of Reclamation | New | 43.3239 | -108.1331 |  | Fremont | Wyoming | Wyoming Mesonet | 1: > 80% | Candidate | Pending Availability (Real Estate Agreement) | FY21 TO2 Planned |  |  |  | USACE Staff | Complete | Complete - 8/30/2021 | Summer 2022 | [6 empty] | New site - This site is along a very busy and popular route, in the summertime, to Tough Creek campground within Boysen State Park. Good access and should be a secure location. No objections from State Parks.
Carlile 2S | R - 16 |  |  | Private | New | 44.4485 | -104.8021 | 4344 | Crook | Wyoming | Wyoming Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Devils Tower 16WNW | Q-15 |  |  | Private | New | 44.713 | -105.014 | 4012 | Crook | Wyoming | Wyoming Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Newcastle 13SSW | S-18 |  |  | Private | New | 43.6662 | -104.2619 | 3804 | Weston | Wyoming | Wyoming Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Osage 31SW | R-18 |  |  | Private | New | 43.6795 | -104.8825 | 4305 | Weston | Wyoming | Wyoming Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Upton 9S | R-17 |  |  | Private | New | 43.9791 | -104.6425 | 4373 | Weston | Wyoming | Wyoming Mesonet |  | Candidate | Submitted as candidate site Oct 2021 | FY22 TO Planned
Sheridan | M-14 | SHMW4 / SHERIDAN 7ENE | N | University - WY |  | 44.8407 | -106.839 | 3738 | Sheridan | Wyoming | Wyoming Mesonet | 1: > 80% | Complete | Pilot Station | FY19 Initial Purchase Order | 2020-04-10 |  |  |  | Complete | Complete | Summer 2022 | Y | Y | Y | Y | Y | Y
Fort_Washakie | I-20 | FWMW4 | N | Tribal Lands - Wind River Tribe | New | 43.005 | -108.8803 | 5571 | Fremont | Wyoming | Wyoming Mesonet | 1: > 80% | In-Progress | Was awarded onTO1 (FY20) for WY- had to be moved due to land use change - new location secured - need to redo 106/NEPA | FY20 TO1 WY |  |  |  | USACE Staff | Needs to be Redone | Needs to be Redone | [7 empty] | Was listed on Task Order 1 for WY- Unable to be installed because of land use change
Powell | I-14 | PLMW4 / POWELL 2N | N | University - WY |  | 44.7764 | -108.759 | 4372 | Park | Wyoming | Wyoming Mesonet | 1: > 80% | Complete |  | FY20 TO1 WY |  |  |  |  | Complete | Complete | Summer 2022
Worland | K-17 | WRMW4 | N | Bureau of Reclamation | New | 44.003 | -107.9061 | 4203 | Washakie | Wyoming | Wyoming Mesonet | 1: > 80% | In-Progress | Was awarded onTO1 (FY20) for WY- had to be moved due to land use change - new location secured - need to redo 106/NEPA | FY20 TO1 WY |  |  |  | USACE Staff | SHPO In-Progress | Needs to be Redone | [7 empty] | Was listed on Task Order 1 for WY- Unable to be installed because of land use change

## Categories
Attribute | Site | NWS LI Name | Part of NMP? | Land Ownership | Site Type | Orig Lat | Orig.Lon | Proposed Lat | Proposed Long | Elevation | County | State | Owner | Retrofit Category | Site Status | Task Order | Date Award | Contract Deadline | Operational Date | Sec 106 and NEPA Responsible party | Sec 106 Status | Sec 106 APE (Area of Potential Effect) | Nepa/REC | NRCS Soil Characterization | Site Report | Station Report | Annual Report | Installation Complete | Data Transmission
Description | Identifier given by states - some names end in a number and direction which is the distance in miles and cardinal direction to a major city | 5-digit name given by the National Weather Service for sites. For sites that are not yet in the network- these are proposed names by the Mesonet | Is the site part of the National Mesonet Program? | Type of land ownership where the station is e.g. private lands, state lands, public lands | Describes if site is a new or exisiting site or existing but moved more than 100 feet. | Orginal latitude at existing site | Original Longitude at existing site | Proposed Latitude for new site | Proposed Longitude for new site | Elevation in feet of station location based on Proposed Lat and Proposed Long. | County which station is in. | State that site is located | Name of Climate Center that Owns the Station | The percentage of a site being replaced base on cost. Category 1 - 80%; Category 2 - 50 to 80% percent; Category 3 - 20 to 50%; Category 4 - less than 20%. | The category of retrofit of the station. Future Retrofit - Exisiting site within the Network that may or may not be retrofitted. Retrofit complete- A retrofit that is already complete and operational. Retrofit In-Progress - Site is Awarded on a Task Order. Retrofit Planned - Site eligibility is being assessed fo future task order. | Name of Task Order (TO) that site is included on e.g. TO2 for ND and SD, T01 for NE, etc. | Date that the SATOC was awarded. Null means not yet awarded. | Date that site MUST be operational according to USACE Contract. Null means not yet awarded or unknown. | Date that the Mesonets have stated in their work plans that they will have the site operational by. | Repsonsible Party for Completing NEPA and Sec 106 Work. | Where are we at in the cultural clearance process | Type (Size) of Sec 106 Survey done based on area. Existing site is 1 -acre. Moved more that 100 feet from exisiting site or new site is 3- acres. | Date that REC (NEPA) was signed. Null [Not Begun], Complete - Date | Date that the Soil Assessment fieldwork is scheduled. | Tracks if the Site Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Tracks if the Station Report has been submitted and Received | Date that installation is reported completed | Status of Data Transmission with MADIS
Options (may not be all inclusive for some categories) | E.g. Wapiti 6E | E.g. SHMW4 | Y (Yes) | Private | New | [6 empty] | Montana | MT Climate Office | 1: > 80% | Existing | Intitial Purchase Order | MM/DD/YYYY | MM/DD/YYYY | MM/DD/YYYY | USACE Contractor | MM/DD/YYYY- Anticipated data of field workd | 1-acre | Null | Null [No date scheduled] | Null [Not Submitted] | null [not submitted], | null [not submitted], | MM/DD/YYYY | Site not operational
| Worland |  | N (No) | City | Existing | [6 empty] | Nebraska | NE Mesonet | 2: 50% – 80% | Candidate | TO1 |  |  |  | USACE Staff | In-Progress SHPO/THPO - field work is done - now is it moving through the USACE and SHPO/THPO process | 3-acre | In-Progress | MM/DD/YYY [Date that fieldwork is scheduled] | N [Task Order Awarded but report not submitted] | N [station online but report not submitted], | N [station online for 1 year but report not submitted], |  | Site not transmitting
|  |  |  | State | Existing - Moved more than 100 Feet | [6 empty] | North Dakota | NDAWN | 3: 20% – 50% | Available | TO2 |  |  |  | NPS | Complete - all work is complete |  | Complete - DD/MM/YYYY | I [Fieldwork Complete, Lab work not complete] | Y [Report Submitted and Received] | Y [report submitted] | Y [report submitted] |  | Site transmitting
|  |  |  | Federal (Many agencies) | [7 empty] | South Dakota | SD Mesonet | 4: < 20% | In-Progress | TO3 |  |  |  | Rosebud Tribe |  |  | Flag | C [Fieldwork and Lab work Complete]
|  |  |  | Tribal Lands | [7 empty] | Wyoming | WACNet |  | Complete | TO4
TO5